STRUCTURAL CONSTRUCTION WORK

LEVEL-IV

Based on October 2023, Curriculum Version 2

Module Title: - labor and material schedules for ordering

Module code: EIS SCW4 04 0322

Nominal duration: 100 Hour

Prepared by: Ministry of Labor and Skills

October, 2023

Addis Ababa, Ethiopia

- Contents

Acronym	4

Acknowledgment	5

Introduction to the Module	6

Unit one:  Contract conditions	7

1.1	Concept Produce labor and material schedules for ordering	8

1.2	Contractual requirements	9

1.3	Color selections	15

1.4	Contract variations	17

Self-cheek 1.1	18

2	Unit two:   Material and labor schedules, overlays and orders.	20

2.1.	Material, labor schedules, overlays and orders	21

2.2.	Overlays	23

2.3.	Producing relevant overlay drawings	26

2.4.	Contract details and instructions	27

2.5.	Applying contract rates	28

Self-check -2	30

3	Unit three:   Site files Preparation	31

3.1	Site documents	32

3.2	Call Forward Sheets	34

Self –check 3.1	35

4	Unit Four:  Monitor and report on project costs.	38

4.1	Project costs	39

4.2	Variation costs	41

4.3	Final project cost	45

Self-cheek – 4.1	52

5	Unit five:   Maintain data files of standard costs	55

5.1	Approved Variation Cost	56

5.2	Changes into Standard Plans, Specifications, and Cost Files	57

Self-check 5.1.	60

6	Reference	62

# Acronym

EIA 	environmental impact assessment

EPA 	Ethiopian Environmental Protection Authority

HVAC 	heating, ventilation, and air conditioning

RFP 	Request for Proposal

CAD 	Computer-Aided Design

KPIs 	key performance indicators

HTML 	 Hypertext Markup Language

CSS 	 Cascading Style Sheets

CMS 	content management system

IBC 	International Building Code

ICC 	 International Code Council

IBC 	 national model codes such as the

NBCC  	 National Building Code of Canada

BSI  	 British Standards Institution

FAA   	Federal Aviation Administration

NASA 	National Aeronautics and Space Administration

FDA 	 Food and Drug Administration

SAE 	Automotive Engineers

SWOT 	 analysis Strengths, Weaknesses, Opportunities, Threats

KPI	key performance indicators

WBS 	work breakdown structure

# Acknowledgment

The Ministry of Labor and skill, wish to thank MoLS experts, regional labor and skill bureaus, TVT trainers, and industry experts who contribute their time and professional experience to the development of this Training module for finishing construction work.

We would like to express our appreciation to the Ministry of Labor and skill for their technical and financial support and workshop facilitation of this training module development.

# Introduction to the Module

The designing and sizing sanitary plumbing systems helps to know the identify and apply all contract conditions to the schedules ,produce material and labor schedules, overlays and orders, prepare site files, monitor and report on project costs, maintain data files of standard costsstructural Construction work filed.

This module is designed to meet the industry requirement under the plumbing installation work occupational standard, particularly for the unit of competency produce labor and material schedules for ordering

This module covers the units:

- Contract conditions

- Material and labor schedules

- Site filesPreparation

- project costs

- data files of standard costs

Learning Objective of the Module

- Identify and apply contract conditions

- Produce material and labor schedules

- Prepare site files

- Monitor and report on project costs.

- Maintain data files of standard costs.

Module Instruction

For effective use this modules trainees are expected to follow the following module instruction:

- Read the information written in each unit

- Accomplish the Self-checks at the end of each unit

- Perform Operation Sheets which were provided at the end of units

- Do the “LAP test” giver at the end of each unit and

- Read the identified reference book for Examples and exercise

# Unit one: Contract conditions

This unit is developed to provide you the necessary information regarding the following content coverage and topics: - Concept of produce labor and material schedules for ordering - Contractual requirements - Local government and regulatory bodies approval - Color selections - Contracts variations Work area Preparation This unit will also assist you to attain the learning outcomes stated in the cover page. Specifically, upon completion of this learning guide, you will be able to: - Understand of produce labor and material schedules for ordering - Contractual requirements - Approvallocal government and regulatory bodies approval - Select color selections - Schedule contracts variations

## Concept Produce labor and material schedules for ordering

Labor and material schedules for ordering, you'll need to consider several factors, including project timelines, labor requirements, material availability, and lead times.

Step of Schedules:

- Project Planning: Begin by reviewing the project plans and specifications to understand the scope, milestones, and timelines. Identify the key tasks and phases that require labor and materials.

- Labor Requirements: Determine the labor requirements for each task or phase. Consider the skills, expertise, and number of workers needed to complete the work efficiently. Consult with project managers, supervisors, or relevant personnel to gather accurate labor estimates.

- Material Requirements: Identify the materials needed for each task or phase. Create a comprehensive list of materials, including quantities, specifications, and any specific brands or models required. Consult with suppliers, manufacturers, or contractors to gather accurate material estimates.

- Lead Times and Availability: Contact your suppliers and vendors to determine the lead times for each material. Consider the availability of materials and any potential delays in delivery. Factor in any seasonal fluctuations or industry-specific constraints that may impact material availability.

- Create Schedules: With the labor and material requirements in hand, create schedules for ordering. Break down the schedules by task or phase, and include the following information:

- Task/Phase Name: Clearly identify each task or phase requiring labor and materials.

- Labor Requirement: Specify the number of workers, their skills, and the estimated hours or duration for each task.

- Material Requirement: List the materials needed, including quantities, specifications, and any special considerations.

- Lead Time: Indicate the lead time for each material, considering the time required for procurement and delivery.

- Order Dates: Determine the specific dates when orders should be placed to ensure timely delivery.

- Delivery Dates: Estimate the expected delivery dates for each material, accounting for lead times and potential delays.

- Review and Adjust: Review the labor and material schedules with project managers, supervisors, or relevant stakeholders. Make necessary adjustments based on their feedback, considering any budgetary constraints, resource limitations, or scheduling conflicts.

- Monitor and Update: Regularly monitor the progress of the project and adjust the schedules as needed. Keep in touch with suppliers and vendors to ensure timely delivery and address any changes in material availability or lead times.

Maintain clear communication channels with your team and suppliers throughout the process. Regularly update the schedules and coordinate with all stakeholders to ensure smooth project execution.

## Contractual requirements

In construction projects, contractual requirements are typically documented in several places, including the schedules. However, it's important to note that the specific arrangement and content of contractual requirements may vary depending on the project and the contract type. While schedules are an essential part of construction contracts, they usually focus on the timing and sequence of activities rather than explicitly listing all contractual obligations.

The main document that outlines the contractual requirements in construction projects is the contract itself. This agreement is typically prepared by the project owner or client and details the rights, responsibilities, and obligations of all parties involved, such as the owner, contractor, subcontractors, and suppliers. It covers various aspects, including scope of work, payment terms, project schedule, quality standards, insurance requirements, and dispute resolution procedures.

In addition to the contract, other contractual documents include:

Specifications: These define the technical requirements and standards for materials, workmanship, and installation methods.

Drawings: Detailed architectural, structural, and engineering drawings that provide visual representations of the project's design and construction requirements.

General Conditions: This document outlines the general rules, procedures, and administrative provisions governing the project. It typically covers topics such as permits, inspections, change orders, warranties, and termination clauses.

Special Conditions: Sometimes, specific project conditions require additional contractual provisions. Special Conditions address these unique requirements or circumstances that are not covered in the general contract.

Addenda: These are supplemental documents issued during the bidding or construction phase, modifying or adding to the original contract documents. Addenda may contain specific requirements or instructions, including changes to the project scope, specifications, or schedules.

Its schedules play an important role in construction contracts; they primarily focus on project timelines, milestones, and sequencing of activities. They typically outline the start and completion dates for various project phases, major deliverables, and specific deadlines for critical activities. Schedules may be included as separate documents or as an integral part of the contract or project specifications.

It's essential for all parties involved in a construction project to carefully review and understand the contractual requirements outlined in these documents to ensure compliance and successful project execution. Consulting with legal professionals or contract administrators can provide further guidance and clarity on the specific contractual obligations within the construction schedules.

Project scheduling

Project scheduling is the act of constructing a timetable for each project activity, and differs in complexity due to the presence of renewable resources with limited availability.

Is placing of a plan on a calendar and showing the allocation of the equipment and man power that will put the plan in to effect.

It involves the construction of an activity timetable, i.e. the determination of a start and finish time for each project activity, respecting the precedence relations and the limited availability of the renewable resources, while optimizing a predefined scheduling objective.

Scheduling will be discussed, as given along the following lines:

- Sequencing: scheduling with unlimited resources

- Scheduling: scheduling within limited resource constraints

A scheduling objective is the objective one aims to reach while constructing a resource-feasible project schedule. Although time is often considered as the dominant scheduling objective, other objectives are often crucial from a practical point-of-view.  A non-exhaustive list of possible objectives is given along the following lines:

- Time: minimize the total duration of the project

- Net present value: maximize the discounted cash flows of project activities

- Work continuity: avoid idle time of bottleneck resources in a project

- Leveling: avoid resource jumps but try to balance the use of resources

- Others: Many other scheduling objectives can occur and are often project specific.

Moreover, it is logical that in practical environments, a combination of objectives is strived for

- Function of scheduling

- Schedule convert action plan in to operating time table

- Basis for monitoring and controlling projects

- Scheduling is more important in project than in production

- Based on work break down  structure

Local government and regulatory bodies approval

To obtain local government and regulatory bodies' approval for labor and material schedules for ordering in construction in Ethiopia, generally follow these steps:

Identify the relevant local government and regulatory bodies: In Ethiopia, several government agencies and regulatory bodies oversee construction activities, including the Ministry of Urban Development and Construction, the Ethiopian Construction Works Corporation, and regional or city-level regulatory bodies such as the Addis Ababa City Administration Construction Permit and Control Authority. Identify the specific agencies that have jurisdiction over your construction project.

Familiarize yourself with construction regulations and requirements: Review the applicable laws, regulations, and guidelines related to construction in Ethiopia. This includes building codes, labor laws, environmental regulations, and any specific requirements set by the local government or regulatory bodies. Ensure that your labor and material schedules comply with these regulations.

Prepare the labor and material schedules: Develop detailed labor and material schedules based on the specific requirements of your construction project. This should include estimations of the required labor types, quantities, and skills, as well as the materials needed for each phase of the construction process.

Consult with professionals: Seek guidance from professionals such as architects, engineers, and quantity surveyors who have experience in construction projects in Ethiopia. Their expertise can help ensure that your labor and material schedules are accurate and comply with local standards.

Submit the documentation: Prepare a comprehensive submission package that includes your labor and material schedules, along with any supporting documents required by the local government or regulatory bodies. This may include architectural drawings, project plans, environmental impact assessments, and proof of compliance with safety regulations.

Submit the application: Contact the relevant local government or regulatory body to inquire about the application process and submission requirements. Submit your application package to the designated office or online portal, following the specified instructions.00

Follow up and address queries: After submitting your application, follow up with the local government or regulatory body to ensure that the review process is progressing. Be prepared to address any queries or requests for additional information that may arise during the review.

Obtain approval: Once your labor and material schedules have been reviewed and deemed compliant with the applicable regulations, you will receive approval from the local government or regulatory body. This approval may come in the form of a permit, license, or certificate, depending on the specific requirements of the jurisdiction.

It's important to note that the specific procedures and requirements may vary depending on the location and nature of your construction project in Ethiopia. Therefore, it is advisable to consult directly with the relevant local government or regulatory bodies to obtain accurate and up-to-date information for your specific case.

It’s important to note that specific requirements set by local government or regulatory bodies in Ethiopia may vary depending on the region, city, and nature of the construction project. It is crucial to consult with the relevant authorities or seek professional advice to ensure compliance with the specific requirements.

Construction projects in Ethiopia: Building permits and approvals: In Ethiopia, construction projects typically require obtaining building permits and approvals from the local government or regulatory bodies. The application process may involve submitting architectural drawings, project plans, structural calculations, and other relevant documents. The authorities will review the proposed design and ensure compliance with building codes, zoning regulations, and safety standards.

Environmental impact assessment: Depending on the scale and nature of the construction project, an environmental impact assessment (EIA) may be required. This assessment evaluates the potential environmental, social, and economic impacts of the project and proposes mitigation measures. The Ethiopian Environmental Protection Authority (EPA) is responsible for overseeing environmental assessments and issuing the necessary approvals.

Labor and employment regulations: Ethiopia has labor laws and regulations that govern employment practices in the construction sector. These regulations cover areas such as minimum wage, working hours, occupational health and safety, and employment contracts. Compliance with these regulations is essential when preparing labor schedules and engaging with construction workers.

Local content requirements: In some cases, local government or regulatory bodies in Ethiopia may have policies or requirements to promote local participation and content in construction projects. This may include provisions for using locally sourced materials, engaging local labor, or involving local businesses in the supply chain. Familiarize yourself with any such requirements and ensure they are reflected in your labor and material schedules.

Quality standards and inspections: Construction projects in Ethiopia are subject to quality standards and inspections. These standards may cover areas such as structural integrity, electrical and plumbing systems, fire safety, and overall workmanship. Inspections are typically conducted at various stages of the construction process to ensure compliance with the standards and regulations.

Payment of fees and taxes: Local government or regulatory bodies may require the payment of certain fees, taxes, or levies associated with construction projects. These could include building permit fees, development charges, or other local taxes. Ensure that you are aware of the applicable fees and payment processes to fulfill your financial obligations.

Approval processes local government and regulatory bodies typically have their own specific conditions and requirements. The inclusion of these conditions in schedules may vary depending on the jurisdiction and the specific regulations in place. A general overview of some common conditions that may be included by the authorities you mentioned.

Electricity Regulatory Authorities: These bodies oversee the regulation and management of electricity supply and distribution. Their conditions may include requirements related to safety standards, grid connection, environmental impact assessment, tariff structures, and compliance with industry codes and standards.

- Compliance with safety regulations for electrical installations and equipment.

- Connection requirements for new electricity generation projects to the grid.

- Tariff structures and pricing regulations for electricity supply.

- Renewable energy targets and incentives.

- Standards for energy efficiency and conservation.

Environmental Authorities: These agencies are responsible for protecting and managing the environment. Their conditions may focus on environmental impact assessment, pollution control measures, waste management, land use planning, and compliance with environmental laws and regulations.

- Environmental Impact Assessment (EIA) requirements for major development projects.

- Pollution control measures, such as emissions limits and wastewater treatment standards.

- Protected area regulations and restrictions on activities in environmentally sensitive areas.

- Environmental monitoring and reporting obligations.

Health Departments: Health departments are concerned with public health and safety. Their conditions may involve issues such as sanitation, hygiene standards, noise control, occupational health and safety, and compliance with health-related regulations.

- Sanitation and hygiene standards for food establishments, healthcare facilities, and public spaces.

- Noise control regulations to protect public health and minimize disturbances.

- Occupational health and safety requirements for workplaces.

- Regulations for the handling and disposal of hazardous substances.

- Guidelines for disease control and prevention.

Shire or Municipal Councils: These local governing bodies are responsible for managing local areas or municipalities. Their conditions may include land use planning, zoning regulations, building permits, compliance with local bylaws, and infrastructure requirements.

- Zoning regulations and land use planning guidelines.

- Building codes and requirements for construction permits.

- Regulations for signage, outdoor advertising, and display of goods.

- Guidelines for parking facilities and transportation planning.

- Regulations for the maintenance and use of public spaces and facilities.

Water Corporations: Water corporations are entities responsible for the supply and management of water resources. Their conditions may involve water quality standards, water extraction permits, wastewater management, water conservation measures, and compliance with water-related regulations.

- Water quality standards for drinking water and water bodies.

- Water extraction permits and regulations.

- Storm water management requirements.

- Water conservation measures and restrictions.

- Wastewater treatment and disposal regulations.

It's important to note that the specific conditions and requirements can vary significantly depending on the jurisdiction and the nature of the project or activity being regulated. It's always advisable to consult the relevant local government and regulatory bodies in your specific area for accurate and up-to-date information regarding their approval processes and associated conditions.

## Color selections

Creating labor and material schedules for ordering in construction, it's important to note that color selections typically refer to the identification and categorization of different items or tasks on the schedule. While there isn't a standardized color scheme for construction schedules, you can create your own color system based on your specific needs and preferences.

Color selections:

General Items: Use black or a neutral color (e.g., gray) to represent general items, such as administrative tasks, meetings, or non-specific labor activities.

Labor: Choose a distinct color for each type of labor involved in the project. For example:

- Blue for carpentry work.

- Green for electrical work.

- Red for plumbing work.

- Yellow for painting.

- Orange for HVAC (heating, ventilation, and air conditioning).

- Purple for masonry work.

Materials: Assign colors to different materials or material categories. Here are some examples:

- Brown for wood-related materials.

- Gray for concrete and masonry.

- Light blue for plumbing fixtures.

- Light green for electrical equipment.

- Pink for insulation materials.

- Dark blue for structural steel.

Critical Tasks: It can be helpful to highlight critical tasks that have tight deadlines or are crucial to the project's success. You can use a bold or vibrant color, such as bright red or orange, to draw attention to these tasks.

Notes or Changes: Reserve a specific color, like yellow or pink, to indicate notes, changes, or revisions to the schedule.

Color selections are just suggestions, and tailor them to suit your project's specific requirements. It's essential to communicate the color legend or key to all team members involved so that everyone understands the schedule and can easily identify different items or tasks.

## Contract variations

Including variations to contracts in the schedules is a common practice in the construction industry. When a client or builder requests changes to the original contract, these variations are documented and incorporated into the project schedules.

The schedules serve as a roadmap for the project, outlining the sequence of activities and their timelines. By including variations in the schedules, all parties involved have a clear understanding of the changes and their impact on the overall project timeline.

When a variation is proposed, it is typically evaluated for its feasibility, cost implications, and potential impact on the project schedule. If the variation is approved, it is documented in the contract as an amendment or addendum, and the schedules are updated accordingly. The updated schedules reflect the revised scope of work, including any new activities, modifications to existing activities, and adjusted timelines.

By including variations in the schedules, project stakeholders can effectively manage and track the changes throughout the construction process. This helps ensure that all parties are aware of the modifications and can plan and allocate resources accordingly. Additionally, having variations documented in the schedules can be beneficial for contract administration, project reporting, and dispute resolution purposes.

It's important to note that the specific procedures for handling variations may vary depending on the contract type, project requirements, and applicable laws and regulations. Consulting with legal and construction professionals is advisable to ensure compliance and to establish appropriate protocols for managing contract variations.

# Self-cheek 1.1

Part –I choose the best answer

- Which of the following is an essential contractual requirement for labor and material schedules?

  - Project timeline

  - Material specifications

  - Payment terms

  - All of the above

- Why is it important to obtain approval from local government and regulatory bodies?

  - To ensure compliance with safety regulations

  - To avoid legal penalties

  - To maintain good relations with local authorities

  - All of the above

- What factors should be considered when selecting colors for a construction project?

  - Aesthetics and design preferences

  - Local building codes and regulations

  - Environmental impact

  - All of the above

- What is the purpose of contract variations in labor and material schedules?

  - To accommodate changes in project scope

  - To address unforeseen challenges or delays

  - To modify material quantities or specifications

  - All of the above

- Which of the following is a key consideration when producing labor and material schedules?

  - Availability of skilled labor

  - Lead time for material procurement

  - Budget constraints

  - All of the above

PART-II

Give short answer

- What are contractual requirements in the context of labor and material scheduling for ordering, and why are they important?

- What factors should be considered when making color selections for labor and material schedules? How do these selections impact the overall project?

- Can you explain the concept of contract variations in the context of labor and material schedules for ordering? How do they affect project timelines and costs?

- What steps should be taken to ensure compliance with contractual requirements and local government regulations when creating labor and material schedules for ordering?

- How can color selections in labor and material schedules contribute to achieving project objectives, such as aesthetics, branding, or functionality?

- How can labor and material schedules be effectively organized and structured to facilitate efficient ordering processes and minimize delays?

# Unit two: Material and labor schedules, overlays and orders.

This unit is developed to provide you the necessary information regarding the following content coverage and topics: - Suppliers and contractors work schedules. - Overlays - Contract details and instructions - Applying contract rates - Work area Preparation This unit will also assist you to attain the learning outcomes stated in the cover page. Specifically, upon completion of this learning guide, you will be able to: - Nominate suppliers and contractors work schedules. - Produce Overlays - Contract details and instructions - Apply contract rates

## Material, labor schedules, overlays and orders

Construction project managers use various tools to manage material and labor flow, ensuring timely completion. Material schedules, overlays, and orders are essential documents that outline the project's material composition, work quantities, and the relationship between project scope and design, material cost, type, sizes, and quantities. They provide a detailed overview of project progress.

Material schedules are used to plan and track the delivery of materials to the project site. These schedules typically include the following information:

- Material quantities: The amount of each material needed for the project.

- Material delivery dates: The dates when materials will be delivered to the project site.

- Material suppliers: The companies or individuals supplying the materials.

- Material storage locations: The locations where materials will be stored on the project site.

- Material schedules help project managers to: Ensure that the right materials are delivered to the project site at the right time. Avoid delays in material delivery and ensure that materials are available when needed. Reduce the risk of material shortages or overstocking.

Steps to Preparing Material Schedule

- Identify and establish the work quantity

- Understand the building/construction process

- Identify work material proportion and components

- Understand material conversion factors and constants

- Adjustments to cover for wastages/shrinkage/bulkage

Table -2.1 Sample material schedule

Labor Schedules

Labor schedules are used to plan and track the work of laborers on the project site. These schedules typically include the following information:

Laborer names and positions: The names and positions of the laborers working on the project.

Laborer availability: The dates and times when laborers are available to work.

Laborer assignments: The tasks and activities that laborers will perform on the project site.

Labor schedules help project managers to: Ensure that the right laborers are assigned to the right tasks and activities. Avoid delays in labor productivity and ensure that laborers are working at their full capacity.

Reduce the risk of labor disputes or conflicts.

Tabel-1.2 Labor schedule

## Overlays

Overlays are used to visualize the progress of the project and identify potential delays or issues. These overlays typically include the following information:

- Gantt charts: A visual representation of the project schedule, showing the start and end dates for each task and activity.

- Resource leveling: A visual representation of the resources (e.g., materials, laborers) required for each task and activity.

- Critical path: The sequence of tasks and activities that determines the overall duration of the project.

- Overlays help project managers to: Identify potential delays or issues and take corrective action.

- Ensure that resources are allocated efficiently and effectively.

- Communicate the project plan and progress to stakeholders.

Orders

Orders are used to request and track the delivery of materials and equipment to the project site. These orders typically include the following information:

- Order number: A unique identifier for the order.

- Order date: The date when the order was placed.

- Material or equipment description: A description of the materials or equipment being ordered.

- Quantity: The amount of materials or equipment being ordered.

- Supplier: The company or individual supplying the materials or equipment.

- Delivery date: The date when the materials or equipment will be delivered to the project site.

- Orders help project managers to: Ensure that materials and equipment are delivered to the project site on time.

- Reduce the risk of material or equipment shortages.

- Track the progress of orders and ensure that they are fulfilled.

Benefits and Limitations

The use of material and labor schedules, overlays, and orders in construction projects

Benefits, including:

- Improved project planning and management.

- Increased efficiency and productivity.

- Reduced risk of delays or issues.

- Improved communication with stakeholders.

Limitations to consider: Material and labor schedules can be time-consuming to create and maintain.

- Overlays can be complex and difficult to interpret.

- Orders can be costly and may require significant lead time.

- Detailing nominated suppliers and contractors

Nominated suppliers and contractors are individuals or companies that have been selected or recommended for a particular project or contract. These nominations typically occur through a formal process, such as a bidding or procurement process, where potential suppliers and contractors submit their proposals or bids for consideration.

Suppliers refer to individuals or companies that provide goods or materials required for a project. They can range from manufacturers and wholesalers to distributors and retailers. Suppliers play a crucial role in ensuring the availability and quality of materials needed for the successful completion of a project.

Contractors, on the other hand, are individuals or companies that provide services related to the execution of a project. They can include construction contractors, engineering firms, IT service providers, consultants, and many others. Contractors are responsible for carrying out specific tasks or activities within the project scope.

The process of nominating suppliers and contractors:

- Identification: The first step is to identify potential suppliers and contractors who have the necessary expertise, experience, and resources to meet the project requirements.

- This can be done through market research, referrals, industry directories, or by inviting interested parties to submit their qualifications.

- Prequalification: Once potential suppliers and contractors have been identified, they may be required to go through a prequalification process. This involves assessing their financial stability, technical capabilities, past performance, compliance with regulations, and other relevant criteria. Prequalification helps ensure that only qualified and reliable entities are considered for nomination.

- Request for Proposal (RFP): In many cases, a formal RFP is issued to the prequalified suppliers and contractors. The RFP outlines the project requirements, specifications, terms and conditions, evaluation criteria, and submission deadlines. It provides an opportunity for suppliers and contractors to understand the project scope in detail and prepare their proposals accordingly.

- Proposal Evaluation: The submitted proposals are then evaluated based on predetermined criteria such as price, technical capabilities, past performance, delivery schedule, and compliance with specifications. Evaluation committees or procurement teams assess the proposals and shortlist the most suitable candidates for further consideration.

- Negotiation and Selection: The shortlisted suppliers and contractors may be invited for negotiation to finalize the terms of the contract, including pricing, delivery schedules, warranties, and other relevant aspects. After negotiations, the final selection is made based on factors such as cost-effectiveness, quality, reliability, and overall value for money.

The nomination of suppliers and contractors for a project should be fair and transparent, with government agencies and organizations implementing guidelines to ensure a competitive and unbiased selection process. This includes identifying potential candidates, prequalifying them, and negotiating terms.

## Producing relevant overlay drawings

Producing relevant overlay drawings involves the process of superimposing additional information or graphics onto an existing drawing or image. The technique is commonly used in various fields, such as architecture, engineering, construction, and design to convey additional details, modifications, or annotations.

To produce relevant overlay drawings, several steps need to be followed:

- Identify the purpose: Determine the specific purpose of the overlay drawing. This could include highlighting changes or modifications to an existing design, indicating dimensions or measurements, or adding annotations for clarity.

- Gather necessary information: Collect all the relevant data and information required for the overlay drawing. This may include architectural plans, engineering drawings, site surveys, or any other relevant documentation.

- Choose appropriate software: Select a suitable software tool for creating overlay drawings. There are various options available, ranging from general-purpose graphic design software to specialized CAD (Computer-Aided Design) applications. The choice of software depends on the complexity of the project and the specific requirements.

- Import base drawing: Import the base drawing or image onto which the overlay will be added. This can be done by scanning a physical drawing or importing a digital file into the chosen software.

- Create overlay elements: Use the software's tools and features to create the desired overlay elements. These can include lines, shapes, text boxes, symbols, or any other graphical representation needed to convey the intended information.

- Position and align: Position and align the overlay elements accurately over the base drawing. This step requires precision to ensure that the added information is correctly placed and aligned with the existing elements.

- Adjust transparency: Adjust the transparency or opacity of the overlay elements if necessary. This allows for better visibility of both the base drawing and the added information.

- Add annotations: Include any necessary annotations or labels to provide additional context or explanations for the overlayed elements.

## Contract details and instructions

Contract details and instructions refer to the specific terms, conditions, and guidelines outlined in a contract agreement. These details provide a comprehensive understanding of the rights, obligations, and responsibilities of the parties involved in the contract. They serve as a roadmap for how the contract should be executed and what actions are required from each party.

key components:

- Parties Involved: The contract should clearly identify the parties entering into the agreement. This includes their legal names, addresses, and any other relevant contact information.

- Purpose of the Contract: The purpose or objective of the contract should be clearly stated. This helps to establish the context and scope of the agreement.

- Terms and Conditions: The terms and conditions section outlines the specific obligations, rights, and responsibilities of each party. It covers various aspects such as payment terms, delivery schedules, performance expectations, warranties, dispute resolution mechanisms, termination clauses, and more.

- Performance Metrics: In some contracts, performance metrics or key performance indicators (KPIs) may be included to measure and evaluate the performance of one or both parties. These metrics help ensure that contractual obligations are being met.

- Payment Details: Contracts often include provisions related to payment terms such as pricing structures, invoicing procedures, due dates, late payment penalties, and any other financial considerations.

- Confidentiality and Non-Disclosure: If there is a need for confidentiality or non-disclosure of sensitive information shared during the course of the contract, these provisions should be clearly outlined to protect both parties' interests.

- Governing Law: Contracts typically specify which jurisdiction's laws will govern the interpretation and enforcement of the agreement. This helps establish a legal framework for resolving disputes.

- Amendments and Modifications: The contract may include provisions on how amendments or modifications to the agreement can be made. This ensures that any changes to the contract are properly documented and agreed upon by all parties.

## Applying contract rates

Applying contract rates refers to the process of implementing and enforcing the terms and conditions outlined in a contractual agreement between two or more parties. Contract rates are typically used in various industries such as transportation, logistics, construction, and professional services, where parties agree on specific pricing structures for goods or services. There are several key steps involved:

- Contract Negotiation: Before applying contract rates, parties must first negotiate and agree upon the terms and conditions of the contract. This includes determining the scope of work, pricing structure, payment terms, delivery schedules, and any other relevant provisions. The negotiation process may involve multiple rounds of discussions and revisions until both parties reach a mutually acceptable agreement.

- Contract Documentation: Once the terms are finalized, it is essential to document them in a legally binding contract. The contract should clearly outline all agreed-upon rates, including any discounts or surcharges that may apply under specific circumstances. It should also specify the duration of the contract, termination clauses, dispute resolution mechanisms, and any other relevant details to ensure clarity and avoid misunderstandings.

- Rate Application: After the contract is signed, both parties must adhere to the agreed-upon rates throughout the duration of the contract. This involves accurately calculating and applying the specified rates for each transaction or service provided. For example, in transportation and logistics contracts, rates may be based on factors such as distance traveled, weight or volume of goods transported, fuel prices, tolls, and other applicable charges.

- Rate Adjustments: In some cases, contract rates may need to be adjusted during the term of the agreement. This can occur due to various factors such as changes in market conditions, inflation, regulatory requirements, or unforeseen circumstances that impact costs. When rate adjustments are necessary, it is important for both parties to follow any procedures outlined in the contract for requesting and approving changes.

- Monitoring and Compliance: Applying contract rates also involves monitoring and ensuring compliance with the agreed-upon terms. This includes verifying that the correct rates are being applied, tracking any additional charges or discounts, and addressing any discrepancies or billing errors promptly. Regular communication and reporting between the parties can help maintain transparency and resolve any issues that may arise.

- Contract Renewal or Termination: As the contract approaches its expiration date, parties may choose to renew the agreement or terminate it based on their respective needs and satisfaction with the existing terms. If renewal is desired, negotiations for new rates or modifications to the existing rates may take place. If termination is chosen, parties must follow any notice periods or termination clauses specified in the contract.

# Self-check -2

Directions:  Answer all the questions listed below.

Part I: Fill in the blank space

- _________are used to request and track the delivery of materials and equipment to the project site.

- _________ refers to the process of implementing and enforcing the terms and conditions outlined in a contractual agreement between two or more parties.

Part-II:  Choose the correct answer from the given alternatives

      - the first step is to identify potential suppliers and contractors who have the necessary expertise, experience, and resources.

- Identification                                     B. Evaluation

- Collapse                                            D. All

- The amount of materials or equipment being ordered.

- Quality                                             B. One pipe system

- C. Quantity                                         D. All

Part- III: write the answer briefly for the following question.

- What are the Contract details and instructions?

- What is the Purpose of the Contract?

# Unit three: Site files Preparation

This unit is developed to provide you the necessary information regarding the following content coverage and topics: - Site documents. - call forward sheets Work area Preparation This unit will also assist you to attain the learning outcomes stated in the cover page. Specifically, upon completion of this learning guide, you will be able to: - Prepare Site documents. - Prepare call forward sheets

## Site documents

The Prepare Site Files phase is a critical stage in construction projects as it lays the groundwork for successful project execution. A key component of this phase is the production of labor and material schedules for ordering, which significantly contributes to the efficiency and coordination of the project. This article aims to highlight the importance of including comprehensive labor and material schedules in the site files and explore the essential elements that should be incorporated.

- Significance of Comprehensive Labor and Material Schedules in Site Files:

Efficient project management heavily relies on accurate and accessible information. By including in-depth labor and material schedules in the site files, project stakeholders can benefit in several ways. These schedules serve as

- A central reference point,

- facilitating streamlined procurement processes,

- minimizing delays, and

- enhancing resource allocation efficiency.

The comprehensive nature of these schedules ensures that all necessary information is readily available to the relevant parties involved in the project.

- Key Elements to Include in Labor and Material Schedules:

To maximize the effectiveness of labor and material schedules, it is crucial to incorporate the following elements:

- Building Codes:

Compliance with building codes is essential to ensure the safety and quality of the construction project. Including relevant building codes in the labor and material schedules helps all stakeholders understand and adhere to the necessary regulations, minimizing the risk of non-compliance issues.

- Color Selections:

In projects with aesthetic considerations, such as interior design or exterior finishes, color selections play a vital role. Including color selections in the schedules enables efficient coordination of material procurement, ensuring that the desired color scheme is achieved.

- Contract Requirements:

The labor and material schedules should align with the specific requirements outlined in the construction contract. This includes incorporating details regarding quality standards, delivery timelines, budgetary constraints, and any other contractual obligations that need to be fulfilled.

- Material and Labor Schedules:

The core of labor and material schedules lies in providing comprehensive information about the required resources. This includes specifying the quantities, types, and specifications of materials needed for each construction phase. Additionally, the schedules should outline the labor requirements, such as the number of workers, their skill sets, and the estimated time needed for completion. Clear and detailed schedules enhance resource planning and enable effective project coordination.

- Materials Specifications:

To ensure consistency and quality, integrating materials specifications in the schedules is crucial. These specifications provide precise guidelines for suppliers and contractors regarding the specific materials that need to be procured, including technical specifications and applicable industry standards.

- Plans, Sketches, and Drawings:

Accurate and detailed plans, sketches, and drawings are vital for effective communication and understanding among project stakeholders. Including these visual representations in the labor and material schedules ensures that everyone is aligned and can refer to the relevant documents when needed, minimizing potential errors or misinterpretations.

- Statements of Requirements:

Incorporating statements of requirements in the schedules ensures that the project aligns with the client's expectations and unique project specifications. These statements may include sustainability goals, energy efficiency requirements, design preferences, or any other specific project needs.

the inclusion of comprehensive labor and material schedules in the Prepare Site Files phase significantly contributes to the efficiency and success of construction projects. By incorporating essential elements such as building codes, color selections, contract requirements, material and labor schedules, materials specifications, plans, sketches, drawings, and statements of requirements, project stakeholders can streamline the procurement process, enhance resource allocation, and minimize project risks. This level of organization and attention to detail sets the stage for a well-coordinated and successful construction project.

## Call Forward Sheets

The Prepare Site Files phase is a critical stage in construction projects, and efficient project management relies on meticulous planning and organization. A key component of this process is the preparation of call forward sheets, which play a significant role in detailing all orders. This article explores the importance of comprehensive call forward sheets during the Prepare Site Files phase, specifically focusing on their role in producing labor and material schedules for ordering. By understanding the purpose and benefits of call forward sheets, construction professionals can streamline their processes, minimize delays, and ensure efficient resource allocation.

- Understanding Call Forward Sheets:

Call forward sheets are comprehensive documents that provide a detailed overview of all orders required for a construction project. These sheets serve as a reference point for project managers, site supervisors, and procurement teams, ensuring that all necessary materials and labor are scheduled and ordered in a timely manner. They include information such as item descriptions, quantities, specifications, delivery dates, and supplier details.

- Importance of Call Forward Sheets in the Prepare Site Files Phase:

During the Prepare Site Files phase, call forward sheets play a crucial role in ensuring that all necessary orders are accounted for and properly scheduled. This phase involves compiling all relevant project documentation, including permits, contracts, and technical specifications. Call forward sheets act as a bridge between project planning and execution, ensuring that the necessary resources are available when needed.

- Producing Labor and Material Schedules for Ordering:

One of the primary functions of call forward sheets is to facilitate the production of labor and material schedules for ordering. These schedules outline the specific quantities, types, and delivery dates of materials required for each phase of the project. By accurately estimating labor requirements and coordinating material deliveries, construction professionals can minimize delays, avoid cost overruns, and maintain project timelines.

- Benefits of Comprehensive Call Forward Sheets:

- Streamlined Ordering Process: Comprehensive call forward sheets provide a centralized reference point for all project-related orders, streamlining the ordering process. This reduces the chances of errors, duplicate orders, and miscommunication, ultimately improving overall project efficiency.

- Improved Communication: Call forward sheets promote effective communication between project stakeholders, including suppliers, contractors, and site personnel. By clearly outlining the requirements and deadlines, these sheets ensure that everyone involved is on the same page, minimizing confusion and delays.

- Cost Control: Accurate labor and material schedules derived from call forward sheets enable construction professionals to monitor and control project costs more effectively. By having a clear overview of the ordered quantities and delivery dates, unnecessary expenses can be avoided, and budget adherence can be ensured.

Comprehensive call forward sheets are invaluable tools during the Prepare Site Files phase of construction projects. By producing labor and material schedules for ordering, these sheets streamline the procurement process, enhance efficiency, improve communication, and enable effective cost control. By recognizing the importance of call forward sheets and incorporating them into project planning, construction professionals can optimize their processes and achieve successful project outcomes.

# Self –check 3.1

Choice the given alternatives

1. What is the purpose of including comprehensive labor and material schedules in site files?

A. To facilitate streamlined procurement processes.

B. To ensure compliance with building codes.

C. To provide accurate plans, sketches, and drawings.

D. To align with client's statements of requirements.

2. Which of the following is an essential element to include in labor and material schedules?

A. Building permits and contracts.

B. Sustainability goals and energy efficiency requirements.

C. Supplier details and delivery dates.

D. Quality standards and budgetary constraints.

3. What is the role of call forward sheets in the Prepare Site Files phase?

A. To ensure compliance with building codes.

B. To provide accurate plans, sketches, and drawings.

C. To schedule and order necessary materials and labor.

D. To communicate project expectations to stakeholders.

4. What is the benefit of comprehensive call forward sheets?

A. Improved communication and coordination.

B. Streamlined procurement and cost control.

C. Efficient resource allocation and risk minimization.

D. Compliance with building codes and specifications.

5. Which document serves as a bridge between project planning and execution during the Prepare Site Files phase?

A. Building codes and color selections.

B. Statements of requirements and material specifications.

C. Labor and material schedules and call forward sheets.

D. Plans, sketches, and drawings.

True or False Questions:

1. Including comprehensive labor and material schedules in site files enhances resource allocation efficiency.

2. Call forward sheets provide a detailed overview of all orders required for a construction project.

3. Labor and material schedules derived from call forward sheets minimize delays and cost overruns.

4. Comprehensive call forward sheets improve overall project efficiency by reducing errors and miscommunication.

5. Including building codes in labor and material schedules ensures compliance with quality standards.

# Unit Four: Monitor and report on project costs.

This unit is developed to provide you the necessary information regarding the following content coverage and topics: - Project costs - Variation Costs - Final project cost Work area Preparation This unit will also assist you to attain the learning outcomes stated in the cover page. Specifically, upon completion of this learning guide, you will be able to: - Analyze project costs - Approve variation Costs - Analyze final project cost

## Project costs

Construction estimates are an essential part of the construction process and are used to determine the anticipated costs of a construction project. There are several types of construction estimates, including:

- Approximate Estimates: Also known as preliminary or ballpark estimates, approximate estimates provide a rough idea of the project's cost during the early stages of planning. They are based on limited information and are often used to assess the feasibility of a project or for budgetary purposes.

- Detailed Estimates: Detailed estimates are comprehensive and provide a breakdown of all the costs involved in a construction project. They take into account quantities, labor, materials, equipment, overheads, and profit margins. Detailed estimates are typically prepared during the later stages of project planning and are used for accurate budgeting, bidding, and project management.

- Quantity Takeoff Estimates: Quantity takeoff estimates involve measuring and quantifying all the materials required for a construction project. This includes determining the quantities of concrete, steel, bricks, lumber, and other materials needed. Quantity takeoff estimates are often used in conjunction with unit prices to calculate the overall project cost.

- Unit Price Estimates: Unit price estimates involve assigning costs to individual construction elements based on industry-standard unit rates. These rates are typically derived from historical data or current market prices. Unit price estimates are useful for quickly estimating costs based on quantities, such as the cost per square foot or cost per linear foot.

- Parametric Estimates: Parametric estimates use mathematical models and statistical analysis to estimate construction costs based on key project parameters. These parameters can include factors such as the building area, number of floors, type of construction, and known cost data from similar projects. Parametric estimates are often used for early-stage cost forecasting and benchmarking.

- Design-Build Estimates: Design-build estimates are prepared by design-build firms that handle both the design and construction phases of a project. These estimates are typically based on conceptual designs and preliminary information provided by the client. Design-build estimates allow for collaboration between the design and construction teams, resulting in cost-effective and efficient project delivery.

- Bid Estimates: Bid estimates are prepared by contractors and subcontractors when submitting bids for a construction project. These estimates are based on the project's specifications, drawings, and other bid documents provided by the client. Bid estimates require careful analysis and consideration of all project requirements to ensure accurate pricing and competitive bidding

Analyzing project costs against estimates during construction is an essential practice to ensure that the project stays within budget and to identify any deviations or potential cost overruns. Let's break down the different cost elements mentioned:

- Building or Construction Materials: This includes the cost of raw materials, such as cement, steel, lumber, wiring, pipes, and other materials required for the construction process. These costs can be estimated based on market prices and quantities needed for the project.

- Communications Costs: This refers to the expenses associated with communication systems and services required during construction, such as telephone lines, internet connectivity, mobile phones, and any related subscriptions or usage charges.

- Fuels, Lubricants, and Other Consumables: Construction sites often require fuels, lubricants, and other consumables like adhesives, solvents, paints, and cleaning agents. The costs for these items should be estimated based on the expected consumption and prevailing market prices.

- Organizational and Subcontract Labor Costs: This includes the wages, salaries, benefits, and other labor-related expenses for both the organization's employees and subcontracted workers involved in the construction project. These costs are estimated based on labor rates, anticipated work hours, and the project's timeline.

- Overheads: Overhead costs encompass the indirect expenses incurred in running the construction project but are not directly tied to specific activities. Examples include office rent, utilities, equipment maintenance, and administrative staff salaries. Overheads are typically allocated to the project based on predetermined rates or as a percentage of direct labor or material costs.

- Professional Indemnity and Other Insurance Costs: Construction projects often require insurance coverage to protect against risks and liabilities. Professional indemnity insurance, general liability insurance, workers' compensation insurance, and other relevant policies should be considered. The costs of insurance premiums are estimated based on factors such as project value, scope, and associated risks.

- Project Administration Costs: This category encompasses various administrative expenses, including project management fees, legal fees, accounting services, permits, licenses, and other regulatory compliance costs. These costs are estimated based on industry standards, contractual agreements, and the complexity of the project.

During the construction phase, actual costs are tracked and compared to the estimated costs for each element. This analysis helps project managers identify any discrepancies or potential cost overruns, allowing them to take corrective actions if necessary, such as adjusting the project plan, negotiating with suppliers or subcontractors, or implementing cost-saving measures.

## Variation costs

Analyzing and approving variations in construction can incur certain costs. These costs can be categorized into direct and indirect costs.

- Direct Costs:

- Labor Costs: Additional labor may be required to assess the variation, including project managers, engineers, architects, and other professionals involved in the approval process.

- Material Costs: Variations may involve changes in materials, which can lead to additional procurement and transportation expenses.

- Equipment Costs: If variations necessitate the use of specialized equipment or tools, there may be additional costs associated with their rental, purchase, or maintenance.

- Indirect Costs:

Time and Schedule Impact: Analyzing and approving variations can lead to delays, impacting the project schedule. Delays may result in increased indirect costs such as extended overhead expenses, extended rentals, and extended general conditions.

- Design and Documentation: Modifications to the design and documentation may be necessary to accommodate the approved variations. These changes can incur additional costs, including architectural or engineering fees.

- Contract Administration: The process of analyzing and approving variations requires administrative efforts, such as reviewing and processing change orders, which can increase administrative costs.

- Disruption and Productivity Loss: Construction activities may be disrupted due to variations, resulting in decreased productivity and increased labor costs.

It's important to note that the cost impact of analyzing and approving variations can vary depending on the nature, complexity, and scale of the proposed changes. Additionally, effective project management and communication can help mitigate some of these costs by identifying and addressing variations in a timely manner.

To assess the specific cost implications of analyzing and approving variations in construction, it is recommended to consult with construction professionals, such as quantity surveyors, estimators, and project managers, who can provide a more accurate estimation based on the project's unique circumstances

    - Variations may be initiated by the Engineer at any time prior to issuing the Taking-Over Certificate for the whole of the Works, either by an instruction under  [Engineer’s Instructions] or by a request for the Contractor to submit a proposal.

- Variation may include:

- changes to the quantities of any item of work included in the Contract (however, such changes do not necessarily constitute a Variation);

- changes to the quality and other characteristics of any item of work;

- changes to the levels, positions and/or dimensions of any part of the Works;

- omission of any part of the Works;

- any additional work, Plant, Materials or services necessary for the Permanent Works, including any associated Tests on Completion, boreholes and other testing and exploratory work; and/or

- Changes to the sequence or timing of the execution of the Works (including advancing or postponing the Time for Completion).

B, The Contractor shall submit a proposal, unless the Contractor promptly gives a Notice to the Engineer stating (with detailed supporting particulars) that:

- the varied work was Unforeseeable having regard to the scope and nature of the Works described in the Specification;

- the Contractor cannot readily obtain the Goods required for the Variation; or

- Any other reason that adversely affects the Contractor’s obligations under the Contract.

    - The Contractor shall within fourteen (14) days of receipt of the Notice, and before the Contractor carries out the Variation, submit to the Engineer a detailed proposal, including:

- a detailed description of the varied works to be performed including pertinent details such as resources, methodology and Program me;

- a breakdown of the increase or decrease in the Contract Price and any effect on the Program me and Time for Completion; and

- Any further particulars that the Engineer may reasonably require.

    - The Engineer shall respond with approval, disapproval or comments to the proposal. The Contractor shall then be bound by any such Variation Notice and shall execute the Variation with due expedition and without delay.

    - The Contractor shall not make any alteration and/or modification of the Permanent Works, unless and until the Engineer instructs a Variation in writing.

    - Notwithstanding any other provisions of the Contract, no change, modification, addition or deletion to, in or from the Specification or the Contractor's Documents, the Works or the Contractor's conditions and methods of working, which are necessary due to any act, omission or default of the Contractor in the performance of its obligations under the Contract, shall be deemed to be a Variation and any such matter shall not result in any adjustment of the Contract Price, EOT or other relief. Any additional Cost to the Employer caused by such change, modification, addition or deletion which are attributable to such default or breach shall be borne by the Contractor and shall be recovered by the Employer subject to Sub- [Employer’s Claims].

j. If the Contractor incurs Costs in complying with an acceleration direction under Sub- [Rate of Progress] except where the direction was issued as a consequence of the failure of the Contractor to fulfill its obligations under the Contract, the Contractor shall be entitled, subject to [Contractor’s Claims], to the payment of any such Costs, which shall be added to the Contract Price as a Variation.

H. No Variation invalidates the Contract. The Contractor agrees that a Variation may involve the omission of any part or parts of the Works and the Contractor agrees that the Employer may engage others to perform that part or parts of the Works which have been omitted. The Contractor further acknowledges that any omission or omissions will not constitute a basis for the Contractor to allege that the Employer has repudiated the Contract no matter the extent or timing of the omission or omissions.

In project management, variation costs refer to the additional or unexpected expenses that arise during the course of a project due to changes in scope, requirements, or other factors. These costs are often managed and reported through a specific process to ensure transparency and control.  Explanation of how variation costs are typically managed and reported:

Identification: The first step in managing variation costs is to identify and recognize any changes that may impact the project's cost. This involves closely monitoring the project's progress, tracking scope changes, and actively engaging with stakeholders to identify potential variations.

Documentation: Once a variation is identified, it is important to document it thoroughly. This includes capturing the details of the change, the reasons behind it, and the anticipated impact on project costs. Documentation helps provide a clear record of the variation and supports accurate reporting.

Impact Assessment: After documenting a variation, a comprehensive impact assessment is conducted to evaluate its effect on the project's cost. This assessment involves analyzing the additional resources, materials, labor, or any other cost implications resulting from the variation. The impact assessment provides an estimate of the variation costs.

Change Control: Managing variation costs typically involves a change control process. This process ensures that variations are properly reviewed, evaluated, approved, and implemented. Change control helps maintain control over the project's budget by preventing unauthorized or uncontrolled changes.

Approval and Authorization: Once the impact assessment is complete, the identified variation costs are presented to the appropriate stakeholders, such as project sponsors or management, for approval. The stakeholders review the impact assessment and make decisions regarding whether to proceed with the variation and its associated costs.

Reporting: Variation costs are reported through various project management reporting mechanisms. These reports may include cost variance reports, change order logs, or project status updates. The reports provide visibility into the variation costs, their impact on the overall project budget, and any adjustments made to accommodate the changes.

Tracking and Monitoring: Throughout the project, variation costs are continuously tracked and monitored to ensure that they are properly managed and controlled. Regular monitoring enables project managers to identify trends, analyze the impact of variations, and take corrective actions if necessary.

By following these steps, project managers can effectively manage and report variation costs, enabling better control over the project budget and improved decision-making regarding changes.

## Final project cost

The final project cost in construction can vary significantly depending on several factors such as the size and complexity of the project, location, materials used, labor costs, and any additional features or requirements.

Breakdown of cost components in construction projects:

- Direct Costs: These include all expenses directly related to the physical construction of the project, such as materials, equipment, and labor. Direct costs can vary significantly based on the project's scope and quality expectations.

- Indirect Costs: These are expenses that are not directly tied to the physical construction, but are necessary for the project to proceed. Examples include permits, inspections, architectural and engineering fees, insurance, and temporary utilities.

- Contingency Costs: It is common to allocate a certain percentage of the total project cost as a contingency fund to account for unforeseen circumstances or changes during construction. Contingency costs are typically around 5% to 10% of the direct and indirect costs.

- Professional Fees: These are fees paid to professionals such as architects, engineers, and consultants involved in the design and management of the project. Professional fees are typically calculated as a percentage of the total construction cost, ranging from 5% to 15%.

- Land and Site Costs: If the project involves acquiring land or preparing the site for construction, costs associated with land purchase, site clearing, grading, and utility connections should be considered.

- Financing Costs: If the project is financed through loans or other financing options, interest expenses and fees associated with borrowing should be factored in.

It's essential to obtain detailed estimates and quotes from construction professionals or contractors for a specific project to accurately determine the final cost. They can analyze the project's requirements and comprehensive breakdown of costs based on current market rates and local considerations.

To perform a cost analysis for a construction project, need detailed information about the project scope, specifications, and any available cost data.

- Project Scope: Clearly define the project scope, including the type of construction, size, complexity, and any unique features or requirements.

- Cost Categories: Identify the major cost categories associated with the project. This may include:

- Direct Costs: Material costs, labor costs, equipment costs, subcontractor costs, permits, and fees.

- Indirect Costs: Overhead expenses, such as project management, insurance, utilities, and temporary facilities.

- Contingency: Allowance for unforeseen events or changes that may affect the project's cost.

- Quantity Takeoff: Develop a comprehensive list of materials and quantities required for construction based on the project's design and specifications. This may involve performing a quantity takeoff from architectural and engineering drawings.

- Material Costs: Research current market prices for construction materials and estimate the costs based on the quantities required. Consider factors such as material availability, quality, and any price fluctuations that may impact the project timeline.

- Labor Costs: Determine the labor requirements for the project, including the number of workers, their skill levels, and their respective wages. Consider the project duration and any labor productivity factors that may affect the overall cost.

- Equipment Costs: Identify the equipment needed for the construction project and estimate the associated costs. This includes rental or purchase costs, fuel, maintenance, and operator wages if applicable.

- Subcontractor Costs: If subcontractors are involved, obtain quotes or estimates from multiple subcontractors for their respective scopes of work. Consider their reputation, experience, and track record when evaluating the costs.

- Overhead Costs: Calculate the indirect costs associated with the project, such as project management, insurance, permits, utilities, and temporary facilities. These costs are typically expressed as a percentage of the direct costs.

- Contingency: Allocate a contingency amount to account for unforeseen events or changes during the construction process. The contingency percentage can vary depending on the project's complexity and level of risk.

- Cost Estimation: Sum up all the direct costs, indirect costs, and contingency to arrive at the total estimated cost for the construction project.

- Cost Control: Throughout the project, track the actual expenses against the estimated costs. Implement effective cost control measures to monitor and manage the budget, making adjustments as necessary.

The accuracy of the cost analysis heavily relies on the quality of the data and the expertise of the individuals involved. It's essential to consult with experienced professionals, such as quantity surveyors or construction estimators, to ensure a more accurate and reliable cost analysis.

The above components will include the total project cost at the time of the cost estimate. To arrive at the total recommended budget, additional line items will be included in the component summary for:

- Contingency for design development.

- Allowance for rising costs to the mid-point of construction.

The contingency for design development is determined by consultation with the owner and typically can range from 5% up to 15% of the total construction cost.  Frequently, the contingency is decreased during the design process as the likelihood of changes to the plans decreases.

Allowance for rising costs, or escalation, is determined by national or regional conditions. A predetermined monthly percentage is used to increase the construction cost from the date of the cost estimate by the number of months to start plus one-half of the number of months of construction.  For example, if it is June 2002 and construction is anticipated to begin in December 2002 and last for a period of 12 months, the construction cost will be increased or escalated by the percentage utilized times 6 (June 2002 to December 2002) plus 6 (January 2003 to June 2003), or times 12.  At an annual inflation rate of 3%, or a monthly rate of  .25%, the escalation would be .25% x 12 months, or a total of 3% of the total construction cost.

Summary Page

The summary page provides a one-page overview of the total cost summary with a single line item and cost per square foot for each building component. Table 1 below illustrates the Components Summary for an 87,500 square foot facility with a cost estimate of $18,909,000.

Component Detail

The component detail sheets provide a more detailed overview of the contents of each line item. In the illustration below for the component, Function Equipment & Specialties, library shelving is included in the cost estimate with the specific quantities and cost per unit shown.  End panels are included as an additional cost. The reference desk is estimated at $500 per linear foot (LF) for a total cost of $12,500.  The general contract supplied marker boards are estimated at $15 per square foot (SF). Audiovisual equipment for the bibliographic instruction classroom is included as an allowance (LS) at $50,000.  Signage is included as an allowance (LS) at $35,000.  Window shades are calculated by the square foot (SF) at $15.00 per square foot for electronically operated window shades.  The total of the component detail for these items appears on line 8 of the Component Summary  (See above.)

Monitoring and reporting on project costs and producing labor and material schedules for ordering are important aspects of project management.

- Step tasks:

- Establish a cost tracking system: Set up a system to track all project costs, including labor and material expenses. You can use project management software or create a spreadsheet to record and monitor costs throughout the project.

- Define cost categories: Identify the different cost categories relevant to your project, such as labor, materials, equipment, subcontractors, and overhead expenses. This will help you organize and track costs more effectively.

- Estimate costs: Before the project starts, estimate the costs associated with labor and materials. Consult with relevant stakeholders, such as contractors, suppliers, and team members, to gather accurate cost estimates.

- Create a budget: Based on the cost estimates, create a project budget that outlines the expected expenses for labor and materials. The budget will serve as a baseline against which you can track and compare actual costs.

- Track labor costs: Monitor labor costs by keeping a record of hours worked by each team member and their corresponding rates. This can be done through timesheets or a time tracking system. Regularly update the labor cost information in your tracking system.

- Track material costs: Keep track of all material purchases and expenditures related to the project. Maintain detailed records of quantities, unit costs, and suppliers. Update the material cost information in your tracking system accordingly.

- Compare actual costs to the budget: Regularly compare the actual costs incurred with the budgeted amounts. This will help you identify any cost overruns or savings. Analyze the reasons behind deviations from the budget and take appropriate actions to manage costs effectively.

- Generate cost reports: Prepare regular cost reports to provide an overview of project expenses. These reports should include a breakdown of costs by category (labor, materials, etc.), a comparison of actual costs against the budget, and any cost projections or forecasts for the remainder of the project.

- Review and analyze cost data: Analyze the cost data to identify trends, patterns, and areas where costs can be optimized. This analysis will enable you to make informed decisions and take corrective actions, if necessary, to keep the project on track financially.

- Produce labor and material schedules: Utilize the project schedule and resource allocation information to create labor and material schedules. These schedules should outline the quantity and timing of labor and material requirements throughout the project's duration. Coordinate with suppliers and team members to ensure timely ordering and delivery of materials.

- Regularly update schedules: As the project progresses, update the labor and material schedules based on actual progress and any changes in requirements. Communicate schedule updates to the relevant stakeholders to ensure everyone is aware of the latest information.

- Communicate and collaborate: Maintain open communication with the project team, suppliers, and other stakeholders regarding costs, schedules, and any changes or updates. Collaboration and effective communication will help ensure that labor and material schedules are aligned with project requirements and budget constraints.

By following these steps, effectively monitor and report on project costs while producing labor and material schedules for ordering. Remember to continuously review and adjust your approach based on the project's progress and any changing circumstances.

# Self-cheek – 4.1

- Which of the following are components of project cost monitoring and reporting?

- Project costs

- Variation costs

- Final project cost

- All of the above

- What aspects of the project should be included in cost monitoring and reporting?

- Project costs

- Variation costs

- Final project cost

- Both a) and b)

- All of the above

- Which of the following should be considered when reporting on project costs?

- Project costs only

- Variation costs only

- Final project cost only

- Both a) and b)

- All of the above

- What is the purpose of monitoring and reporting on project costs?

- To track project expenditures

- To identify cost overruns or savings

- To assess project performance

- All of the above

- Which of the following is an example of variation costs in a project?

- Labor cost increases due to overtime

- Equipment rental expenses

- Materials cost fluctuations

- All of the above

- How does monitoring project costs contribute to the final project cost?

- It helps identify cost variances

- It enables cost control measures

- It allows for adjustments to the budget

- All of the above

Give short answer

- What is meant by "monitoring project costs" and why is it important in project management?

- How can project costs be effectively tracked and monitored throughout the project's lifecycle?

- What are the key components of project costs and how are they typically categorized?

- What is the significance of variation costs in project management and how are they managed and reported?

- How can project managers ensure accurate and timely reporting of project costs?

- What challenges or risks are associated with monitoring and reporting on project costs, and how can they be mitigated?

- What role does cost estimation and forecasting play in monitoring and reporting on project costs?

- How can project managers determine the final project cost and what factors might influence its accuracy?

- What techniques or tools are commonly used to monitor and report on project costs?

- How can project cost reports be presented to stakeholders in a clear and meaningful way?

# Unit five: Maintain data files of standard costs

This unit is developed to provide you the necessary information regarding the following content coverage and topics: - Approving variation cost. - Standard plans, specifications and cost files Work area Preparation This unit will also assist you to attain the learning outcomes stated in the cover page. Specifically, upon completion of this learning guide, you will be able to: - Approve variation cost. - Apply standard plans, specifications and cost files

## Approved Variation Cost

Accurate management of cost variations is essential for successful construction projects. One crucial aspect of this process is incorporating approved variation cost increases into site files. This article provides a comprehensive guide on how construction professionals can effectively manage and update data files to reflect these variations, ensuring accurate scheduling and ordering. By following the steps outlined, project teams can streamline their processes and maintain financial control.

- Understanding Approved Variation Cost Increases:

Approved variation cost increases refer to changes in the project scope or specifications that have been authorized and agreed upon by relevant stakeholders. These variations can impact labor and material costs, necessitating updates to the standard cost data files. Proper tracking of these changes is crucial to prevent discrepancies in the ordering process.

- Maintaining Data Files of Standard Costs:

To maintain accurate data files of standard costs, construction professionals can follow these steps:

- Documenting Approved Variation Cost Increases: Whenever a variation is approved, record all relevant details, including the nature of the variation, the associated cost increase, and the approval date. Use a standardized format or template to ensure consistency across all variations.

- Updating Labor and Material Schedules: Review existing labor and material schedules in the data files and identify areas that require adjustment due to the approved variations. Update the schedules accordingly, considering the revised costs, quantities, or specifications.

- Communicating Changes to the Team: It is crucial to communicate any updates or changes to the project team, including the site manager, procurement team, and subcontractors. This ensures that everyone is aware of the approved variation cost increases and can adjust their ordering and scheduling accordingly.

- Incorporating Changes into Site Files: Once the labor and material schedules have been updated, incorporate these changes into the site files. This can be done by updating the electronic or physical files used to track standard costs. Ensure that the revised schedules are easily accessible to all team members involved in the ordering process.

- Regularly reviewing and Revising Data Files: Maintaining accurate data files of standard costs is an ongoing process. Regularly review and revise the files to reflect any new variations or changes that may arise throughout the project. This ensures that the ordering process remains accurate and efficient.

Incorporating approved variation cost increases into site files is vital for maintaining accurate data files of standard costs. By following the steps outlined, construction professionals can effectively manage and update their data files, ensuring accurate scheduling and ordering of labor and materials. Accurate records and effective communication within the project team are essential for successful cost management and project execution.

## Changes into Standard Plans, Specifications, and Cost Files

Accurate and up-to-date data files are vital for effective construction project management. This article highlights the significance of incorporating changes into standard plans, specifications, and cost files in order to streamline construction processes. It also provides recommendations for improving the implementation of these changes.

- Understanding the Importance of Standard Plans, Specifications, and Cost Files:

Standard plans, specifications, and cost files serve as crucial references in construction projects. Standard plans outline the design and layout of project components, while specifications provide detailed requirements for materials and workmanship. Cost files contain information about estimated project costs, including labor, materials, and equipment.

- The Need for Incorporating Changes:

Changes to standard plans, specifications, and cost files often arise during construction projects. These changes may result from design modifications, unforeseen circumstances, or client requests. It is essential to incorporate these changes into site files to ensure accurate and up-to-date information.

- Benefits of Updating Site Files:

Updating site files with changes to standard plans, specifications, and cost files offers several advantages:

- Accurate Decision-Making: By having the most current information readily available, project stakeholders can make informed decisions promptly. Changes in specifications or plans can impact costs, labor requirements, and scheduling. Access to updated site files enables project managers to assess these impacts accurately.

- Improved Resource Allocation: Labor and material scheduling is critical in construction project management. Incorporating changes into site files ensures that schedules are based on the latest information, minimizing errors and discrepancies. This leads to improved resource allocation and cost control.

- Enhanced Collaboration: Up-to-date site files facilitate effective communication and collaboration among project teams, contractors, and suppliers. By sharing accurate information, all stakeholders can align their plans and work together more efficiently.

- Implementing Changes to Site Files:

- Documentation: Thoroughly document all changes made to standard plans, specifications, and cost files. Include the nature of the change, reasons behind it, and any associated impacts. This documentation serves as a reference for future decision-making and ensures transparency.

- Communication: Effectively communicate changes to relevant stakeholders, including project managers, contractors, and suppliers. Clear communication ensures that everyone is aware of the modifications and can adjust their plans accordingly.

- Timely Updates: Promptly update site files to reflect the changes. Revise the relevant sections and ensure that the new information is accurately recorded. This helps maintain the accuracy and reliability of the site files.

- Regular Review: Continuously review and update site files as new changes arise. Regular reviews ensure that the site files remain current throughout the construction project.

Incorporating changes into standard plans, specifications, and cost files is crucial for efficient construction project management. By updating site files with accurate and up-to-date information, project stakeholders can make informed decisions, allocate resources effectively, and enhance collaboration. Implementing a systematic approach to incorporating changes will streamline construction processes and contribute to the overall success of the project.

# Self-check 5.1.

Choice alternative questions

1. Which of the following best defines approved variation cost increases?

A. Changes in project scope or specifications that have been authorized and agreed upon.

B. Changes in project schedule due to unforeseen circumstances.

C. Changes in labor and material costs without proper authorization.

D. Changes in project design that require additional resources.

2. What is the purpose of maintaining data files of standard costs?

A. To track labor and material schedules.

B. To communicate changes to the project team.

C. To prevent discrepancies in the ordering process.

D. To incorporate changes into site files.

3 How can construction professionals communicate changes to the project team effectively?

A. By updating labor and material schedules.

B. By incorporating changes into site files.

C. By using a standardized format or template.

D. By regularly reviewing and revising data files.

4. Why is it important to regularly review and revise data files of standard costs?

A. To ensure accurate scheduling and ordering.

B. To prevent discrepancies in the ordering process.

C. To communicate changes to the project team.

D. To track labor and material schedules.

5.What is the significance of incorporating changes into standard plans, specifications, and cost files?

A. To improve resource allocation.

B. To maintain accurate and up-to-date information.

C. To enhance collaboration among project teams.

D. To facilitate effective communication.

True or False Questions:

1. Accurate management of cost variations is essential for successful construction projects.

2. Updating site files with changes to standard plans, specifications, and cost files can improve resource allocation.

3. Thorough documentation of changes is not necessary when incorporating changes into site files.

4. Promptly updating site files is not important for maintaining their accuracy and reliability.

5. Incorporating changes into standard plans, specifications, and cost files contributes to the overall success of the project.

# Reference

Anderson, D.S. (2013). The impact of labor scheduling on construction project performance. Construction Engineering and Management Journal, 19(1), 34-57.

Brown, E.R., & Thompson, L.W. (2012). Optimizing labor scheduling for greater efficiency. Journal of Industrial Engineering, 15(4), 89-108.

Davis, K.L., & Wilson, P.L. (2016). Labor and material scheduling: A comprehensive approach. Construction Planning and Management Journal, 22(4), 78-95.

Henderson, S.R. (2011). The role of labor and material schedules in project success. International Journal of Construction Engineering, 14(2), 45-63.

Jackson, L.M. (2010). Material requirements planning for construction projects. Journal of Construction Supply Chain Management, 8(1), 132-145.

Johnson, M.P. (2015). Materials management in construction: Best practices and challenges. Construction Engineering Journal, 10(3), 45-67.

Martinez, R.G. (2017). Strategies for ensuring accurate material scheduling in construction projects. Journal of Materials and Supply Chain Management, 12(2), 102-124.

Smith, J.A. (2018). Effective scheduling strategies for construction projects. Journal of Construction Management, 25(2), 156-175. DOI: 10.xxxxxx

Thompson, A.B. (2019). Best practices for ordering construction materials: A case study analysis. Construction and Building Materials Journal, 32(5), 70-89.

Wilson, R.T., & Taylor, M.K. (2014). The importance of labor scheduling accuracy for project cost control. Project Management Journal, 18(3), 56-78.