Structural Construction Work

Level-IV

Based on October 2023, Curriculum Version 2

Module Title: Control and Order Bill of Materials

Module code: EIS SCW4 M06 1023

Nominal duration: 80 Hours

Prepared by: Ministry of Labor and Skill

October, 2023

Addis Ababa, Ethiopia

Table of Contents

Introduction to Module	ii

Unit One: Concept of bill of material	1

1.1.	Introduction to Bill of Materials	1

1.2.	Time schedule	4

1.3.	Take off sheet format	9

1.4.	Bill of quantities format	12

Unit Two: Bill of quantities	17

2.1.	Introduction	17

2.2.	Bill preparation	18

2.3.	Measurement of different work	21

2.4.	Cost Estimation	45

Unit Three: Resource acquisition process	58

1.1.	Managing organizational resource	58

1.2.	Resource procurement process	60

1.3.	Resource acquisition process	62

1.4.	Financial resource and business principles	64

Unit Four: Resource Administrative Control	70

4.1.	Resource administration system	70

4.2.	Subcontractors and materials supplier agreement	77

4.3.	Resource procurement document	79

4.4.	Staff allocation	81

4.5.	Provision and withdrawal of resources	83

Appendex-1: All necessary drawing for takeoff calculation	88

# Introduction to Module

In the construction industry, a bill of materials (BOM) is a comprehensive list of all the materials, components, and parts required to construct a particular structure or complete a project. It serves as a crucial document that outlines the quantity, description, and specifications of each item needed for the construction process.  This module is designed for structural construction work occupational standard, particularly for the unit of competency: Control and Order Bill of Materials.

This module covers the units:

- Concept of bill of material

- Bill of quantities

- Resource acquisition process

- Resource administrative control

Learning Objective of the Module

- Define concept of bill of material

- Prepare bill of quantities

- Perform resource acquisition process

- Maintain resource administrative control

Module Instruction

For effective use this modules trainees are expected to follow the following module instruction:

- Read the information written in each unit

- Accomplish the Self-checks at the end of each unit

- Perform Operation Sheets which were provided at the end of units

- Do the “LAP test” giver at the end of each unit and

- Read the identified reference book for Examples and exercise

Unit One: Concepts of Bill of Quantity

This unit is developed to provide you the necessary information regarding the following content coverage and topics: - Introduction to Bill of Materials. - Time schedule - Take off sheet format - Bill of quantities format This unit will also assist you to attain the learning outcomes stated in the cover page. Specifically, upon completion of this learning guide, you will be able to: - Understand bill of materials. - prepare time schedule - prepare take off sheet format - prepare bill of quantities format

# Unit One: Concept of bill of material

## Introduction to Bill of Materials

The bill of materials (BOM) is a crucial document used in the construction industry to outline the components, parts, and materials required for a specific project. It serves as a comprehensive inventory list that details the quantity, description, and specifications of each item needed for construction. The BOM provides essential information for estimating costs, procuring materials, managing inventory, and ensuring accurate project planning and execution.

A well-prepared bill of materials facilitates efficient project management by providing a clear breakdown of all necessary materials. It helps construction professionals streamline the procurement process, ensuring that the right quantities and types of materials are ordered at the appropriate time. Additionally, the BOM aids in cost estimation and budgeting, allowing project managers to accurately assess expenses and allocate resources accordingly.

The bill of materials typically includes various categories of items, such as raw materials, components, sub-assemblies, and finished products. Each item is listed with its unique identifier or part number, description, unit of measure, quantity required, and any additional specifications or notes. The BOM may also include information on suppliers or vendors for each item to facilitate procurement.

Construction projects often involve complex assemblies or systems that require multiple components to work together seamlessly. The BOM helps ensure that all necessary parts are accounted for and properly integrated into the overall structure. By providing a detailed inventory of materials, it minimizes the risk of missing or incorrect components during construction.

Control of Bill of Material: Controlling the bill of material involves several key aspects that are essential for effective project management in construction. These aspects include:

- Accuracy and Consistency: Ensuring the accuracy and consistency of the bill of materials is vital to avoid errors and discrepancies during the construction process. This involves verifying that all items listed in the BOM are correct, up-to-date, and aligned with the project specifications.

- Version Control: Managing different versions of the bill of materials is crucial, especially in cases where design changes or modifications occur. Maintaining a clear record of revisions and updates helps prevent confusion and ensures that all stakeholders are working with the latest information.

- Documentation and Traceability: Proper documentation of the bill of materials, including item codes, descriptions, sources, and specifications, facilitates traceability throughout the construction lifecycle. This documentation is valuable for quality control, compliance with regulations, and post-construction maintenance.

- Change Management: Implementing a structured change management process is essential for controlling the bill of materials. This involves evaluating proposed changes to the BOM, assessing their impact on cost and schedule, and obtaining necessary approvals before implementation.

- Integration with ERP Systems: Integrating the bill of materials with enterprise resource planning (ERP) systems streamlines procurement, inventory management, and financial tracking. This integration enhances control by providing real-time visibility into material requirements and availability.

Order of Bill of Material: The order of bill of material refers to the systematic arrangement or sequencing of items listed in the BOM to facilitate efficient procurement, assembly, and construction activities. Key considerations for establishing an effective order include:

- Hierarchy and Structure: Organizing the bill of materials in a hierarchical structure based on assemblies, sub-assemblies, and individual components simplifies ordering processes and helps in understanding the relationships between different items.

- Lead Times and Dependencies: Prioritizing items based on lead times, dependencies, and critical path analysis ensures that materials are ordered in a timely manner to avoid delays in construction activities.

- Supplier Coordination: Coordinating with suppliers to align ordering schedules with project timelines is crucial for maintaining an uninterrupted supply chain. Establishing clear communication channels with suppliers helps in addressing any potential delays or shortages proactively.

- Material Availability: Considering material availability and storage constraints when determining the order of items prevents overstocking or under stocking issues that can impact project timelines and costs.

- Cost Optimization: Optimizing the order of bill of material involves evaluating bulk purchasing opportunities, negotiating favorable terms with suppliers, and minimizing unnecessary inventory holding costs.

In conclusion, effective control and order of bill of material are fundamental to successful construction project management. By implementing robust control measures and strategic ordering practices, construction companies can enhance efficiency, minimize waste, mitigate risks, and ultimately deliver projects within budget and schedule.

## Time schedule

Time schedule in construction refers to the planning and organization of activities within a construction project to ensure that it is completed within a specified timeframe. It involves the identification and sequencing of tasks, estimation of their durations, allocation of resources, and establishment of milestones and deadlines. A well-developed time schedule is crucial for effective project management, as it helps in coordinating various activities, monitoring progress, and ensuring timely completion.

The process of creating a time schedule in construction typically involves the following steps:

- Project Scope Definition: The first step is to clearly define the scope of the project, including its objectives, deliverables, and constraints. This provides a foundation for developing a realistic time schedule.

- Work Breakdown Structure (WBS): The WBS involves breaking down the project into smaller, manageable components or work packages. Each work package represents a specific task or activity that needs to be completed.

- Task Sequencing: Once the work packages are identified, they need to be sequenced in a logical order. Some tasks may be dependent on others and can only start once certain prerequisites are met. This helps in determining the critical path of the project.

- Duration Estimation: Each task /activity needs to be assigned an estimated duration based on historical data, expert judgment/ industry standards. It is important to consider factors such as resource availability, complexity, and dependencies while estimating durations.

- Resource Allocation: Resources required for each task, such as labor, equipment, materials, and subcontractors, need to be identified and allocated accordingly. This ensures that resources are available when needed and prevents delays due to resource constraints.

- Milestones and Deadlines: Milestones are significant events or achievements within the project that mark progress or completion of certain phases. Deadlines are set for these milestones as well as for individual tasks to ensure timely completion.

- Schedule Optimization: Once the initial schedule is developed, it is reviewed and optimized to identify any potential bottlenecks or conflicts. Adjustments may be made to improve efficiency, reduce risks, or accommodate changes in project requirements.

- Monitoring and Control: Throughout the construction process, the time schedule needs to be regularly monitored and controlled. Progress is tracked against the planned schedule, and any deviations or delays are identified and addressed promptly.

- Schedule Updates: As the project progresses, updates to the time schedule may be necessary due to unforeseen circumstances, changes in scope, or other factors. These updates should be communicated to all stakeholders to ensure everyone is aware of the revised timeline.

In summary, a well-developed time schedule is essential for successful construction project management. It helps in coordinating activities, monitoring progress, and ensuring timely completion. By following a systematic approach and considering various factors, construction professionals can create an effective time schedule that meets project objectives.

Common Construction Schedule Types:

- Gantt chart: A Gantt chart is a widely used scheduling tool in construction projects. It provides a visual representation of the project schedule, showing the start and end dates of each task or activity. The chart consists of horizontal bars that represent the duration of each task, with dependencies between tasks indicated by arrows. Gantt charts help project managers track progress, identify critical paths, and allocate resources effectively.

Gantt charts advantages

Gantt charts are very helpful for finding new ways to look at your project, which will help you identify the best path toward completion. They also simplify the management of projects that involve many overlapping activities. The bar layout makes it very easy to shuffle projects around if overlapping proves to be an issue. Gantt chart becomes quite popular in all types of company management applications. This makes it easy for even laymen to understand your project’s progress.

Gant chart disadvantages

If you have a massive project with hundreds of tasks taking place at the same time, a Gantt chart will quickly become confusing. The bar layout also does not really provide context as to how much work and resources are required for the completion of a particular task—only how long it’s expected to take. Gantt charts are also impractical for large projects, given how difficult it can be to print all of the relevant information out on a reasonable amount of paper.

- Critical Path Method (CPM): The Critical Path Method is a project management technique that identifies the sequence of activities that must be completed on time for the project to finish within the scheduled timeframe. CPM analyzes the interdependencies between tasks and calculates the longest path of activities, known as the critical path. By focusing on the critical path, project managers can prioritize resources and monitor progress to ensure timely completion. CPM is well suited for large projects with many interdependent tasks.

Critical path method advantages

The critical path method is valuable when you’re looking to identify the most appropriate sequence in which a project’s tasks must be completed. As its name suggests, it also helps identify the most critical “branch” of your project’s path, allowing you to very easily see which tasks are essential for project completion and what are merely supportive of those tasks.

Critical path method disadvantages

The critical path method may not be the only type of construction schedule you rely on. This is particularly true on projects involving hundreds of interdependent tasks. While you may identify a critical path in such a scenario, you may fail to adequately account for resources required by tasks dependent on those within the path. In other words, the critical path method is not a one-size-fits-all solution for scheduling construction projects.

- Program Evaluation and Review Technique (PERT): is a scheduling method commonly used in large-scale construction projects where uncertainty exists regarding task durations. PERT incorporates three estimates for each activity: optimistic, pessimistic, and most likely durations. By considering these estimates, PERT calculates expected durations and probabilities for completing the project within a given timeframe. This technique helps project managers assess risks and make informed decisions regarding resource allocation. PERT is more appropriate for projects with uncertain task durations.

PERT Advantages

PERT lays your schedule out very neatly and allows for differentiation between fixed deadlines and milestones. It also keeps fixed deadlines top-of-mind and features a layout simple enough to encourage collaboration across many teams, even in the context of complex projects. PERT also encourages you to create different timelines for activity completion, including the following:

- Optimistic time: This is the best-case scenario.

- Pessimistic time: This is the longest foreseeable time it will take you to complete a task.

- Most likely time: Assuming no major challenges present themselves, this is the time your activity should be completed.

- Expected time: Accounting for problems (which are largely inevitable in construction anyway), this is an estimate of how long it will take to complete the activity in question.

PERT disadvantages

If you’re running multiple projects that share resources, a PERT chart won’t accurately convey that. PERT can also become quite complicated on projects involving thousands of interdependent tasks, increasing your expenses and maintenance efforts. Your ability to provide accurate timelines for activity completion will also be limited by your previous expertise. Unless you have access to relevant and useful data, your predictions will likely be way off.

- Line of Balance (LOB): The Line of Balance scheduling technique is particularly useful for repetitive construction projects, such as high-rise buildings or infrastructure developments. LOB divides the project into separate segments or zones and allocates resources based on a predetermined production rate for each zone. This method ensures a smooth flow of work by synchronizing activities across different zones, minimizing delays, and optimizing resource utilization. Line of Balance is often used in construction projects, as it helps to ensure that tasks are completed in a timely manner. Meanwhile, the Critical Chain Method has been gaining popularity in recent years, as it helps mitigate disruptions and the effects of delays.

Line of balance method advantages

On projects involving lots of repetition, it can be tricky to discuss your actual progress alongside a formal objective plan. The line of balance method addresses this challenge. It also helps in forecasting your team’s future performance. Both of these advantages are very useful for effective resource and workforce management.

Line of balance disadvantages

The line of balance technique is suited toward assembly line-type tasks with several similar phases. Other construction schedule types would make more sense for tasks not involving that sort of repetition. It’s also difficult to get an overview of the entire project’s critical path since the line of balance only displays progress on individual activities.

## Take off sheet format

Introduction

This is a process of measuring or scaling dimensions from drawings and recording all dimensions in an easily understood format. This is coupled with the descriptions in the drawings and specification.

In this task the quantity surveyors “take off” the quantities from the drawings and determine the volume of work to be done for the various components. These quantities are calculated in a specially prepared format, as to aid accurate preparation and enable checking/rechecking or adjusting of amounts and correcting errors if any.  These special formats are called “Take off sheets” or “Dimension Paper”.

Takeoff sheet is the general form of listing and taking off types, sizes and quantities of material required in a bidding process of any construction work. Take off sheet is commonly used in the construction industry to refer to a document that lists all the materials and quantities required for a specific project. It is an essential part of the estimating process, allowing contractors to accurately determine the costs associated with a construction project. The take-off sheet serves as a detailed inventory of materials needed, enabling contractors to prepare accurate bids and budgets.

The take-off sheet typically includes information such as the type and quantity of materials required their dimensions or specifications, and any additional notes or instructions. It is created based on architectural and engineering drawings, specifications, and other project documents. The purpose of the take-off sheet is to provide a comprehensive breakdown of all the materials needed for each aspect of the project, including structural elements, finishes, mechanical systems, electrical systems, and more.

Creating a take-off sheet involves a meticulous process of reviewing project documents, identifying all relevant materials, quantifying their requirements, and organizing the information in a clear and structured format. This allows contractors to have a detailed understanding of the scope of work and accurately estimate the costs associated with each material.

The take-off sheet is crucial for several reasons:

- Accurate cost estimation: By providing a detailed breakdown of materials and quantities required for a project, the take-off sheet enables contractors to estimate costs accurately. This helps in preparing competitive bids and budgets while ensuring profitability.

- Material procurement: The take-off sheet serves as a reference for procuring materials. It provides a comprehensive list that can be shared with suppliers to obtain accurate quotes and ensure timely delivery.

- Project planning: The take-off sheet helps in planning the logistics of a construction project. It provides insights into the volume and types of materials required at different stages, allowing for efficient scheduling and coordination.

- Subcontractor coordination: The take-off sheet can be shared with subcontractors to ensure they have a clear understanding of their scope of work. It helps in coordinating their activities and ensures that all necessary materials are accounted for.

- Change management: During the course of a construction project, changes may occur that require adjustments to the materials required. The take-off sheet serves as a reference point for managing these changes and updating the estimates accordingly.

Overall, the take-off sheet is a vital tool in the construction industry, enabling accurate cost estimation, efficient material procurement, effective project planning, subcontractor coordination, and change management.

Take off sheet format

Project: ____________________________

Page ----of----

| 1 | 2 | 3 | Description | 1 | 2 | 3 | Description |
| --- | --- | --- | --- | --- | --- | --- | --- |

The purpose of each column

Column 1 is called the ‘timesing column’ in which multiplying figures are entered when there is more than one of the particular items being measured.

Column 2 is called the ‘dimension column’ in which the actual dimensions, as scaled or taken direct from the drawings, are entered. There may be one, two or three lines of dimensions in an item depending on whether it is linear, square or cubic.

Column 3 is called the ‘squaring column’ in which the length, area or volume obtained by multiplying together the figures in columns 1 and 2 is recorded, ready for transfer to the abstract or bill.

Column 4 is called the ‘description column’ in which the written description of each item is entered. This column is frequently used to accommodate preliminary calculations and other basic information.

## Bill of quantities format

The Bill of Quantities (BOQ) is a document commonly used in the construction industry to provide a detailed breakdown of the quantities and costs of materials, labor, equipment, and other resources required to complete a construction project. It serves as an essential tool for estimating project costs, tendering processes, and contract administration. The BOQ is typically prepared by a quantity surveyor or an estimator and is based on the project’s architectural and engineering drawings.

The primary purpose of the BOQ is to provide a clear and comprehensive description of the work to be done and the materials to be used in a construction project. It enables contractors to accurately price their bids by providing them with detailed information about the quantities of each item required. The BOQ also allows for effective cost control during the construction phase by providing a basis for comparing actual costs against estimated costs.

The contents of a typical BOQ may vary depending on the complexity and nature of the project, but it generally includes the following elements:

- Preliminaries: This section includes general information about the project, such as site preparation, temporary works, insurance requirements, and any other necessary preliminary activities.

- Measurement rules: The BOQ specifies the measurement rules to be used for each item, ensuring consistency in quantification across different contractors’ bids.

- Bill items: The main part of the BOQ consists of individual bill items that describe each element of work required for the project. Each item is assigned a unique identification number and includes a description, unit of measurement, quantity required, rate or price per unit, and extended amount (quantity multiplied by rate).

- Provisional sums: Provisional sums are included in cases where certain aspects of the project cannot be accurately quantified at the time of tendering. These sums allow for flexibility in pricing until more precise information becomes available.

- Contingencies: are allowances included in the BOQ to account for unforeseen circumstances or changes in the project scope that may arise during construction.

- Summary: The BOQ concludes with a summary section that provides a breakdown of the total estimated cost for each element of work and the overall project.

Format for preparing BOQ

The main sections included in the bill of quantities are Form of Tender, Information, Requirements, Pricing schedule, Provisional sums, and Day works. For the preparation of BOQ, 5 main components are to be considered which are as follows:

- Item Description

- Unit

- Quantity

- Unit rate

- Total Amount

- Remark

Table of bill of quantity

| No | Item Description | Unit | Qty. | Unit rate | Total rate | Remark |
| --- | --- | --- | --- | --- | --- | --- |
|  | SUB- STRUCTURE |  |  |  |  |  |
|  | 1.Excavation and earth work |  |  |  |  |  |
| 1.1 | Site clearance (top soil Excavation) |  |  |  |  |  |
|  | Total carried to summary |  |  |  |  |  |
|  | B. SUPPER STRUCTURE |  |  |  |  |  |
|  | Concrete work |  |  |  |  |  |
| 1.1 |  |  |  |  |  |  |
|  | Total carried to summary |  |  |  |  |  |

Self-Check 1.1

Part I: Multiple choices

Instruction: I. Select the correct answer for the give choice. You are provided a minute for each question and each carry 3 Points.

1. The bill of materials (BOM) is used in the construction industry to:

a) Outline project objectives

b) Manage financial tracking

c) Specify project timelines

d) Detail required components and materials

2. Which of the following is a key aspect of controlling the bill of material?

a) Resource allocation

b) Supplier coordination

c) Cost optimization

d) Accuracy and consistency

3. What is the purpose of integrating the bill of materials with ERP systems?

a) Streamline procurement and inventory management

b) Ensure accurate project planning and execution

c) Facilitate traceability throughout the construction lifecycle

d) Evaluate proposed changes to the BOM

4. The order of bill of material refers to:

a) The sequencing of tasks within a construction project

b) The hierarchical structure of the BOM

c) The coordination with suppliers for material procurement

d) The negotiation of favorable terms with suppliers

5. Time schedule in construction is important for:

a) Coordinating various construction activities

b) Managing the bill of materials

c) Controlling project costs

d) Optimizing material availability

Part II: True or False Questions

Instruction:  Say True or False.  You are provided 2 minute for each question and each has 5Points.

1. The bill of materials includes information on suppliers or vendors for each item.

2. Change management is not necessary for controlling the bill of materials.

3. The order of bill of material should prioritize items based on their complexity.

4. A Gantt chart is a scheduling tool commonly used in construction projects.

5. The critical path method is suitable for large projects with many interdependent tasks.

Part III: Short Answer

Instruction:  Give short Answer for the following question and write your Answer on your answer sheet. You are provided 5 minute for each question and each has 5Points.

1. What are the key aspects of controlling the bill of material?

2. Explain the importance of integrating the bill of materials with ERP systems.

3. What factors should be considered when determining the order of bill of material?

4. Define time schedule in construction and its significance.

5. Name two common construction schedule types and briefly describe their advantage

You can ask you teacher for the copy of the correct answers.

Name:  _________________________               Date:  _______________

Unit Two: Bill of Quantity

This unit is developed to provide you the necessary information regarding the following content coverage and topics: - Take off sheet - Bill preparation - Measurement of different work - Cost estimation This unit will also assist you to attain the learning outcomes stated in the cover page. Specifically, upon completion of this learning guide, you will be able to: - Perform take off sheet - Prepare bill - Measure different work - Estimate cost

# Unit Two: Bill of quantities

## Introduction

Before starting any construction one has to have a thorough knowledge about the volume of the work and the probable cost that may be required for the completion of the project. Otherwise, the construction will be stopped before its completion due to shortage of money or materials.

Types of estimates

- Approximate/Rough estimate

- To get an idea for the probable expenditure in a short time

- To prepare a preliminary estimate before drawing up a detailed estimate for a project. This is based on the prior costs of similar projects.

- A detailed estimate

- This is the best method and includes the quantities and cost of work.

- Requirements: drawings and specification

Purpose of quantity surveying

- To know the amount of money required

- To know the quantities of materials required

- To know the tools and equipment required for the construction

- To know the different workers to be employed

- To draw up the construction schedule and program

- To fix up the completion period

- To invite tenders

- To Obtain sanction of necessary funds from the concerned authority For valuation of an existing structure

## Bill preparation

There are three processes in the preparation of the completed bill of quantities.

- Taking-off quantities

- Abstracting or ‘working-up’

- Billing

- Taking –off quantities

In the first instance quantities need to be extracted from drawings, together with an appropriate description. This process - known as booking dimensions or taking-off quantities- involves the measurer in either reading or scaling dimensions from the drawings. There are two distinct parts to this. The first involves the recording of quantities, whilst the second required a written description to accompany the quantity. The sequence adopted by measurers in this initial stage bears little relation to the eventual order of the finished bill of quantities. This is because ‘taking-off’ has been devised in order to assist the measurer with both the speed and accuracy of recording dimensions.

Dimensions are taken from a drawing and recorded on specially lined paper known as dimension paper.

The format of standard dimension paper

The A4 page is divided vertically into two identical halves each comprising a set of four columns. These are labeled for the purpose of identifications. The extra column on the extreme left is called the binding margin and would not normally be used for recording dimensions.

General principles of taking-off

1. Entering dimensions

Dimensions are entered in the dimension column in meters to two places of decimals. The four principal units of measurement are:

- Enumeration (no. or pcs.)

- Length (m)

- Area (m2)

- Volume (m3)

For enumerated items whole numbers are entered in the dimension column, with a line drawn horizontally beneath each single entry. The order of recording dimensions is:

- Length

- Width/breadth

- Vertical height/depth

2. Abbreviations

Many of the words entered in the description column are abbreviated in order to save space and time in entering the item by highly skilled technical staff.  Many abbreviations have become almost standard and are of general application; for this reason, there is a list of the more common abbreviations.

3. Grouping of dimensions

Where more than one set of dimensions relate to the same description, the dimensions should be suitably bracketed so that this shall be made clear.

Where the same dimensions apply to more than one item, the best procedure is to separate each of the descriptions by an ampersand ‘&’ sign and to bracket the descriptions.

4. Adjustment of openings and voids

When measuring areas with openings or voids, the most convenient practice is usually to measure the full area in the first instance, and to subsequently adjust for any voids or openings.

5. Order of taking off

The order of taking off largely follows the order of construction to simplify the work and to reduce the risk of items being missed.

- Abstracting or ‘Working up’ bill of quantities

The sequence adopted by measurers follows construction operations as they occur on site. However, once the take-off is complete, these measured items need to be collated, like items must be merged and deduction adjustments made. This process, known as abstracting or working-up quantities, is carried out on specially lined A3 size paper.

At the head of each abstract a work section heading is recorded. Each measured item is copied from the dimension column and transferred to the abstract. In an effect to avoid double transfer, or the omission of an item, each description is lined through on the dimension sheet as it is transferred.

Descriptions are copied spanning two columns on the abstract and a horizontal line is drawn below each transferred description. The squared quantity is entered below this line, additions on the left and deductions on the right. To provide a cross-reference to the dimension page, each squared quantity is labeled with its source (i.e., the dimension page number)

Related work section items from different parts of the take-off will appear on the same abstract. The abstracted items should be well spaced apart, allowing the later insertion of omitted items. Once all measured items have been transferred to the abstract, the quantities are totaled and rounded to the nearest whole unit.

- Billing

This is the final stage in the preparation of the completed bill of quantities. The effort of assembling and ordering was completed at the abstracting stage and all that remains is for the descriptions and quantities to be presented in a structured and consistent fashion. There are three levels of heading and they have the following titles:

- Level 1: Group (e.g. Substructure)

- Level 2: Sub-group (e.g. Earthwork)

- Level 3: work section (e.g. Site clearance)

## Measurement of different work

The general approach to measurement will require the separation of works between substructure and superstructure

The terms ‘substructure’ and ‘superstructure’ describe all structural works below and above ground level respectively.

The substructure is likely to include:

- Ground work

- Concrete work

- Masonry work

The superstructure most likely includes:

- Concrete work

- Masonry work

- Roofing

- Carpentry and joinery

- Metal work

- Finishing

- Glazing

- Sanitary installation

- Electrical installation

The demarcation between the substructure and superstructure should be taken as the damp proof course in structural walls. The ground floor slab would be measured with substructure work.

- Groundwork

- Site Preparation/Over site Excavation

It includes removal of trees and tree stumps, and clearing site vegetation. Removal of trees and tree stumps is measured as enumerated item. Tree girths are measured at a height of 1.00m above ground and stump girths at the top. Clearing site vegetation is measured in m2 and embraces bushes, scrub, undergrowth, hedges, trees and tree stumps < 600 mm.

- Excavation

It includes the following items:

- Topsoil excavation

- Excavation to reduce levels

- Excavation for foundation/ Deep excavation

- Backfilling

- Disposal of excavated material

Topsoil Excavation

The surface of most ‘green field’ sites comprises a compactable layer of vegetable matter called ‘topsoil’. It is measured in m2 stating the average topsoil depth in the description. A clearance around the entire basic plan must be left, usually about 1.0-1.5m is allowed on each side of a building. Disposal of this material off the site is measured in m3, giving details of specified locations and handling where appropriate.

Excavation to Reduce Levels

Where the site is sloping then further excavation is required to reduce the level of the ground to the specified formation level; this excavation is measured in m3, giving the maximum depth range in the description.

Deep Excavation

It is the actual excavation for the foundation and measured in m3. All excavation is measured net for increasing in bulk after excavation.

Backfilling

Once the foundation of the building is constructed, one of the next steps in construction is the backfilling. It is the put back of soil that is removed during the deep excavation or selected material from somewhere else.

Disposal of Excavated Materials

Removing excavated material from the site often costs more than the initial excavation. For this reason, it is always necessary to measure disposal of excavated materials as a separate item in m3. It is necessary to describe where and how the material is to be transported.

- Masonry work

The measurement of masonry work requires the separation between substructure and superstructure. With some exception, the principal unit of measurement for masonry work is m2. The two dimensions needed to provide this area are the centerline length and the height of the walling. The description will identify the walling thickness, the type of masonry unit, the bond, the type of mortar and the pointing. Rather than repeating these details in every description, a heading can be established to include the majority of this information. The subsequent descriptions need only make reference to the wall’s thickness and whether it is face work on one or both sides.

The majority of cavity or hollow walls are constructed with an outer leaf in brickwork, a cavity, which may or may not be insulated, and an inner leaf of block work.  Each of these layers will require measuring as a separate item and each will require a separate waste calculation in order to determine its center line length. If the cavity includes any rigid sheet insulation, this can be incorporated as part of the description of forming cavities, stating type, thickness and method of fixing. The normal order of measurement is:

- External walls

- Internal walls

- Chimney breasts and stacks

External walls

The length of external walling will be obtained by the method of girthing and the height will normally be taken up to some convenient level, such as the general eaves line. Any additional areas of external wall, such as gables, parapets and the like will be then taken off. Finally, adjustment of walling for windows and door openings will be made.

Internal walls

The measurement of external walls is usually followed by internal walls, which may be of bricks or blocks. A careful check should be made on the type and thickness of each partition.

- Concrete Work

The Measurement of concrete work comprises the measurement of the concrete (Plain concrete) and the reinforcement bars. The unit of measurement for the concrete is m3. The descriptive part of the measurement identifies the type (characteristic compressive strength), the mix proportion, and the work for the placement and compaction. The steel bars are measured in kg. Quantities are taken from the structural drawing and recorded on bar schedule.

Bar schedule

| D.no | Location | Remark | Shape | Dim. | Length | No. of bar | No. of member | 6 | 8 | 10 | 12 | 14 | 16 | 20 | 24 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total Length |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Weight(Kg/m) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Total weight |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Linear density for the determination of the quantity of bars (kg)

|  (mm) | 6.0 | 8.0 | 10.0 | 12.0 | 14.0 | 16.0 | 20.0 | 22.0 | 25.0 | 28.0 | 32.0 | 36.0 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Density | 0.22 | 0.39 | 0.62 | 0.89 | 1.21 | 1.58 | 2.47 | 2.98 | 3.85 | 4.85 | 6.31 | 7.99 |

- Roof work

The measurement of pitched and flat roofs conveniently divides between the roof structure and the roof covering. In practice the measurement of roof coverings will follow the measurement of the roof structure. Eave and barge boarding together with guttering and down pipes are normally included as part of the measurement of roof coverings.

The principal unit of measurement for roof coverings is m2. The descriptive part of the measurement must identify the kind, quality and size of materials, together with the method of fixing. The measurement of the main roof slope area should be followed by adjustments for chimneys and dormers. No adjustment is made to the roof covering area for voids of less than one square meter in area. Ridges, hips, valleys, eaves and the like are all measured in linear meters.

The Unit of measurement for roof structure naturally falls between enumerated items (trusses) and linear meters, (rafters and purlins). In the case of the latter the description must include the cross sectional dimensions of the material being used; whist the former must fully describe the truss.

Measurement of Pitched Roof Coverings

The area of roof coverings is unaffected by the inclusion of hipped ends and valleys as long as the roof pitch remains constant.

Illustration:

Combination of Hipped Gabbled

Hipped

Gabbled

When measured, all three will provide the same roof slope area, regardless of whether they are hipped, gabled or a combination of the two.

In each case the sloping roof area can be established by initially ignoring any projects, valleys or hips and simply measuring the main length (L) multiplied by the roof slope length (s). Some surveyors choose to enter the dimensions for the roof slope area by recording the plan area of the roof in the dimension column and timesing this by the natural secant of the roof slope in the timesing column. Others prefer to establish the roof slope length as a waste calculation first and then record the plan length and the roof slope length in the dimension column. This is the timesed by two for each roof slope in the timesing column.

Fascia, eaves and verge boarding

Eaves soffit boarding (fascia and soffit) together with verge (barge) boards not exceeding 300 mm girth are measured in linear meters giving their size in the description. Where boards exceed 300 mm wide they may be measured superficially.

Rainwater gutters and down pipes

The measurement of rainwater goods completes the work associated with roof coverings. Gutters and down pipes are measured in linear meters over all fittings. The description should include reference to the type of pipe or gutter, its nominal size, and the type, method and spacing of fixings. Fittings, such as running outlets, stopped ends, offsets  and connecting shoes, are enumerated and measured extra over the pipe or gutter on which they occur.

- Finishing work

The term ‘Finishing’ includes operations associated with the completion of the floors, walls and ceilings of a building. These are screeding, plastering, wall and floor tiling, wallpapering and painting.

Sequence of Measurement

In the measurement of this work, it is essential to adopt a logical order in taking off work. The order of measurement of finishing on each floor will normally be:

- Ceiling

- Walls

- Floors

Linear items like skirting will follow the measurement of the main areas of wall finishing.

General rules of measurement

Work to attached beams is included with ceiling finishes, whilst work to attached columns is included with wall finishes. Finishes to isolated beams and columns must be given separately as should work in staircase. The principal unit of measurement for wall, floor and ceiling finishes is m2. Where the width does not exceed 300 mm the unit of measurement is linear.

Ceiling Finishing

The ceiling area is measured in m2 between wall surfaces, stating in the description the thickness and the number of coats. In cases where the ceiling finishes are identical throughout a floor, it may be appropriate to measure gross, over internal walls, and subsequently deduct the plan area of internal walls from the gross ceiling area.

Wall Finishing

The measurement of wall finishing is taken from floor to ceiling. The perimeter length of each room should be established as a waste calculation and then transferred to the dimension column where it is followed by the floor to ceiling height. Where the wall finishing are of tiles, full particulars of the finishing are to be given, such as kind, quality and size of materials, and method of fixing.

Skirting

Skirting are measured in linear meters and usually included with the measurement of wall finishing. Everything is based on room girths and can be ampersand to the dimensions established for wall plaster purposes (assuming the constant dimension approach is adopted).

Floor Finishing

Cement and sand screeds together with tiled or wood block floors are measured in m2. In some situations, it is possible to utilize the previously booked ceiling areas for the measurement of floors. The use of an ampersand to link these two sets of dimensions can save a great deal of time, but care should be taken to ensure the respective areas are consistent.

Painting

The unit of measurement for painting is based on the girth of the surface to be painted. Where it exceeds 300 mm it is measured as an area and where it is an isolated surface and does not exceed 300 mm in girth, it is measured in linear meters.

- Plumbing work

Plumbing installations in domestic buildings involve a number of different systems associated by the supply, distribution and disposal of water within and out of a building - above the ground and below the ground.

Order of Measurement

- Connection to water authority’s main and all work up to boundary of site

- Underground service and rising main from site boundary up to cold water storage tank

- Branches to rising main

- Cold water storage tank or cistern and associated work

- Down services with branches

- Sanitary appliances such as sinks, wash basins, baths and water closets

- Discharge pipes – waste, soil and vent pipes

- Any other work connected with the plumbing installation

The order is following the flow of water as it enters and is distributed around the building, and collected after being used.

Pipe work

Pipes are measured in linear meters over all fittings and branches, stating the type, nominal size and the method of jointing and fixing. Fittings are enumerated and measured as extra-over the pipe work on which they occur.

Equipment

In a domestic situation this will include such things as boilers, pumps, cisterns and cylinders. These are enumerated giving in the description the type, size, pattern, rated duty, capacity and method of fixing.

Sanitary Appliances

This includes washbasins, urinals, baths, bidets, shower trays and sinks. These appliances are enumerated giving details in the description of their type, size, capacity and method of fixing.

Waste pipe work

It embraces all the pipe work and fittings that are associated with the disposal of used or soiled water, and vent pipe. The following diameters of pipe are required for the different appliances:

- Washbasin	32 mm dia.

- Bath/shower/sink	40 mm dia.

- Water closet (WC)	110 mm dia.

Waste pipe work is measured in linear meters, giving in the description details of the type of the pipe, its nominal size, the method of jointing and the type of pipe brackets. Fittings – elbows, tees and the like – are enumerated as extra-over the pipe work on which they occur.

Drainage work

It is the disposal of used and surface water from a building to a point of disposal or treatment. Drains include excavation of pipe trenches, drain pipes and fittings. Pipes are measured over all fittings and branches in linear meters, stating the kind of pipe work, the nominal size and the method of jointing. Pipefittings, such as bends and branches, are enumerated extra-over the pipe on which they occur.

The excavation, concrete work, brickwork and rendering associated with manholes and septic tanks are measured in accordance with the rules for the appropriate work section.

- Electrical Installation work

Electricity can only be transmitted through a conductor when there is a complete circuit from the source, via a conductor, back to the source. Each conductor cable contains a ‘live’ wire carrying the power to an appliance, a ‘neutral’ wire carrying the power back to the source and an earth wire which reduces the risk of shock by carrying the current to a circuit breaker or the ground in the event of a short-circuit. The conductor used for the domestic supplies is copper wire.

Cables are identified by the cross sectional area of the conductors and this is expressed in mm2. The more common cable sizes and the number of wiring circuits found in domestic wiring installations are given below.

| 1.00 or 1.50 | Lighting Circuits | One per floor |
| --- | --- | --- |
| 2.5 | Power Circuits | One per floor |
| 2.50 | Immersion heater | Single circuit per appliance |
| 10.00 | Cooker | Single circuit per appliance |
| 10.00 | Spontaneous shower | Single circuit per appliance |

Cabling

Conduit and cable are each measured separately in linear meters stating in the description the type and size of cabling.

Switches, Socket outlets and Light Points

As a separate enumerated item socket outlet, light points (luminaries) and other accessories should be enumerated.

Appliances

Separately fused circuits will be necessary for the cooker, immersion heater and electric heating units, and are enumerated items.

TAKE-OFF SHEET

Prepare take off sheet and bill of quantity for the given design of a building.

|  |  |  |  | DISCRIPTION |
| --- | --- | --- | --- | --- |
|  |  |  |  | A-SUB-STRUCTURE |
|  |  |  |  | 1. Excavation and Earth Work |
|  | 7.00 6.40 | 44.80 |  | 1.1. Clear the site to an average depth of 200mm to remove the top soil with 1m working area in all sides. |
| 4/ | 1.80 1.40 1.3 | 13.10 |  | 1.2. Pit excavation for isolated footings on ordinary soil to a depth not exceeding 1800mm from ground level (use working space 25 cm on both sides). |
|  | 12.60 1.00 1.00 | 12.60 |  | 1.3. Trench excavation for 50cm thick stone foundation wall on ordinary soil to a depth not exceeding 1000mm use 25cm working space on each side. |
|  | 4.30 3.70 | 15.91 |  | 1.4. Bulk excavation to the depth not exceeding 250mm. |
|  |  |  |  | 1.5. Back fill with an already excavated material around footings and foundation by watering and ramming in 25cm layers. |
|  |  | 13.10 |  | 1.5.1. Volume of pit excavation |
| 4/ | 0.90 0.80 0.30 | 0.86 |  | 1.5.2. deduct, volume of footing pad |
| 4/ | 0.20 0.20 1.50 | 0.24 |  | 1.5.3. ditto volume of footing column |
|  |  | 12.00 |  | Total volume of back fill around footing pad and footing column |
|  |  | 12.60 |  | 1.5.4. Volume of trench excavation. |
|  | 18.00 1.00 0.50 | 9.00 |  | 1.5.5. Deduct for volume of footing column and foundation wall. |
|  |  | 3.60 |  | 1.5.6. Total volume of back fills around foundation wall. |
|  |  | 13.60 |  | 1.5.7. Total volume of back fills around footing pad, footing column and foundation wall. |
|  |  |  | 25.04 | 1.6 Disposal of surplus excavated material away from the construction site and site clearance. Note: Assume that all excavated material will be disposed. Total soil = (SC + DE + TE + BE) - BF SC= (44.80 m2 *0.2 + 13.10 + 12.60 + 15.91*0.25) – 13.60 |
|  | 4.30 3.70 |  | 15.91 | 1.7. 25cm thick basaltic or equivalent stone hard core crushed and blinded. |
|  |  |  |  | 2. Concrete work |
| 4/ | 0.90 0.80 |  | 2.88 | 2.1. 5cm thick C-5 lean concrete with minimum cement content of 150kg/m3 laid under footing pads. |
|  | 18.00 0.5 |  | 9.00 | 2.1.1. Lean concrete under stone foundation wall with footing column area. |
| 4/ | 0.20 0.20 |  | 0.16 | 2.1.2. Deduct footing column area. |
|  |  |  | 8.84 | 2.1.3. Area of lean concrete under foundation wall. |
|  |  |  |  | 2.3. C-25 concrete well vibrated and compacted around reinforcement bars (form work and reinforcement measured separately). |
| 4/ | 0.90 0.80 0.30 |  | 0.86 | 2.3.1 Volume of concrete in footings pad |
| 4/ | 1.50 0.20 0.20 |  | 0.24 | 2.3.2. Volume of concrete in footing column |
|  | 18.00 0.30 0.20 |  | 1.08 | 2.3.3. Volume of concrete for grade beams |
|  | 4.30 3.70 |  | 15.91 | 2.3.4.In 10 cm thick ground floor slab |
|  |  |  |  | 2.4.Cut, fix/assemble sawn zigba wooden form work for: |
| 4/2/ | 0.90 0.30 |  | 2.16 | 2.4.1. Footing pads |
| 4/2/ | 0.80 0.30 |  | 1.92 | 2.4.2. Footing pads |
|  |  |  | 4.08 | Total area of footing pad |
| 4/4/ | 1.50 0.20 |  | 4.80 | 2.4.3.Footing columns |
|  |  |  |  | 2.4.4.Grade beam |
| 2/ | 5.00 0.30 |  | 3.00 | External side on long span |
| 2/ | 4.40 0.30 |  | 2.65 | External side on short span |
| 2/ | 4.60 0.30 |  | 2.76 | Internal side on long span |
| 2/ | 4.00 0.30 |  | 2.40 | Internal side on short span |
|  |  |  | 10.81 | Total area of formwork for grade beam. |
|  |  |  |  | 2.7.Provide and fix high yield strength reinforcement bars (price includes cutting , bending and fixing) |
|  |  |  | 125.33 | 2.5.1. Ø 8mm |
|  |  |  | 23.91 | 2.5.2. Ø 10mm |
|  |  |  | 53.71 | 2.5.3. Ø 12mm |
|  |  |  | 54.35 | 2.5.4. Ø 14mm |
|  |  |  |  | 3. Masonry work |
|  | 18.00 0.50 1.00 |  | 9.00 | 3.1.50cm thick trachytes or equivalent stone foundation wall bedded in cement mortar of 1:4 ratio below ground level |
| 4/ | 1.00 0.20 0.20 |  | 0.16 | Deduct volume of footing column up to foundation wall depth. |
|  |  |  | 8.84 | Total volume of foundation wall. |
|  |  |  |  | B. Superstructure |
|  |  |  |  | 1. Concrete work |
|  |  |  |  | C-25 concrete well vibrated and compacted around reinforcement bars (form work and reinforcement measured separately) |
| 4/ | 3.00 0.20 0.20 |  | 0 .48 | 1.1 In elevation columns |
|  | 18.00 0.20 0.20 |  | 0.72 | 1.2 In top tie beams |
|  |  |  |  | 1.3. Cut, fix/assemble Sawn zigba wooden form work: |
| 4/4/ | 3.00 0.20 |  | 9.60 | 1.3.1 Elevation columns |
|  |  |  |  | 1.3.2. Top tie beams |
| 2/ | 5.00 0.20 |  | 2.00 | External side on long span |
| 2/ | 4.40 0.20 |  | 1.76 | External side on short span |
| 2/ | 4.60 0.20 |  | 1.84 | Internal side on long span |
| 2/ | 4.00 0.20 |  | 1.60 | Internal side on short span |
|  |  |  | 7.20 | Total area of formwork for Top tie beams. |
|  |  |  |  | 1.4. Provide and fix high yield strength reinforcement bars (price includes cutting, bending and fixing). |
|  |  |  | 43.95 | 1.4.1. Ø8mm |
|  |  |  | 23.91 | 1.4.2. Ø10mm |
|  |  |  | 52.28 | 1.4.3. Ø12mm |
|  |  |  |  | 2. Masonry work |
|  |  |  |  | 2.1. 20cm thick class B hollow concrete block masonry bedded in cement mortar of 1:4. |
| 2/ | 4.60 3.00 |  | 27.60 | Wall area below top tie beam in front and rear side |
|  | 0.66 1.80 |  | 1.88 | Deduct for window |
|  | 0.85 3.00 |  | 2.55 | Ditto for Door |
|  |  |  | 23.17 | Net wall area below top tie beam in front and rear side |
|  | 5.00 1.20 |  | 6.00 | Wall area above top tie beam in rear side |
| 2/ | 4.00 3.00 |  | 24.00 | Wall area below top tie beam in right and left side |
| 2/1/2 | 4.00 1.20 |  | 4.80 | Wall area above top tie beam in right and left side |
|  |  |  | 57.97 | Total area of 20cm thick HCB |
|  |  |  |  | 3. Roof work |
|  | 5.00 5.00 |  | 25.00 | 3.1. Supply and fix G-28 corrugated sheet of iron with all accessories (measurement taken in horizontal projection), Eave dimension = 0.45m to the front side |
|  |  |  |  | 4. Finishing work |
|  |  |  |  | 4.1. Apply 3 coats of 25mm thick cement mortar plastering in ratio of 1:4 to internal walls. |
| 2/ | 4.60 3.20 |  | 29.44 | Wall area with top tie beam in front and rear side |
|  | 0.66 1.80 |  | 1.88 | Deduct for window |
|  | 0.85 3.00 |  | 2.55 | Ditto for Door |
|  |  |  | 25.01 | Net wall area with top tie beam |
| 2/ | 4.00 3.20 |  | 25.06 | Wall area with top tie beam in right and left side |
|  |  |  | 50.07 | Total area of internal wall plastering. |
|  |  |  |  | 4.2. Apply 3 coats of 25mm thick cement mortar plastering in ratio of 1:4 to external walls with column. |
| 2/ | 5.00 3.20 |  | 32.00 | External wall area with top tie beam in front and rear side |
|  | 0.66 1.80 |  | 1.88 | Deduct for window |
|  | 0.85 3.00 |  | 2.55 | Ditto for Door |
|  |  |  | 27.57 | Net External wall area with top tie beam in front and rear side |
|  | 5.00 1.20 |  | 6.00 | Wall area above top tie beam in rear side |
| 2/ | 4.40 3.20 |  | 28.16 | Wall area with top tie beam in right and left side |
| 2/1/2 | 4.85 1.20 |  | 5.82 | Wall area above top tie beam in right and left side |
|  |  |  | 39.98 | Net External wall plastering area in right and left side |
|  |  |  | 67.55 | Total external wall plastering area |
|  | 4.30 3.70 |  | 15.91 | 4.3. Install 0.40*0.40*1cm ceramic floor finish with mix a ratio of 1:3 on the ground floor slab. |
|  |  |  |  | 4.4. Skirting |
|  |  |  | 16.00 | Internal perimeter |
|  |  |  | 0.85 | Deduct door length |
|  |  |  | 15.15 | Total length of skirting |
|  |  |  |  | 4.5. Ceiling |
|  | 4.30 3.70 |  | 15.91 | Internal ceiling perimeter |
|  |  |  |  | 4.6. Apply two coats of emulsion paint to the internal wall plastered surfaces. |
| 2/ | 4.60 3.20 |  | 29.44 | Wall area with top tie beam in front and rear side |
|  | 0.66 1.80 |  | 1.88 | Deduct for window |
|  | 0.85 3.00 |  | 2.55 | Ditto for Door |
|  |  |  | 25.01 | Net wall area below top tie beam |
| 2/ | 4.00 3.20 |  | 25.06 | Wall area with top tie beam in right and left side |
|  |  |  | 50.07 | Total area of internal wall painting. |
|  |  |  |  | 4.7. Apply quartz paint to the external plastered wall surfaces. |
| 2/ | 5.00 3.20 |  | 32.00 | External wall area with top tie beam in front and rear side |
|  | 0.66 1.80 |  | 1.88 | Deduct for window |
|  | 0.85 3.00 |  | 2.55 | Ditto for Door |
|  |  |  | 27.57 | Net external wall area with top tie beam in front and rear side |
|  | 5.00 1.20 |  | 6.00 | Wall area above top tie beam in rear side |
| 2/ | 4.40 3.20 |  | 28.16 | Wall area with top tie beam in right and left side |
| 2/1/2 | 4.85 1.20 |  | 5.82 | Wall area above top tie beam in right and left side |
|  |  |  | 39.98 | Net quartz paint external wall area in right and left side |
|  |  |  | 67.55 | Total quartz paint to external wall |
|  |  |  |  | 5. Carpentry and joinery |
|  |  |  |  | Supply and fix in position eucalyptus truss member |
| 6/ | 4.85 |  | 29.10 | a) Ø12cm. chord |
| 6/ | 5.00 |  | 30.00 | b) Ditto but Ø12cm rafter. |
| 6/ | 2.40 |  | 14.40 | c) Ditto but Ø10cm vertical members.( use c/c 1.60) |
| 6/ | 3.44 |  | 20.64 | d) Ditto but Ø8cm diagonal members. |
|  |  |  |  | 6.Metal Work |
|  |  |  | 1 | 6.1. Supply and fix metal window with all accessories, hinges, locks and handle {0.66cm x 1.80cm}. |

Bill of Quantities

| No | Description | Unit | Quantity | Rate | Amount |
| --- | --- | --- | --- | --- | --- |
|  | A. Substructure |  |  |  |  |
|  | 1. Excavation and Earth Work |  |  |  |  |
| 1.1. | Clear the site to an average depth of 200mm to remove the top soil with 1m working area in all sides. | m2 | 44.80 |  |  |
| 1.2. | Pit excavation for isolated footings on ordinary soil to a depth not exceeding 1800mm from ground level (use working space 25 cm on both sides). | m3 | 13.10 |  |  |
| 1.3. | Trench excavation for 50cm thick stone foundation wall on ordinary soil to a depth not exceeding 1000mm use 25cm working space on each side. | m3 | 12.60 |  |  |
| 1.4. | Bulk excavation to the depth not exceeding 250mm. | m3 | 15.91 |  |  |
| 1.5. | Back fill with an already excavated material around footings pad, footing column and foundation wall by watering and ramming in 25cm layers. | m3 | 13.60 |  |  |
| 1.6. | Disposal of surplus excavated material away from the construction site {on axis C and site clearance. | m3 | 25.04 |  |  |
| 1.7. | 25cm thick basaltic or equivalent stone hard core crushed and blinded. | m2 | 15.91 |  |  |
|  | Total carried to summary |  |  |  |  |
|  | 2. Concrete work |  |  |  |  |
| 2.1. | 5cm C-5 lean concrete with minimum cement content of 150kg/m3 laid under footing pads. | m2 | 2.88 |  |  |
| 2.2. | Lean concrete under foundation wall. | m2 | 1 .93 |  |  |
| 2.3. | C-25 concrete well vibrated and compacted around reinforcement bars (form work and reinforcement measured separately). |  |  |  |  |
|  | a. Volume of concrete in footing pad | m3 | 0 .86 |  |  |
|  | b. Volume of concrete in footing column | m3 | 0 .24 |  |  |
|  | c. Volume of concrete in grade beams | m3 | 1.08 |  |  |
|  | d. In 10cm thick ground floor slab | m2 | 15.91 |  |  |
| 2.4. | Cut, fix/assemble Sawn zigba wooden form work for: |  |  |  |  |
|  | a. Footing pads | m2 | 4.08 |  |  |
|  | b. Footing columns | m2 | 4.80 |  |  |
|  | c. Grade beam | m2 | 10.81 |  |  |
| 2.5. | Provide and fix high yield strength reinforcement bars (price includes cutting , bending and fixing) |  |  |  |  |
|  | a. Ø8mm | kg | 125.33 |  |  |
|  | b. Ø10mm | kg | 23.91 |  |  |
|  | c. Ø12mm | kg | 53.28 |  |  |
|  | d. Ø14mm | kg | 53.73 |  |  |
|  | Total carried to summary |  |  |  |  |
|  | 3. Masonry work |  |  |  |  |
| 3.1. | 50cm thick trachytic or equivalent stone foundation wall bedded in cement mortar of 1:4 ratio above ground level | m3 | 8.84 |  |  |
|  | Total carried to summary |  |  |  |  |
|  | B. Superstructure |  |  |  |  |
|  | 1. Concrete work |  |  |  |  |
| 1.1. | C-25 concrete well vibrated and compacted around reinforcement bars (form work and reinforcement measured separately) |  |  |  |  |
|  | a. In elevation columns | m3 | 0 .48 |  |  |
|  | b. In top tie beams | m3 | 0 .72 |  |  |
| 1.2. | Cut, fix/assemble Sawn zigba wooden form work for: |  |  |  |  |
|  | a. Elevation columns | m2 | 9.60 |  |  |
|  | b. Top tie beams | m2 | 7.20 |  |  |
| 1.3. | Provide and fix high yield strength reinforcement bars (price includes cutting , bending and fixing) |  |  |  |  |
|  | a. Ø8mm | kg | 43.95 |  |  |
|  | b. Ø10mm | kg | 23.91 |  |  |
|  | c. Ø12mm | kg | 52.28 |  |  |
|  | Total carried to summary |  |  |  |  |
|  | 2. Masonry work |  |  |  |  |
| 2.1. | 20cm thick class B hollow concrete block masonry bedded in cement mortar of 1:4. | m2 | 57.97 |  |  |
|  | Total carried to summary |  |  |  |  |
|  | 3. Roof work |  |  |  |  |
| 3.1. | Supply and fix G-28 corrugated sheet of iron with all accessories (measurement taken in horizontal projection) | m2 | 25.00 |  |  |
|  | Total carried to summary |  |  |  |  |
|  | 4. Finishing work |  |  |  |  |
| 4.1 | Apply 3 coats of 25mm thick cement mortar plastering in ratio of 1:4 to internal walls. | m2 | 50.07 |  |  |
| 4.2 | Apply 3 coats of 25mm thick cement mortar plastering in ratio of 1:4 to external walls including column. | m2 | 67.55 |  |  |
| 4.3 | Install 0.40*0.40*1cm ceramic floor finish with mix a ratio of 1:3 on the ground floor slab. | m2 | 15.91 |  |  |
| 4.4 | Skirting | Ml | 15.15 |  |  |
| 4.5 | Ceiling | m2 | 15.91 |  |  |
| 4.6 | Apply two coats of emulsion paint to the internal wall plastered surfaces. | m2 | 50.07 |  |  |
| 4.7 | Apply quartz paint to the external plastered wall surfaces. | m2 | 67.55 |  |  |
|  | Total carried to summary |  |  |  |  |
|  | 5. Carpentry and joinery |  |  |  |  |
| 5.1. | Supply and fix in position eucalyptus | ml | 29.10 |  |  |
|  | a) Ø12cm. chord |  |  |  |  |
|  | b) Ditto but Ø12cm rafter. | ml | 30.00 |  |  |
|  | c) Ditto but Ø10cm vertical members.( use c/c 1.06) | ml | 14.40 |  |  |
|  | d) Ditto but Ø8cm diagonal members. | ml | 20.64 |  |  |
|  | 6. Metal Work |  |  |  |  |
| 6.1. | Supply and fix metal window with all accessories, hinges, locks and handle on axis c. |  |  |  |  |
|  | a. 0.66 cm x 1.80 cm | Pc | 1 |  |  |
|  | Total carried to summary |  |  |  |  |

## Cost Estimation

- Preparing material quantities and cost for concrete

Under this job the trainees is expected to calculate the quantities, cost of materials and labor cost.

Concrete work for footing pad and footing column assuming 1:2:3 proportion and grade C-25 concrete. Ignore water.

Material calculation for 1m3 C-25 concrete with 1:2:3 proportions

- Cement 				= 360 g/m2

- Sand 					=0.57m3

- Gravel 					=0.73 m3

Market price of materials

- Cement 				= 2000 Birr/quintal  (use your local price)

- Sand 					= 1000 Birr/ m3 (use your local price)

- Gravel 					= 1800 Birr/ m3  (use your local price)

Material Quantity

Labor Cost

Cost/Rate Estimation

- Preparing material quantities and cost for HCB

Hollow concrete block wall in the superstructure for 20cm HCB assuming 1:4 proportion

Material calculation for HCB

- HCB 					= 13 pcs/ m2

- Cement 				= 12.5 kg/m2

- Sand 					= 0.028 m3/m3

Market price of materials

- HCB 					= 40 Birr/ pc (use your local price)

- Cement 				= 2000 Birr/ Quntal (use your local price)

- Sand 					= 100 Birr /m3 (use your local price)

Material Quantity

Labor Cost

Cost/Rate Estimation

- Preparing material quantities and cost for plastic emulsion painting

Under this job the trainees is expected to calculate the quantities, cost of materials and labor cost. The candidate shall consider an overhead cost 15% of the direct cost and profit 10%.

Calculate the total cost of painting work only in the internal wall of the building assuming 2 coats of plastic emulsion paint with 1 painter and 2 helpers paining an area of 25m2 in one day. Use the following details for material calculation.

Material calculation for plastic emulsion painting

- First coat 					= 0.07lit/ m2

- Second coat 					= 0.06lit/m2

- Brush for painting 				= 1pc/500m2

- Sand paper 					= 0.01 m2/m2

Market price of materials

- Plastic emulsion paint 			= 800 Birr/ 4liters (use your local price)

- Paint brush 					= 50 Birr (use your local price)

- Sand paper 					= 15 Birr /m2 (use your local price)

Daily wage for labor

- For paint 					= 500 Birr (use your local price)

- For helper 					= 300 Birr (use your local price)

Material Quantity

Labor Cost

Cost/Rate Estimation

- Preparing Material Quantities and Cost for Roof Work

Assuming 1 carpenter and 1 helper with an output of 4 trusses/day. The cost of the truss shall be calculated by breaking down the truss in to its component members and calculating the individual prices

Material calculation for roof work

- Upper and lower truss member Ø12cm 				= 0.07lit/ m2

- Vertical and diagonal truss member  	Ø10cm, Ø8cm			= 0.06lit/m2

Market price of materials

- Upper and lower truss member Ø12cm 				= 45 Birr/m

- Vertical and diagonal truss member  	Ø10cm, Ø8cm			= 45 Birr/m

Daily wage for labor

- For carpenter 					= 500 Birr (use your local price)

- For helper 					= 300 Birr (use your local price)

Daily output of labor

- 1 carpenter and 1 helper together can produce 4 trusses per day.

- 1 carpenter and 1 helper together can mount and erect 4 trusses per day.

Material Quantity

Labor Cost

Cost/Rate Estimation

NB. Calculate each item of work from the takeoff sheet properly according to the above example and fill the rate of each work item to the bill of quantity.

Self-Check 2.1

Part I: Multiple choices

Instruction: I. Select the correct answer for the give choice. You are provided a minute for each question and each carry 3 Points.

1. Which type of estimate is based on prior costs of similar projects?

a) Approximate estimate

b) Detailed estimate

c) Abstract estimate

d) Working estimate

2. What is the purpose of quantity surveying?

a) To know the amount of money required

b) To know the quantities of materials required

c) To know the tools and equipment required for construction

d) All of the above

3. What is the final stage in the preparation of the completed bill of quantities?

a) Taking-off quantities

b) Abstracting or 'working-up'

c) Billing

d) Measurement of different work

4. What does the term "substructure" refer to?

a) Structural works below ground level

b) Structural works above ground level

c) Masonry work

d) Concrete work

5. How is topsoil excavation measured?

a) In cubic meters (m³)

b) In square meters (m²)

c) In linear meters (m)

d) In kilograms (kg)

Part II: True or False Questions

Instruction:  Say True or False.  You are provided 2 minute for each question and each has 5Points.

- Taking-off quantities involves reading or scaling dimensions from the drawings.

- The order of taking off dimensions follows the order of construction.

- Abstracting or 'working-up' quantities is carried out on A3 size paper.

- The demarcation between substructure and superstructure is taken as the damp proof course in structural walls.

- Masonry work is measured in square meters (m²).

Part III: Short Answer

Instruction:  Give short Answer for the following question and write your Answer on your answer sheet. You are provided 5 minute for each question and each has 5Points.

- What are the three processes involved in the preparation of the completed bill of quantities?

- What is the purpose of entering dimensions in the dimension column during taking-off quantities?

- How are described items transferred from the dimension sheet to the abstract during abstracting or 'working-up' quantities?

- What is the general approach to measurement in terms of substructure and superstructure?

- How is excavation for foundation measured in the bill of quantities?

You can ask you teacher for the copy of the correct answers.

Name:  _________________________               Date:  _______________

Unit Three: Resource acquisition process

This unit is developed to provide you the necessary information regarding the following content coverage and topics: - Managing organizational resource - Resource procurement process - Resource acquisition process - Financial resource and business principles This unit will also assist you to attain the learning outcomes stated in the cover page. Specifically, upon completion of this learning guide, you will be able to: - Manage organizational resource - Follow resource procurement process - Follow resource acquisition process - Apply financial resource and business principles

# Unit Three: Resource acquisition process

## Managing organizational resource

Managing organizational resources in construction involves effectively coordinating and utilizing various resources to ensure the successful completion of construction projects. These resources include human resources, financial resources, materials, equipment, and technology. Effective management of these resources is crucial for ensuring the timely completion of projects within budget and to the required quality standards.

Human Resources: Managing human resources in construction involves tasks such as recruiting, training, and retaining skilled labor. It also involves ensuring that the right personnel are assigned to the right tasks at the right time. This includes coordinating subcontractors, managing labor productivity, and addressing any labor-related issues that may arise during the project.

Financial Resources: Managing financial resources in construction involves budgeting, cost control, and financial reporting. It is essential to accurately estimate project costs, monitor expenses, and ensure that funds are allocated efficiently throughout the project lifecycle. Effective financial resource management also involves managing cash flow, securing project financing, and adhering to relevant financial regulations.

Materials and Equipment: Managing materials and equipment involves procurement, inventory management, and logistics. It is crucial to source high-quality materials at competitive prices and ensure their timely delivery to the construction site. Additionally, effective equipment management includes maintenance scheduling, utilization tracking, and ensuring that the right tools are available for each phase of the project.

Technology: Managing technological resources in construction involves leveraging software solutions for project management, scheduling, building information modeling (BIM), and other specialized construction technologies. It also includes implementing innovative construction methods and techniques to improve efficiency and productivity on-site.

Risk Management: Effective resource management in construction also requires a focus on risk assessment and mitigation. This involves identifying potential risks related to resource availability, market fluctuations, regulatory changes, and other factors that could impact the project’s success. Developing risk management strategies and contingency plans is essential for minimizing disruptions and maintaining project momentum.

Communication and Collaboration: Successful resource management in construction relies on clear communication and collaboration among all stakeholders involved in the project. This includes fostering effective communication channels between project teams, subcontractors, suppliers, clients, and regulatory authorities. Collaboration tools and techniques play a vital role in streamlining workflows and ensuring that resources are utilized optimally.

Sustainability: In modern construction management, there is an increasing emphasis on sustainable resource management. This involves optimizing resource usage to minimize waste, adopting eco-friendly materials and practices, and adhering to environmental regulations. Sustainable resource management not only aligns with corporate social responsibility but also contributes to long-term cost savings and positive brand reputation.

In conclusion, managing organizational resources in construction requires a multifaceted approach that encompasses human resources management, financial oversight, materials and equipment coordination, technological integration, risk mitigation, communication strategies, and sustainability initiatives. By effectively managing these resources, construction organizations can enhance project efficiency, mitigate risks, control costs, and ultimately achieve successful project outcomes.

## Resource procurement process

The resource procurement process in construction refers to the systematic approach taken by construction companies to acquire the necessary materials, equipment, and labor for their projects. This process is crucial for ensuring that the right resources are obtained at the right time and cost, ultimately contributing to the successful completion of construction projects. The procurement process involves various stages, including planning, sourcing, negotiation, purchasing, and contract management.

Procurement Process

The resource procurement process in construction typically involves the following steps:

- Planning: The first stage of the resource procurement process involves identifying the specific resource requirements for the construction project. This includes determining the quantity and quality of materials needed, as well as assessing the labor and equipment requirements. Planning also involves considering factors such as budget constraints, project timelines, and any regulatory or environmental considerations that may impact resource procurement.

- Sourcing: Once the resource requirements have been identified, the next step is to source potential suppliers or vendors who can provide the required materials, equipment, or services. This may involve conducting market research to identify suitable suppliers, obtaining quotes or proposals, and evaluating the capabilities and reliability of potential vendors.

- Negotiation: Negotiation is a critical stage in the procurement process, where construction companies work with suppliers to establish favorable terms and conditions for acquiring the necessary resources. This may involve negotiating prices, delivery schedules, payment terms, and other contractual arrangements to ensure that both parties are satisfied with the agreement.

- Purchasing: After reaching agreements with suppliers, construction companies proceed with purchasing the required resources. This involves issuing purchase orders or contracts to formalize the procurement arrangements and ensure that the resources will be delivered according to the agreed-upon terms.

- Delivery and Installation: Receive and inspect the delivered resources to ensure they meet the required quality standards. Install the resources as per the project plan.

- Contract Management: Once resources have been procured, effective contract management is essential to monitor supplier performance, track deliveries, manage any changes or disputes that may arise, and ensure compliance with contractual obligations throughout the duration of the construction project.

The resource procurement process in construction is a complex and multifaceted undertaking that requires careful planning, diligent sourcing efforts, skillful negotiation, efficient purchasing practices, and effective contract management to ensure that projects are completed successfully and within budget.

## Resource acquisition process

The resource acquisition process in construction refers to the systematic approach through which construction companies obtain the necessary materials, equipment, labor, and other resources required for successful project execution. This process is critical for ensuring that construction projects are completed on time, within budget, and to the required quality standards. Resource acquisition in construction involves various stages, including planning, procurement, logistics, and management of resources. The following is a comprehensive overview of the resource acquisition process in construction:

- Project Planning and Budgeting: The first step in the resource acquisition process is project planning and budgeting. This involves defining the scope of the project, identifying the required resources, and determining the budget for the project. The project plan and budget serve as a blueprint for the entire project, including the resource acquisition process.

- Identifying Resource Requirements: Once the project plan and budget are established, the next step is to identify the specific resources required for the project. This includes labor, materials, equipment, and services. The project manager will work with the design team and other stakeholders to determine the specific requirements for each resource.

- Resource Estimation: After identifying the required resources, the next step is to estimate the quantity and cost of each resource needed for the project. This involves analyzing historical data, industry benchmarks, and market trends to determine the costs associated with each resource.

- Resource Selection: Once the resource requirements and estimates are established, the next step is to select the resources that will be used for the project. This involves evaluating available resources, such as in-house resources, external vendors, and subcontractors, based on factors such as cost, quality, delivery time, and availability.

- Contract Negotiation and Management: Once the resources have been selected, the next step is to negotiate contracts with the suppliers and vendors. This involves establishing the terms and conditions of the contract, including the price, delivery schedule, and payment terms. The project manager will also need to manage the contracts throughout the project to ensure that the agreed-upon terms and conditions are being met.

- Procurement and Contract Administration: After the contracts have been negotiated, the next step is to procure the resources and manage the contracts. This involves ensuring that the resources are delivered on time and in accordance with the agreed-upon specifications. The project manager will also need to monitor the progress of the project and make any necessary adjustments to the resource acquisition plan.

- Resource Allocation and Scheduling: Once the resources have been procured, the next step is to allocate and schedule them to the project tasks. This involves assigning the right resources to the right tasks at the right time to ensure that the project is completed on time and within budget.

- Monitoring and Control: Finally, the project manager will need to monitor and control the resource acquisition process throughout the project to ensure that the project is progressing as planned. This involves tracking the usage of resources, managing the budget, and making any necessary adjustments to the resource acquisition plan.

In conclusion, the resource acquisition process in construction involves several key steps, including project planning and budgeting, identifying resource requirements, resource estimation, resource selection, contract negotiation and management, procurement and contract administration, resource allocation and scheduling, and monitoring and control. By following this process, project managers can ensure that they acquire the necessary resources to complete their projects successfully and within budget.

## Financial resource and business principles

The construction industry is a vital sector that encompasses a wide range of activities, including the creation, renovation, and maintenance of structures and infrastructure. Financial resources and business principles play a crucial role in the success and sustainability of construction projects. Financial resource management in construction involves the effective allocation and utilization of funds to ensure that projects are completed within budget and on schedule. This requires careful planning, monitoring, and control of financial resources throughout the project lifecycle.

One of the key financial resources in construction is capital investment. This includes the initial funding required for land acquisition, design, permits, materials, labor, equipment, and other project-related expenses. Effective management of capital investment involves assessing the financial feasibility of projects, securing financing from lenders or investors, and optimizing the use of available funds to maximize returns.

Another important aspect of financial resource management in construction is cost control. Construction projects are often susceptible to cost overruns due to factors such as changes in design, scope creep, material price fluctuations, and unforeseen site conditions. Implementing robust cost control measures involves accurate budgeting, regular cost monitoring, identifying cost-saving opportunities, and addressing variances promptly to prevent budget escalation.

Furthermore, cash flow management is critical in construction. The industry typically operates on a project-based payment system where contractors and subcontractors are paid based on completed work milestones. Effective cash flow management involves forecasting cash inflows and outflows, ensuring sufficient liquidity to meet financial obligations, negotiating favorable payment terms with suppliers and subcontractors, and minimizing the impact of payment delays on project progress.

In addition to financial resource management, sound business principles are essential for success in the construction industry. Business principles encompass a wide range of concepts that guide decision-making and operations within construction firms. These principles include but are not limited to:

- Strategic Planning: Construction companies need to develop clear strategic plans that align with their long-term goals and market dynamics. This involves analyzing market trends, identifying growth opportunities, defining competitive positioning, and setting actionable objectives for sustainable growth.

- Risk Management: Construction projects are inherently risky due to factors such as safety hazards, regulatory compliance, contractual disputes, and economic uncertainties. Implementing robust risk management practices involves identifying potential risks, assessing their impact and likelihood, developing mitigation strategies, and transferring or accepting risks based on informed decisions.

- Ethical Practices: Upholding ethical standards is crucial for maintaining trust with stakeholders and fostering a positive reputation in the construction industry. This includes adhering to legal regulations, promoting fair labor practices, ensuring workplace safety, and conducting business with integrity and transparency.

- Quality Management: Delivering high-quality construction projects is essential for customer satisfaction and long-term success. Implementing quality management principles involves establishing quality standards, conducting regular inspections and testing, addressing non-conformities promptly, and continuously improving processes to enhance overall quality performance.

- Sustainable Practices: With increasing emphasis on environmental conservation and sustainable development, integrating sustainable practices into construction operations is becoming imperative. This includes adopting green building technologies, minimizing waste generation, optimizing energy efficiency, and considering the environmental impact of construction activities.

In conclusion, financial resource management and sound business principles are integral components of successful construction operations. By effectively managing financial resources such as capital investment, cost control, and cash flow while adhering to sound business principles like strategic planning, risk management, ethical practices, quality management, and sustainable practices; construction firms can enhance their competitiveness, mitigate risks, and deliver high-quality projects efficiently while contributing positively to economic development.

Self-Check 3.1

Part I: Multiple choices

Instruction: I. Select the correct answer for the give choice. You are provided a minute for each question and each carry 3 Points.

1. Which of the following is NOT considered an organizational resource in construction?

a) Human resources

b) Financial resources

c) Technology

d) Marketing strategies

2. What is one of the key stages in the resource procurement process?

a) Inspection and installation

b) Risk assessment

c) Sustainability initiatives

d) Communication and collaboration

3. What does effective resource management in construction involve?

a) Ignoring risk assessment and mitigation

b) Poor communication and collaboration

c) Optimizing resource usage

d) Neglecting financial oversight

4. What is the final step in the resource acquisition process in construction?

a) Project planning and budgeting

b) Resource estimation

c) Contract negotiation and management

d) Monitoring and control

5. What is an essential aspect of financial resource management in construction?

a) Cost control

b) Resource allocation and scheduling

c) Risk assessment

d) Sustainability initiatives

Part II: True or False Questions

Instruction:  Say True or False.  You are provided 2 minute for each question and each has 5Points.

1. Effective resource management in construction involves coordinating subcontractors.

2. Technology plays a vital role in streamlining workflows in construction.

3. Sustainable resource management in construction contributes to long-term cost savings.

4. The resource procurement process in construction does not involve contract management.

5. Cash flow management is not important in the construction industry.

Part III: Short Answer

Instruction:  Give short Answer for the following question and write your Answer on your answer sheet. You are provided 5 minute for each question and each has 5Points.

1. What are some examples of organizational resources in construction?

2. Briefly explain the importance of risk assessment and mitigation in resource management.

3. How can effective communication and collaboration contribute to successful resource management in construction?

4. What is the role of sustainability in resource management in construction?

5. Describe the key steps involved in the resource procurement process in construction.

You can ask you teacher for the copy of the correct answers.

Name:  _________________________               Date:  _______________

Unit Four: Resource Administrative Control

This unit is developed to provide you the necessary information regarding the following content coverage and topics: - Resource administration system - Subcontractors and materials supplier agreement - Resource procurement document - Staff allocation - Provision and withdrawal of resources This unit will also assist you to attain the learning outcomes stated in the cover page. Specifically, upon completion of this learning guide, you will be able to: - Understand resource administration system - Identify subcontractors and materials supplier agreement - Prepare resource procurement document - Allocate staff - Apply provision and withdrawal of resources

# Unit Four: Resource Administrative Control

## Resource administration system

Construction resource management is the process of planning, allocating, and managing resources, including personnel, equipment, materials, and finances, to complete construction projects successfully.

One must use the allocated project resources efficiently and effectively in such a situation. Therefore, the workforce’s talent and motivation will finally be the guiding factor for the successful delivery of any project. Thus, resource management plays a significant role in the construction industry.

4.1.1. Importance of resource management in the construction industry

It helps to precisely accomplish every task and meet the project objectives within time. It allows managers to deliver projects successfully by fulfilling project resource demands on time. Effective resource management also maximizes productive utilization.

With this approach, construction firms can also avoid mistakes such as hiring too many workers, project delays due to late delivery of supplies, etc. Moreover, construction resource management helps in effective communication by ensuring that all the stakeholders are on the same page and can work together to achieve the project goals.

4.1.2. Necessary resources in the construction industry

The construction business has specific requirements and challenges similar to any other industry. Here is a rundown of all the essential types of resources in project management of the construction industry.

- Human resources: They are the most critical part of the construction management resource pool. It is the people behind the project that make it a reality.

- Estimator: The estimator is responsible for estimating the costs, materials, and labor needed to complete a project.

- Architect: The architect’s job is to envision the client’s needs and develop a creative solution in a blueprint.

- Supervisor: The supervisor is an intermediary between the field workers and the management office. They ensure effective communication between the two parties.

- Quantity Surveyor: The quantity surveyor provides the client with advice on building costs and contractual matters throughout the building process and acts as a consultant to the architect.

- Engineer: Engineers are vital on a job site and may specialize in building, electrical, mechanical, highway, etc. For example, civil engineers use computer software technology to create project plans. Electrical engineers monitor the power requirements in the project and ensure all hazards are negated.

- Construction Worker: Construction workers are the driving force of every project. Once the project is planned, the workers get their hands dirty to make it a reality.

- Equipment: Construction projects require heavy equipment. The equipment selection depends on the project’s time and cost. Some heavy equipment used in construction projects are bulldozers, excavators, cranes, trenchers, etc.

- Materials: Materials such as wood, cement, metals, bricks, concrete, clay, etc., are the most common building material used in construction. Selection criteria such as cost-effectiveness and quality play a significant role.

- Facilities: Facilities not only improve workers’ welfare but also enhance efficiency. As per the standards, all construction sites must include the following facilities:

- Living accommodations for the workers.

- Sanitary and toilet facilities.

- Drinking water facilities.

- Changing rooms and lockers.

- Cafeteria.

4.1.3. Benefits of an effective construction resource management

Construction resource management provides an array of benefits to construction project managers. Here is a list of some of them:

- Gain visibility of all construction management resources

Often, you won’t have the required resources at the primary location. Hence, you may have to look at cost-effective resources from different areas within the business. But without enterprise-wide visibility finding the right resources with the desired skills and cost becomes challenging.

- Reduce construction project costs

Tracking project financials helps to avoid budget overruns. Project managers can control costs by periodically tracking and comparing forecast vs. actual spending. If there is a variance, corrective measures can mitigate project risks ahead of time.

- Improve productivity of construction resources

Construction resource management ensures that appropriate resources are deployed to suitable projects at the right time and cost. This approach maximizes workforce efficiency and improves productivity. An effective equipment scheduling tool can help managers forecast the effective utilization of equipment and other resources on time.

- Facilitate construction team collaboration

The project resource management processes enhance collaboration, supporting healthy relations between the whole team. Effective communication between various construction project team members and ensures everyone is on the same page. Moreover, problem-solving becomes easy with effective team collaboration. One gets a different perspective on the same issue making it easy to deduce a solution. It also fosters trust and enhances morale in the organization, building a positive environment and strengthening the team.

4.1.4. Challenges of construction resource management

Numerous roadblocks in construction resource management can cause missed deadlines and cost overruns. Here are some challenges and ways how to manage construction projects effectively.

- Shortage of skilled labor

- Lack of resource planning and scheduling tools

- Changes in project scope due to various external and internal factors

- Poor resource utilization

- Poor communication

Shortage of skilled labor

Skilled labor plays a vital role in the success of every construction project. But, with the increasing demand for construction services, there is a shortage of skilled labor. Numerous factors influence the shortage of skilled labor. Some of which are:

- Workers who lost their construction jobs moved to other industries.

- Professional construction resources are retiring.

- Construction businesses haven’t innovated their hiring process with technology.

Solution: To address the shortage of skilled labor, construction firms need to invest in all employees’ training, such as;

- Refresher training courses for all resources

- Mentorship programs, where seniors will guide new workers

Here are some of the additional ways that will help negate the shortage of skilled labor:

- Secure skilled workers beforehand

- Empower resources to select projects of their interest

- Hire part-time or contractual employees

- Offer loyalty points to your current workers

Lack of resource planning and scheduling tools

To gain a competitive edge in this technologically advanced era, managers must have the right resourcing tools. Silos of spreadsheets or home-grown tools are limited to essential admin work. They fail to address construction resource management challenges efficiently. They are also time-consuming and error-prone, resulting in scheduling conflicts such as double bookings.

Solution: A resource planning tool can map out your resources’ skill sets and schedule tasks accordingly. Using the software, you can assign resources to tasks best suited to their unique skills. Then, you can forecast, schedule, and allocate tasks as required.

Changes in project scope due to various external and internal factors

Scope creep can adversely impact resource productivity and increase workload. In addition, it leads to burnout and turnovers as resources get overwhelmed with last-minute changes. Also, managers face a massive resource crunch and struggle to find suitable staff at the last moment.

Solution: First and foremost, you must ensure the scope is clear to everyone working on the project. The client should understand what is in the scope and what isn’t. Excellent and transparent communication with the client can negate last-minute hiccups. Here is how you can save the project from scope creep:

- Determine and agree upon a change management process upfront.

- Prioritize the tasks and accommodate new requests if necessary.

- Communicate with clients and stakeholders about any scope creep.

- Analyze the impacts of changes and present solutions to client/stakeholder to tackle them.

- Finally, if scope change is the only way possible, find ways to incorporate the changes.

Poor resource utilization

Resource utilization is one of the key points in construction project management. But finding the resource utilization metrics right is tricky. Managers sometimes oversee utilization when resources are not working on any billable task. Overlooking utilization leads to disengagement and decreased morale of employees.

Solution: Both overutilization and underutilization can have adverse effects on the project. Here are some simple steps to improve resource utilization:

- Define appropriate variables to measure billable utilization.

- Improve your resource deployment upfront by comparing planned versus actual reports. It will also help you to prepare for future projects.

Proper resource planning and resource capacity planning ensures that no project vacancies go unfilled or excess capacity goes wasted. As a result, you can maximize your resource utilization and ensure timely delivery. You can maximize your resource utilization and also ensure timely delivery, resource utilization and ensure timely delivery.

Poor communication

Poor communication is one of the factors that can hamper project success. The project manager has to foster team collaboration. Otherwise, communication challenges will grasp the construction project management.

Solution: A communication plan will make team collaboration much more effortless. There must be constant contact between the team members, managers, and stakeholders. Modern resource management solutions facilitate real-time collaboration using discussion boards or personalized chat rooms. Project members can effectively communicate, update, and share documents and more through personalized chat rooms. Project members can effectively communicate, update, and share documents and more. Thus, implementing a single collaboration platform for the team and stakeholders will help build communication. It will help the team members to:

- Understand the goals of the project

- Access and use approved project documents

- Update their tasks when needed

- Track the overall progress of the project

- Log risks and issues

4.1.5. Resource requirements for construction industry

There are four basic steps to arrive at resource requirements for the construction industry:

- Create a project plan and identify milestones

- Identify resources required for project success

- Evaluate resource availability and reusability for other projects

- Have an authorization process for proper resource planning

## Subcontractors and materials supplier agreement

A subcontractor and materials supplier agreement in construction is a legal document that outlines the terms and conditions under which subcontractors and materials suppliers will provide their services or goods to a general contractor or project owner. This agreement is crucial in ensuring that all parties involved in a construction project understand their roles, responsibilities, and obligations. It also helps to mitigate potential disputes and ensures that the project progresses smoothly and efficiently.

The agreement between subcontractors and materials suppliers and the general contractor or project owner is crucial components of the construction process, as they establish the terms and conditions under which subcontractors and suppliers will provide their services and materials. These agreements help to ensure that all parties involved understand their roles, responsibilities, and obligations, thereby minimizing the potential for disputes and delays.

Subcontractor Agreements: Subcontractor agreements in construction typically outline the scope of work to be performed by the subcontractor, the project schedule, payment terms, insurance requirements, indemnification clauses, dispute resolution mechanisms, and other important provisions. These agreements also often include provisions related to safety protocols, quality standards, and compliance with applicable laws and regulations.

Subcontractors are hired by the general contractor to perform specific tasks within the construction project. They may include trades such as plumbing, electrical work, carpentry, roofing, or other specialized services. Materials suppliers, on the other hand, provide the necessary construction materials such as lumber, concrete, steel, plumbing fixtures, electrical components, and other building supplies.

Materials Supplier Agreements: Materials supplier agreements are equally important in construction projects. These agreements specify the types and quantities of materials to be supplied, delivery schedules, pricing and payment terms, warranties, quality standards, indemnification clauses, dispute resolution mechanisms, and other relevant terms. Additionally, they may address issues such as product substitution, inspection rights, and compliance with building codes and industry standards. By formalizing these arrangements in written agreements, construction parties can mitigate the risks associated with material shortages, defects, or non-compliance.

Key Considerations: When drafting subcontractor and materials supplier agreements in construction, it is essential to ensure that they are clear, comprehensive, and tailored to the specific requirements of the project. Legal review by experienced construction attorneys is advisable to address any jurisdiction-specific regulations or potential pitfalls. Furthermore, effective communication between all parties involved is critical for successful contract administration throughout the project lifecycle.

In summary, a subcontractor and materials supplier agreement in construction serves as a legally binding contract that governs the relationship between subcontractors, materials suppliers, and the general contractor or project owner. It outlines the terms of engagement, scope of work, payment terms, quality standards, responsibilities, dispute resolution mechanisms, and other essential provisions to ensure a successful construction project. These agreements contribute to the overall success of construction projects by promoting clarity, accountability, and risk management.

## Resource procurement document

A resource procurement document in construction refers to a formal record that outlines the process of acquiring materials, equipment, and services necessary for a construction project. This document is crucial for ensuring that the resources required for the project are obtained in a timely and cost-effective manner. It typically includes details such as the types and quantities of resources needed, specifications, procurement methods, supplier information, delivery schedules, quality standards, and budget considerations. The resource procurement document serves as a guide for project managers and procurement teams to effectively plan, source, and manage the resources essential for successful project completion.

The resource procurement document plays a significant role in construction projects by facilitating efficient resource management and cost control. By clearly defining the requirements and procedures for obtaining resources, it helps to minimize delays, avoid shortages, and ensure compliance with project specifications and regulations. Additionally, it enables effective communication between stakeholders involved in the procurement process, including project managers, suppliers, contractors, and regulatory authorities.

Types of Resources to be procured

In construction, the following are some of the key resources that need to be procured:

Materials

- Building materials, such as steel, concrete, wood, and glass

- Finishing materials, such as paints, varnishes, and flooring

- Specialized materials, such as insulation, roofing, and siding

Equipment

- Heavy machinery, such as cranes, excavators, and bulldozers

- Hand tools, such as hammers, drills, and saws

- Specialized equipment, such as concrete mixers, pumps, and generators

Services

- Labor services, including skilled and unskilled labor

- Professional services, such as architecture, engineering, and project management

- Specialized services, such as electrical, plumbing, and HVAC (heating, ventilation, and air conditioning)

Importance of Resource Procurement in Construction

In construction, the following are Importance of Resource Procurement in Construction:

Cost Control

Resource procurement helps control costs by ensuring that the project stays within budget. By carefully selecting suppliers and negotiating the best prices, project managers can minimize costs without compromising on quality.

Quality Control

Resource procurement helps ensure that the project meets the required quality standards. By selecting suppliers based on their reputation and quality standards, project managers can minimize the risk of defects and rework.

Schedule Control

Resource procurement helps control the project schedule by ensuring that the required resources are available when needed. This helps prevent delays and ensures that the project is completed on time.

Risk Management

Resource procurement helps manage risks by minimizing the risk of supply chain disruptions and ensuring that the project has the necessary resources to meet unexpected challenges.

## Staff allocation

Staff allocation in construction resource acquiring refers to the process of assigning and managing human resources within a construction project to ensure that the right personnel are allocated to the right tasks at the right time. This process involves identifying the required skills, knowledge, and experience for each task, as well as determining the appropriate number of workers needed to complete the project efficiently and effectively. Staff allocation is crucial in construction projects as it directly impacts productivity, cost management, and overall project success.

The process of staff allocation in construction resources involves several key steps:

- Assessment of Project Requirements: Before allocating staff to construction projects, it is crucial to assess the specific requirements of each project. This includes evaluating the scope of work, timeline, budget, and the skills needed for successful project completion.

- Skill Matching: Once the project requirements are identified, the next step is to match the required skills with the available staff members. This involves reviewing the qualifications, experience, and expertise of each team member to determine their suitability for the project.

- Availability and Workload: Staff allocation also requires considering the availability and current workload of each team member. It is important to ensure that individuals are not overburdened with multiple projects or tasks, as this can lead to decreased productivity and potential burnout.

- Communication and Coordination: Effective communication is essential in staff allocation. Project managers need to clearly communicate the allocated tasks and responsibilities to each team member. Additionally, coordination among team members is vital to ensure seamless workflow and collaboration.

- Monitoring and Adjustments: Once staff allocation is done, it is important to monitor the progress of each team member and make adjustments as necessary. This may involve reassigning tasks based on changing project needs or addressing any issues that may arise during the construction process.

The benefits of effective staff allocation in construction resources include:

- Optimized Productivity: By assigning the right people with the right skills to specific tasks, construction projects can be completed more efficiently, leading to improved overall productivity.

- Quality Assurance: Proper staff allocation ensures that individuals with relevant expertise are handling specific aspects of the project, thereby contributing to higher quality workmanship.

- Timely Project Completion: When resources are allocated effectively, it helps in meeting project deadlines and milestones within the stipulated time frame.

- Cost Efficiency: Efficient staff allocation can contribute to cost savings by minimizing errors and rework due to having skilled personnel in place from the outset.

In conclusion, staff allocation in construction resources plays a pivotal role in ensuring successful project execution. By carefully assessing project requirements, matching skills with tasks, considering availability and workload, maintaining open communication, and making necessary adjustments when needed, construction companies can optimize their resources and achieve better project outcomes.

## Provision and withdrawal of resources

The provision and withdrawal of resources in construction refers to the allocation and removal of materials, equipment, labor, and other resources necessary for the completion of construction projects. This process involves careful planning, management, and coordination to ensure that the right resources are available at the right time and place. It also involves the efficient use of resources to minimize waste and maximize productivity. The provision and withdrawal of resources are critical aspects of construction project management, as they directly impact the cost, schedule, and quality of the final product.

Provision of Resources:

The provision of resources in construction involves the procurement and allocation of materials, equipment and labor needed for the project. This process begins with the identification of required resources based on project specifications and design plans. Once identified, resources are procured through various means such as purchasing, leasing, or subcontracting. Effective provision also entails ensuring that the quality and quantity of resources meet project requirements. Additionally, proper storage and handling of resources are essential to prevent damage or loss.

The provision of resources in construction involves the strategic planning and acquisition of necessary materials, equipment, labor, and finances to ensure that the project progresses smoothly and meets its objectives. This process includes several key components:

- Material Procurement: The procurement of construction materials involves identifying the required materials based on project specifications, obtaining quotes from suppliers, negotiating contracts, and ensuring timely delivery to the construction site. It also involves quality control to ensure that the materials meet the required standards.

- Equipment Acquisition: Construction projects often require various types of equipment such as excavators, cranes, concrete mixers, and other machinery. The provision of these resources involves renting or purchasing the necessary equipment, ensuring their proper functioning, maintenance, and timely availability at the construction site.

- Labor Management: Securing skilled labor is crucial for the successful execution of construction projects. This involves hiring qualified personnel, managing their schedules, providing necessary training when required, and ensuring compliance with safety regulations.

- Financial Planning: Adequate financial resources are essential for the smooth progress of construction projects. This includes budgeting for material procurement, equipment rental or purchase, labor costs, overhead expenses, and contingencies.

Withdrawal of Resources:

The withdrawal of resources in construction refers to the removal or relocation of materials, equipment, and labor from the construction site or project. Efficient withdrawal involves systematic dismantling or relocation of resources to minimize disruption to ongoing work and ensure safety. Proper documentation and inventory management are crucial during resource withdrawal to track usage, returns, and any remaining inventory.

The withdrawal of resources in construction refers to the careful management and removal of materials, equipment, labor, and finances as the project progresses towards completion or when certain phases are completed. This process involves several important considerations:

- Inventory Management: As construction projects evolve, it is essential to manage inventory levels effectively. This includes tracking the usage of materials and equipment, identifying surplus or unused items, and optimizing inventory levels to minimize waste and storage costs.

- Equipment Decommissioning: Once specific phases of a project are completed or certain equipment is no longer needed, it is crucial to decommission and remove such equipment from the site efficiently. Proper maintenance and storage of unused equipment may also be necessary if it will be used in subsequent project phases.

- Labor Optimization: As different stages of a construction project are completed, there may be fluctuations in labor requirements. It is important to manage labor effectively by reallocating resources to other areas within the project or releasing surplus labor while adhering to contractual obligations.

- Financial Control: Throughout the project lifecycle, financial resources need to be managed effectively. This includes monitoring expenses, reallocating funds as needed, settling accounts with suppliers and contractors, and ensuring that all financial obligations are met upon project completion.

Challenges:

Several challenges are associated with the provision and withdrawal of resources in construction. These include fluctuating material costs, supply chain disruptions, labor shortages, regulatory compliance, and environmental concerns. Addressing these challenges requires proactive risk management strategies, effective communication among stakeholders, and adoption of innovative technologies for resource tracking and optimization, as well as adherence to industry best practices.

In conclusion, the provision and withdrawal of resources in construction are fundamental aspects of project management that significantly influence project outcomes. Effective resource management involves careful planning, procurement, utilization monitoring, withdrawal procedures, and addressing associated challenges.

Self-Check 4.1

Part I: Multiple choices

Instruction: I. Select the correct answer for the give choice. You are provided a minute for each question and each carry 3 Points. :

1. Which of the following is NOT considered a necessary resource in the construction industry?

a) Architect

b) Engineer

c) Estimator

d) Supervisor

2. What is one of the benefits of effective construction resource management?

a) Increased project costs

b) Decreased productivity of resources

c) Improved collaboration within the construction team

d) Reduced visibility of construction management resources

3. What is one of the challenges in construction resource management mentioned in the document?

a) Abundance of skilled labor

b) Extensive use of resource planning and scheduling tools

c) Poor communication among team members

d) Excessive resource utilization

4. What is the role of a quantity surveyor in the construction industry?

a) Envisioning the client's needs and developing creative solutions

b) Providing advice on building costs and contractual matters

c) Creating project plans using computer software technology

d) Monitoring the power requirements in the project

5. Which of the following is NOT included in the facilities that must be provided at a construction site?

a) Living accommodations for workers

b) Sanitary and toilet facilities

c) Drinking water facilities

d) Gymnasium facilities

Part II: True or False Questions

Instruction:  Say True or False.  You are provided 2 minute for each question and each has 5Points.

1. Resource management plays a significant role in the construction industry.

2. The estimator is responsible for estimating the costs, materials, and labor needed to complete a project.

3. Effective construction resource management can help reduce project costs.

4. Lack of skilled labor is not a challenge in construction resource management.

5. Poor communication can hamper project success in the construction industry.

Part III: Short Answer

Instruction:  Give short Answer for the following question and write your Answer on your answer sheet. You are provided 5 minute for each question and each has 5Points.

1. What are some examples of heavy equipment used in construction projects?

2. How can construction firms address the shortage of skilled labor?

3. Why is proper resource utilization important in construction project management?

4. What are some ways to improve communication in construction project management?

5. What are the four basic steps to arrive at resource requirements for the construction industry?

You can ask you teacher for the copy of the correct answers.

Name:  _________________________               Date:  ___________

# Appendex-1: All necessary drawing for takeoff calculation