STRUCTURAL CONSTRUCTION WORKS

LEVEL – III

Based on October 2023 Version - II Curriculum

Module Title: Prepare Bill of Quantities

Module code: EIS SCW3 M02 1023

Nominal duration: 80 Hours

October 2023

Addis Ababa, Ethiopia

Table of Contents

Acknowledgment	4

Acronyms	5

Introduction to the module	6

Unit One:  Unit One: Basic concepts of bill of quantity	9

1.1.	Introduction to bill of quantity	10

1.2.	Sorting out materials requirement	11

1.3.	Taking measurement	12

1.4.	Preparing time schedule of specific work	13

Self-Check 1.1	15

Operation Sheet 1.1	17

LAP Test 1.1    Practical Demonstration	20

Unit Two: Measure quantities of work	21

2.1.	Take off sheet	22

2.2.	Bill of quantities	35

2.3.	Bar schedule	45

Self-Check 2.1	52

Operation Sheet 2.1	54

LAP Test 2.1   Practical Demonstration	56

Unit Tree:  Check and correct quantities	57

3.1.	Checking erroneous data and Size of parameters	58

3.2.	Making corrections and adjustment	61

3.3.	Compiling bill of quantity	62

Self-Check 3.1	65

Operation Sheet 3.1	67

LAP Test 3.1   Practical Demonstration	70

Reference	71

# Acknowledgment

Ministry of Labor and Skills wish to extend thanks and appreciation to the many representatives of TVT instructors, respective of MoLS experts and regional labor and skill bureaus who donated their time and professional experience to the development of this Teaching, Training and Learning Materials (TTLM) for structural construction work level III Trainees.

# Acronyms

EIS	Economic infrastructure

SCW	Structural Construction Works

LAP	 Learning Activities Performance

BOQ   	Bill of Quantities

CESMM 	Civil Engineering Standard Method of Measurement

RFID 	Radio Frequency Identification

MEP  	Mechanical, Electrical, Plumbing

GPS  	Global Positioning System

NGL	Natural Ground Level

M²	 Square Meter

M³	Cubic Meter

HTML	Hypertext Markup Language

# Introduction to the module

This module is designed to provide trainees with a comprehensive understanding of the fundamental concepts and practical techniques involved in creating accurate and detailed bills of quantities (BOQs) for construction projects.

A bill of quantity is a document that itemizes the materials, labor, equipment, and other costs required to complete a construction project. It serves as a vital tool for estimating project costs, tendering processes, and facilitating effective project management.

Throughout this module, you will learn the essential components of a bill of quantity, including the measurement and quantification of various construction elements, such as excavation, concrete works, structural steel, finishes, and mechanical and electrical systems.

The module will cover the following key topics: Introduction to Bills of Quantity, Measurement Techniques, Quantity Takeoff, Pricing and Cost Estimation, Developing the skills to present BOQs in a clear, organized, and professional manner.

By the end of this module, trainees will have the necessary knowledge and practical skills to prepare accurate bills of quantities for construction projects.

This module covers the units:

- Basic concepts of bill of quantity

- Measure quantities of work

- Check and correct quantities

Learning Objective of the Module

- Identify Basic concepts of bill of quantity

- Measure quantities of work

- Check and correct quantities

Module Instruction

For effective use this modules trainees are expected to follow the following module instruction:

1.  Read the information written in each unit

2.  Accomplish the Self-checks at the end of each unit

3.  Perform Operation Sheets which were provided at the end of units

4.  Do the “LAP test” giver at the end of each unit and

5.  Read the identified reference book

# Unit One: Unit One: Basic concepts of bill of quantity

This unit is developed to provide you the necessary information regarding the following content coverage and topics: - Introduction to bill of quantity - Sorting out materials requirement. - Taking measurements - Preparing time schedule of specific work This unit will also assist you to attain the learning outcomes stated in the cover page. Specifically, upon completion of this learning guide, you will be able to: - Take measurements - Prepare time schedule of specific work - Sort out materials requirement.

## Introduction to bill of quantity

The Bill of Quantities (BOQ) is a document commonly used in the construction industry to provide a detailed breakdown of the quantities and costs of materials, labor, and equipment required to complete a construction project. It serves as a comprehensive list of all the items needed for the project, including their specifications, quantities, and unit prices.

The main purpose of a Bill of Quantities is to enable accurate cost estimation and tendering for construction projects. It provides a standardized format that allows contractors to understand the scope of work and accurately calculate the costs associated with each item. By providing detailed information on quantities and prices, it helps in comparing bids from different contractors and selecting the most suitable one.

A typical Bill of Quantities consists of several sections, including:

- Preliminaries: This section includes general information about the project, such as project description, location, duration, and any special conditions or requirements.

- Measurement Rules: This section outlines the rules and methods used for measuring quantities, such as the Code of Measurement Practice (e.g., CESMM4) or any other industry-specific standards.

- Schedule of Quantities: This is the core part of the Bill of Quantities and includes a detailed list of all items required for the project. Each item is described with its specifications, quantities, unit prices, and extended totals.

- Provisional Sums: In some cases, certain items may have uncertain quantities or costs at the time of tendering. Provisional sums are included to account for these uncertainties and allow for adjustments during the contract period.

- Day work Schedule: This section includes rates for additional work that may be required on a time basis rather than a fixed price. It covers situations where unforeseen work arises or where specific tasks cannot be accurately quantified in advance.

- Summary: The summary section provides a summary of all the items listed in the Schedule of Quantities, including subtotals for each section and a grand total.

The Bill of Quantities is typically prepared by a quantity surveyor or an estimator who carefully analyzes the project’s drawings, specifications, and other relevant documents. The accuracy and completeness of the BOQ are crucial for successful cost estimation, tendering, and project execution.

## Sorting out materials requirement

Sorting out materials in construction work refers to the process of organizing and categorizing various building components and materials based on their characteristics, specifications, and intended uses. This crucial step in the construction process helps ensure that the right materials are delivered to the right place at the right time, reducing errors, waste, and delays.

The following are the key aspects of sorting out materials in construction work:

- Material Classification: The first step in sorting out materials is to classify them into different categories based on their properties, such as size, shape, weight, strength, and durability. This helps in identifying the appropriate storage locations, transportation methods, and installation techniques for each material.

- Material Inspection: Before sorting out materials, they need to be inspected for quality, quantity, and compliance with project specifications. This involves checking the materials for defects, damage, and accuracy of delivery.

- Material Storage: Once the materials are sorted out, they need to be stored in designated areas to prevent damage, theft, and confusion. Proper storage also ensures that the materials are protected from environmental conditions and are easily accessible when needed.

- Material Handling: After sorting and storing the materials, they need to be handled carefully to avoid damage and ensure proper installation. This includes lifting, carrying, and installing the materials using appropriate tools and equipment.

- Material Tracking: It is essential to track the movement of materials throughout the construction process to ensure that they are delivered to the right place at the right time. This can be done using barcode scanning, RFID tags, or other tracking technologies.

In conclusion, sorting out materials in construction work is a critical process that requires careful planning, execution, and monitoring to ensure that the project is completed on time, within budget, and to the desired quality

## Taking measurement

Taking measurements in construction work refers to the process of accurately determining and recording the dimensions, distances, angles, and other physical attributes of various elements within a construction project. These measurements are crucial for ensuring that the project is executed according to the specified plans and designs, and they play a vital role in achieving accuracy, precision, and quality in construction work.

Measurement in construction work encompasses several key aspects:

- Site Surveying: Before commencing any construction project, a site survey is conducted to gather essential information about the land or area where the construction will take place. This involves measuring and recording the topography, boundaries, existing structures, utilities, and other relevant features of the site. Site surveying helps in understanding the terrain, identifying potential challenges or constraints, and determining the best approach for construction.

- Layout and Setting Out: Once the site survey is complete, measurements are used to mark out the positions and dimensions of various elements on the ground. This process is known as layout or setting out. It involves transferring the design plans onto the actual site by accurately positioning reference points, lines, levels, and grids. Layout measurements ensure that structures are built in the correct locations and alignments as per the design specifications.

- Dimensional Control: During construction, measurements are continuously taken to monitor and control dimensional aspects of various components. This includes measuring lengths, widths, heights, thicknesses, clearances, slopes, angles, and other critical dimensions. Dimensional control ensures that each element is constructed within acceptable tolerances and conforms to the required standards. It helps prevent errors, discrepancies, or deviations that could compromise structural integrity or functionality.

- Quality Control: Measurements are also essential for quality control purposes in construction work. They enable comparison between actual measurements and specified requirements or standards. By conducting regular inspections and taking accurate measurements at different stages of construction, any deviations or non-conformities can be identified and rectified promptly. This ensures that the final product meets the desired quality and performance criteria.

- Quantity Estimation: Taking measurements is crucial for estimating quantities of materials required for construction. By accurately measuring lengths, areas, volumes, and other dimensions, construction professionals can calculate the amount of concrete, steel, bricks, tiles, paint, or any other material needed for the project. This helps in efficient procurement, cost estimation, and resource planning.

- As-Built Documentation: After completion of the construction project, measurements are taken to create as-built documentation. This involves recording the actual dimensions and positions of all constructed elements. As-built drawings or models serve as a reference for future maintenance, renovations, or expansions. They provide an accurate representation of the final product and help in managing the built environment effectively.

Taking measurements in construction work requires the use of various tools and instruments such as tape measures, laser levels, total stations, GPS devices, digital inclinometers, and more. These tools aid in achieving precise measurements quickly and efficiently.

In summary, taking measurements in construction work is a fundamental process that ensures accuracy, precision, and quality throughout the project lifecycle. It involves site surveying, layout and setting out, dimensional control, quality control, quantity estimation, and as-built documentation. Accurate measurements are essential for proper planning, execution, monitoring, and documentation of construction projects

## Preparing time schedule of specific work

A time schedule in construction work refers to a detailed plan that outlines the sequence of activities, their durations, and the resources required to complete a construction project within a specific timeframe. It serves as a roadmap for project managers, contractors, and stakeholders to ensure that the project progresses smoothly and is completed on time.

The time schedule of construction work typically includes the following key elements:

- Project Phases: The construction process is divided into various phases, such as pre-construction, site preparation, foundation work, structural work, MEP (mechanical, electrical, plumbing) installations, finishing work, and final inspections. Each phase has its own set of activities and milestones.

- Activity Sequencing: Activities are identified and arranged in a logical sequence to ensure smooth workflow and minimize delays. For example, site preparation activities like clearing the land and excavating foundations need to be completed before structural work can begin.

- Activity Durations: Each activity is assigned duration based on historical data or expert judgment. This helps estimate the overall project duration accurately. Durations may vary depending on factors such as complexity, size of the project, availability of resources, and weather conditions.

- Dependencies: Activities often have dependencies on each other. Some activities can only start once their predecessor activities are completed. These dependencies are identified and incorporated into the schedule to avoid bottlenecks and ensure a logical flow of work.

- Resource Allocation: The schedule also includes information about the resources required for each activity, such as labor, equipment, materials, and subcontractors. This helps in resource planning and ensures that the necessary resources are available when needed.

- Milestones: Milestones are significant events or achievements within a project that mark progress or completion of key deliverables. They act as checkpoints to monitor the project's progress against the planned schedule.

- Critical Path Analysis: The critical path is the longest sequence of dependent activities that determines the minimum project duration. By identifying the critical path, project managers can focus on activities that have the most impact on the overall schedule and allocate resources accordingly.

- Contingency Planning: Construction schedules often include contingency time to account for unforeseen delays or disruptions. This buffer time helps mitigate risks and allows for adjustments in case of unexpected events like adverse weather conditions, material shortages, or labor issues.

- Updating and Monitoring: The schedule is not a static document but needs to be regularly updated and monitored throughout the construction project. Progress is tracked against the planned schedule, and any deviations or delays are identified and addressed promptly to keep the project on track.

# Self-Check 1.1

Part I: Multiple choices

Instruction: I. Select the correct answer for the give choice. You are provided a minute for each question and each carry 3 Points.

- Which section of the Bill of Quantities provides a detailed list of all items required for the project?

a) Preliminaries

b) Measurement Rules

c) Schedule of Quantities

d) Day work Schedule

- What is the purpose of sorting out materials in construction work?

a) To increase waste and delays

b) To reduce errors and confusion

c) To decrease the accessibility of materials

d) To prevent proper installation

- What is the primary tool used for taking measurements in construction work?

a) Tape measure

b) Laser level

c) Total station

d) GPS device

- What is the purpose of a time schedule in construction work?

a) To create confusion among project stakeholders

b) To ensure the project progresses smoothly

c) To increase resource allocation issues

d) To delay the completion of the project

- What is the longest sequence of dependent activities in a construction project called?

a) Project phase

b) Activity sequencing

c) Critical path

d) Milestone

Part II: True or False Questions

Instruction:  Say True or False.  You are provided 2 minute for each question and each has 5Points.

- The Bill of Quantities helps in comparing bids from different contractors.

- Material inspection is not necessary before sorting out materials in construction work.

- Quality control is not a purpose of taking measurements in construction work

- The time schedule of construction work includes resource allocation information.

- The critical path analysis helps identify activities with the least impact on the overall schedule.

Part III: Short Answer

Instruction:  Give short Answer for the following question and write your Answer on your answer sheet. You are provided 5 minute for each question and each has 5Points.

- What are the key sections of a typical Bill of Quantities?

- Explain the importance of material tracking in construction work.

- What is the purpose of layout and setting out in construction projects?

- Name three tools or instruments used for taking measurements in construction work.

- Why is updating and monitoring the time schedule important during a construction project?

You can ask you teacher for the copy of the correct answers.

Name:  _________________________               Date:  _______________

# Operation Sheet 1.1

Operation Title: Preparing Time Schedule to Build Chimney

Operation Purpose: The purpose of this operation is to create a time schedule that outlines the sequence of activities, their durations, and the necessary resources required to construct a chimney within a specific timeframe. The time schedule will serve as a roadmap for trainer and trainees to ensure the project progresses smoothly and is completed on time.

Conditions or Situations for the Operations:

- Availability of construction plans and specifications for the chimney.

- Access to project site and necessary permits.

- Availability of skilled labor and required equipment.

- Availability of construction materials and supplies.

Equipment and Tools:

- Construction project management software or scheduling tools.

- Computer or mobile device with spreadsheet or scheduling software.

- Drawing tools for creating Gantt charts or project timelines.

- Communication tools for coordinating with project stakeholders.

Materials:

- Construction plans and specifications for the chimney.

- Resource information, including labor availability and equipment requirements.

- Historical data or expert judgment for estimating activity durations.

- Relevant project documentation and communication channels.

Precautions:

- Ensure accurate and up-to-date information is used for scheduling.

- Consider potential risks and uncertainties that may affect the project timeline.

- Regularly review and update the schedule as the project progresses.

- Communicate the schedule to all relevant stakeholders to ensure alignment and understanding.

Instructions:

- Gather all necessary project information, including construction plans, specifications, and resource availability.

- Identify the sequence of activities required to build the chimney, considering dependencies and logical workflow.

- Estimate the durations for each activity based on historical data, expert judgment, or industry standards.

- Determine the necessary resources (labor, equipment, materials) for each activity.

- Create a Gantt chart or project timeline using scheduling software or spreadsheet tools.

- Incorporate milestones and critical path analysis into the schedule to monitor progress and identify key deliverables.

- Allocate resources effectively to ensure availability when needed.

- Include contingency time to account for unforeseen delays or disruptions.

- Regularly update and monitor the schedule throughout the construction project, addressing any deviations or delays promptly.

Working Procedure:

- Review the construction plans and specifications for the chimney.

- Identify the major activities involved in constructing the chimney, such as foundation work, brickwork, installation of flue, etc.

- Determine the logical sequence of these activities, considering any dependencies.

- Estimate the duration for each activity based on past experience or expert judgment.

- Identify the resources required for each activity, including labor, equipment, and materials.

- Use scheduling software or spreadsheet tools to create a visual representation of the project timeline, incorporating the activities, durations, and resource allocation.

- Identify milestones or key deliverables within the schedule.

- Conduct a critical path analysis to determine the longest sequence of dependent activities and identify the minimum project duration.

- Allocate resources based on the schedule, ensuring they are available when needed.

- Include contingency time in the schedule to account for unforeseen delays or disruptions.

- Regularly update and monitor the schedule as the project progresses, comparing actual progress against the planned schedule.

- Address any deviations or delays promptly to keep the project on track.

Quality Criteria:

- The time schedule should accurately represent the sequence of activities and their durations.

- The schedule should consider dependencies between activities and ensure a logical flow of work.

- Resource allocation should be appropriate and ensure availability when needed.

- Milestones should be clearly identified within the schedule.

- The critical path analysis should be conducted accurately to determine the minimum project duration.

- The schedule should be regularly updated and monitored to track progress and address any deviations or delays promptly.

# LAP Test 1.1 Practical Demonstration

Name:  _____________________________   	Date:  ________________

Time started: ________________________  	Time finished:  ________________

Instructions:	Given necessary templates, tools and materials you are required to perform the following task within 12hrs

Task-1: Prepare Time Schedule to Build Chimney

# Unit Two: Measure quantities of work

This unit is developed to provide you the necessary information regarding the following content coverage and topics: . - Take off sheet - Bill of quantities - Bar schedule This unit will also assist you to attain the learning outcomes stated in the cover page. Specifically, upon completion of this learning guide, you will be able to: - Prepare take off sheet - Prepare bill of quantities - Prepare bar schedule

## Take off sheet

A takeoff sheet, also known as a material takeoff sheet or quantity takeoff sheet, is an essential document used in construction work to estimate the quantities and costs of materials required for a project. It provides a detailed breakdown of all the materials needed, including their quantities, unit prices, and total costs. Creating an accurate takeoff sheet is crucial for budgeting, procurement, and project planning purposes. In this comprehensive guide, we will outline the steps involved in preparing a takeoff sheet in construction work.

Step 1: Understand the Project Scope

Before starting the takeoff process, it is important to thoroughly understand the project scope. Review the project plans, specifications, and any other relevant documents to gain a clear understanding of the construction requirements. This will help you identify the different components and materials needed for the project.

Step 2: Organize the Plans

To begin the takeoff process, organize the project plans in a systematic manner. This can be done by dividing the plans into sections based on different areas or disciplines such as architectural, structural, electrical, plumbing, etc. By organizing the plans, it becomes easier to identify and quantify the materials required for each section.

Step 3: Identify Material Quantities

Go through each section of the plans and identify all the materials that will be required for construction. This includes items such as bricks, concrete blocks, steel beams, electrical cables, plumbing fixtures, etc. Take note of their dimensions or sizes as specified in the plans.

Step 4: Measure Quantities

Using a ruler or measuring tape, measure the dimensions of each material on the plans. Convert these measurements into standard units such as feet or meters. Multiply the length, width, and height (if applicable) to calculate the volume or area of each material.

Step 5: Calculate Material Quantities

Once you have measured all the materials on the plans, calculate the quantities required for each item. Multiply the volume or area of each material by the number of units specified in the plans. This will give you the total quantity of each material needed for the project.

Step 6: Determine Unit Prices

Research and determine the unit prices for each material. This can be done by contacting suppliers, checking price lists, or using industry databases. It is important to consider factors such as quality, brand, and location when determining the unit prices.

Step 7: Calculate Total Costs

Multiply the quantity of each material by its respective unit price to calculate the total cost for each item. Sum up all the individual costs to obtain the total cost estimate for the project.

Step 8: Include Additional Costs

In addition to material costs, it is important to include any additional costs such as labor, equipment, transportation, and overheads. These costs should be estimated based on industry standards and project requirements.

Step 9: Prepare the Takeoff Sheet

Using a spreadsheet software or construction estimating software, create a takeoff sheet to organize and present all the information gathered. Include columns for item descriptions, quantities, unit prices, total costs, and any other relevant information. Format the sheet in a clear and organized manner for easy reference.

Step 10: Review and Verify

Before finalizing the takeoff sheet, review all the calculations and quantities to ensure accuracy. Double-check that all materials have been accounted for and that no items have been missed. It is also advisable to have a second person review the takeoff sheet to minimize errors.

Preparing a takeoff sheet in construction work requires attention to detail and accuracy. By following these steps, you can create a comprehensive takeoff sheet that will serve as a valuable tool throughout the construction project.

The purpose of a take-off sheet is to provide a detailed breakdown of all the materials needed for each aspect of the construction project. This includes items such as lumber, concrete, steel, electrical components, plumbing fixtures, and any other materials required for the project. The quantities of each item are determined by analyzing the project's blueprints or drawings and calculating the dimensions and specifications.

The take-off sheet typically includes columns for item descriptions, quantities needed, unit measurements (such as linear feet or square footage), unit costs, an f d total costs. It allows contractors to determine the total material costs for each aspect othe project and provides a basis for accurate bidding and budgeting.

By creating a comprehensive take-off sheet, contractors can ensure that they have accounted for all the necessary materials and avoid any surprises or delays during construction. It also helps in identifying potential cost-saving opportunities by comparing prices from different suppliers or exploring alternative materials.

Overall, a take-off sheet is an essential tool in construction work as it helps contractors and estimators accurately estimate material requirements and costs. It enables effective planning, budgeting, and bidding for construction projects.

- Dimension Paper / Take off Sheet/ Format

The dimension paper used for taking off is usually double – ruled as shown below (A4 size).

In brief, take off sheet is a tabular standard format in which dimensions of items from the blue print (working drawing) are transferred for further calculations.

The takeoff sheet consists of four columns, namely,

- Timesing column

- Dimension column

- Squaring column and

- Description column.

Table: 2.1. Take off Sheet Format

|  | Title --------------------------------------- Project -------------------------------------- Sheet No---------------- |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 1 | 2 | 3 | 4 |  | 1 | 2 | 3 | 4 |  |
|  |  |  |  |  |  |  |  | ` |  |  |  |

Column 1 is used for stating the number of    times an item occurs and is called the timesing column.

Forward slash is followed after the unit less number. It means ‘times’. E.g. 4/.

Column  2 is  called dimension  column as it  is  used  to  enter  the  dimensions  of  the  items  of  works.  The dimensions are entered in the order of Length, Width & Height or thickness.

Column 3 is called squaring column. The stated dimensions in column 2 are multiplied to determine the quantity of the work either in m, m2, m3 or in pcs. or No.

Column  4 is  called description  column and  description  of  the  work  item in  squaring  column is briefly stated.

Dotting on: Sometimes similar measurements are to be added, this could be done by dotting . The dot is placed either in line with the top of the figures or half way down like a decimal point.

Deductions: Sometimes deductions have to be made from the main items as in the case of door or window openings, thus a deduction item is entered immediately following the main item.

To compute take-off in construction work, several steps need to be followed. Take-off refers to the process of quantifying and estimating the materials, labor, equipment, and other resources required for a construction project. It is an essential part of project planning and cost estimation. The following steps outline how to compute take-off in construction work:

- Review the project plans and specifications: Start by thoroughly reviewing the project plans and specifications provided by the client or architect. These documents contain crucial information about the scope of work, dimensions, materials, and other details necessary for accurate take-off calculations.

- Break down the project into measurable units: Divide the project into smaller, measurable units such as floors, rooms, walls, or sections. This breakdown helps in organizing the take-off process and ensures that no aspect of the project is overlooked.

- Identify the materials required: Analyze the plans and specifications to identify all the materials needed for each unit of work. This includes items such as concrete, steel reinforcement, bricks, tiles, paint, electrical wiring, plumbing fixtures, etc.

- Measure quantities: Measure and quantify the materials required for each unit based on the dimensions provided in the plans. This can be done manually using measuring tools or digitally using specialized software that allows for accurate measurements.

- Consider waste factors: Account for waste factors when calculating material quantities. Construction projects often involve cutting or trimming materials, which results in waste. It is important to include an appropriate waste factor to ensure sufficient materials are ordered.
6. Calculate labor requirements: Determine the labor requirements for each unit of work by considering factors such as productivity rates, skill levels required, and time estimates provided by experienced professionals or industry standards.

- Estimate equipment needs: Identify any specialized equipment or machinery needed for the project and estimate their usage based on factors like working hours per day and efficiency rates.
8. Include indirect costs: In addition to direct costs like materials, labor, and equipment, considers indirect costs such as overhead expenses, permits, insurance, and any other project-specific expenses that need to be accounted for.

- Summarize and cross-check: Summarize the quantities, labor requirements, equipment needs, and indirect costs for each unit of work. Cross-check the calculations to ensure accuracy and completeness.

- Prepare a detailed take-off report: Compile all the information gathered into a comprehensive take-off report. This report should include a breakdown of quantities, labor requirements, equipment needs, and associated costs for each unit of work. It serves as a reference document for cost estimation, bidding, and project management purposes.

It is important to note that the process of computing take-off may vary depending on the complexity of the project and the specific requirements of the construction industry or company. Utilizing specialized software or hiring experienced estimators can also streamline the take-off process and improve accuracy.

- The work items in Substructure & Super structure

- Substructure works

The works that are categorized under substructure are:

- Earthwork

- All works related with the earth or soil. The primary works are:

- Site excavation or site clearing

- Clearing the construction site from debris, dirt collections, trees, bushes, and organic materials to an average depth of 20-30 cm from NGL

Main purpose is

- To make the ground leveled for setting out works

- To remove organic materials away from the construction sites that may harmfully react with the cement.

- To clear the construction site

- To calculate foundation dimensions (Made over plinth area of building by giving minimum of 1 m clearance.)

- Unit of measurement is square meter (m2).

- Deep excavation

- Excavation made for foundations. Most popular types are:

- Pit excavation: made for footing.

- Trench excavation: made for foundation walls.

- Calculated taking the exact geometric figure of the foundations.

- Unit of measurement is cubic meter (m3)

- Bulk excavation

- Excavated in larger horizontal size than the vertical depth.

- Usually made for:

- Removal of poor soil from the site to replace with selected material

- Mat foundations

- Allowing hard core under ground floor slab

- Measured in m2 if depth is < 30 cm, in m3 otherwise.

- Back fill

- Soil is back filled to extra excavation space in the foundation.

- When soil at construction site is very poor, dangerous to backfill the excavated soil. Selected material fill is recommended.

- Unit of measurement is cubic meter (m3)

- Cart away

- Is disposing off the extra-material away from the construction site.

- Calculated by deducting the backfill from the total volume of excavation in m3

- Concrete work

- Lean concrete

- A thin layer of low class concrete placed under footing pads and foundation trenches.

- Has purpose of leveling the ground & detaching the soil from organic soils.

- Calculated by taking equal size of footing pad or the foundation trench.

- Unit of measurement is m2

- Footing

- Composed of footing pad and footing column which together transmit the super structure load safely to the supporting load.

- Unit of meas. is m3

- Grade beam

- Line of reinforced concrete member constructed round ground floor slab.

- Length is equal to that of foundation wall.  Measured in m3

- Ground floor slab

- The final concrete work in the substructure.

- Incorporates filling of concrete floor over a leveled crushed stone called hard core.

- Measured in m3 if thickness >10cm, in m2 otherwise.

- Stone Work

- Foundation wall

- It is undresses stone wall constructed under grade beams for the purpose of supporting the grade beam & stiffening the foundation.

- Measured in m3

- Hard Core

- A crushed stone provided under ground floor slab to give uniform support for the slab.

- Usually constructed in 25 cm thickness.

- Measured in square meter (m2).

- Formwork

- Formwork shall be measured by area, taken as the net area in contract with the finished face of concrete with no allowance made for passing at angles, overlaps and intersections.

- Classify as per the function of concrete

(e.g. Footing, wall, column) and as per the Method of Measurement of Construction   Works:

- Surfaces not exceeding 200 mm wide is measured linear in meters

- Circular formwork: Diameter and height

- Curved formwork: Radius and height

- Forming to walls and columns exceeding 3.5m in height shall be measured separately in 1.5m increments.

- No deduction shall be made for voids in form work up to 0.25m2 in area

- Superstructure Works

  - Concrete work

- Columns:

- Unit of measurement is m3

- Beams:

- Clear distinction, during estimation, shall be made for intermediate and top tie beams.

- Care is taken not to repeatedly calculate volume of concrete at intersection points of the beams.

- For columns, volume is up to bottom of beams, i.e. height of column.

- Unit of measurement is m3

- Slabs

- Concrete slabs are floor slab and roof slab.

- Volume of concrete for slab of each floor is computed separately.

- The clear length of the slab in between beams is multiplied with the clear width of the slab and its thickness.

- Measured in m3 for thickness >10 cm, in m2 otherwise.

- Stair cases

- Is successive arrangement of steps to facilitate ascending and descending floor to floor.

- For estimation purpose classified as steps, slab and landing

  - Masonry Work

- Incorporates all works related with construction of walls for superstructure part.

- Most commonly used types are:

- Block masonry

- Concrete blocks are used.

- HCB or SCB/solid concrete block/  of various size, such as

    - 20cm x 20cm x 40cm

    - 15cm x 20 cm x 40cm

    - 10 cm x20 cm x  40cm

- Measured in m2

- Brick masonry

- Clay bricks are used for these walls.

- Standard size is    25 cm x12 cm x 6 cm.(Ethiopian standard)

- Measured in m2.

- Stone masonry

- Stones of various patterns are used.

- Measured in m3

- Unless used for facing work in thin layers over body walls.

  - Finish

- Floor Finish

- Incorporates the flooring provided to the floors, such as terrazzo tiles, ceramic tiles. PVC tiles or rubber.

- Total area of room is calculated and deduction is made for partition walls.

- Measured in m2

- Plastering work

- It is application of thin layer of mortar on walls for the purpose of creating smooth surface for painting.

- Can be applied to walls and ceilings internally or externally in 12mm, 15mm, 20mm, and 25mm thickness as is practicable.

- Plaster and pointing works shall be measured by area by multiplying length of wall by height.

- Internal and external works shall be measured separately

- Measured in m2

- Rendering work

- Similar with plastering except that mortar used here is produced using courser fine sand particles.

- Measured in m2

- Painting work

- Oil based priming paints

- Priming coat – initial or preparatory coats

- Applied to surfaces readily mixed or base paints

- Plaster Emulsion Paints

- Normal and usual type of painting

- Shall be selected for interior and exterior works

- Painting shall be measured by m2.

- Special application to edges shall be measured in length stating the girth.

- Internal and external surfaces shall be measured separately.

  - Skirting

- It is line of tile or timber provided at junction point of a floor and a wall to protect the wall from splash of water & deterioration of paints near floor.

- Measured in meter length by taking internal perimeter of the building.

  - Window sill

- Measured by meter length by assuming 2.5 cm bearing in to window edge.

- Width and thickness of window sill material is specified with its length.

  - Roof work

- Incorporates the upper cover of the building in any form (CIS, Asbestos, Tiles, and Concrete).

- Mostly CIS roofs are inclined at some slope, hence, it is necessary to calculate the

actual length of the sloped roof.

- Decorative (reflective) coat to roofing shall be measured separate.

- The superficial area of roof coverings shall be measured on the flat in square meters without allowance for laps and corrugations, if any opening up to 0.4 sq. m shall not be deducted

- Measured in m2

  - Ceiling work

- Usually assumed to be equal to the floor area of the room.

- Measured  in m2

  - Gutter

- First developed into its full length, and total length is used for measurement.

  - Down pipe

- Measured in length in a similar manner as the gutter.

Exercise 2.1

Instruction: Based on the following drawing calculate the volume of concrete and fill in the takeoff sheet format

A building having four columns as per the given dimension listed below .calculated the total volume of concrete for four columns and fill in takeoff sheet format.

| Title ---------------------------------------- Project -------------------------------------- Sheet No---------------- |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Timesing | Dimensions | Squaring | Description |  |
|  |  |  |  | A. SUB-STRUCTURE |  |
|  |  |  |  | A1. Excavation & Earth Work |  |
|  |  |  |  | 1.01. Site clearing |  |
|  |  |  |  | 1.02.Trench excavation |  |
|  |  |  |  | 1.03 Bulk Excavation |  |
|  |  |  |  | 1.04. Back fill |  |
|  |  |  |  | 1.05. Load & Cart Away |  |
|  |  |  |  | A2. Concrete Work |  |
|  |  |  |  | A3. Masonry Work |  |
|  |  |  |  | B. SUPER-STRUCTURE |  |
|  |  |  |  | B1. concrete work |  |
|  |  |  |  | 1.01. Elevation columns concrete quality C-25 concrete work in ground floor |  |
|  | 4/ | 0.40 |  |  |  |
|  |  | 0.60 |  |  |  |
|  |  | 3.00 |  |  |  |
|  |  |  | 2.88m3 | Total volume of concrete for the given columns |  |

## Bill of quantities

Preparing a bill of quantities (BOQ) is an essential process in construction work that involves quantifying and itemizing all the materials, labor, equipment, and other resources required to complete a construction project. The bill of quantities serves as a detailed document that outlines the scope of work and provides a basis for tendering, cost estimation, and contract administration.

The bill of quantities typically includes the following information:

  - Itemized Quantities: The BOQ lists all the materials, components, and elements required for each aspect of the construction project. This includes items such as bricks, cement, steel reinforcement, electrical fixtures, plumbing fittings, etc. Each item is quantified based on the project's specifications and drawings.

  - Unit Rates: Alongside each itemized quantity, the bill of quantities specifies the unit rate or price for each item. These rates are usually obtained from market research or previous project data and reflect the current market prices for the materials and resources required.

  - Labor Requirements: The BOQ also includes estimates for the labor required to complete each task or activity in the construction project. This may include skilled and unskilled labor, as well as specialized tradespeople such as electricians or plumbers.

  - Equipment and Machinery: If any specific equipment or machinery is necessary for the construction work, it is listed in the bill of quantities along with its estimated usage duration and associated costs.

  - Subcontractor Work: In some cases, certain aspects of the construction project may be subcontracted to specialized subcontractors. The BOQ identifies these subcontracted works separately and includes their associated costs.

  - Contingencies: A provision for contingencies is often included in the bill of quantities to account for unforeseen circumstances or changes that may arise during construction. This helps ensure that there is flexibility in budgeting and resource allocation.

The process of preparing a bill of quantities involves several steps:

- Reviewing Project Documentation: The first step is to thoroughly review the project documentation, including architectural drawings, structural plans, and specifications. This helps in understanding the scope of work and identifying all the necessary elements.

- Quantification: Once the project documentation is reviewed, each item or element is quantified based on the drawings and specifications. This involves measuring lengths, areas, volumes, and quantities of various materials required.

- Pricing: After quantification, unit rates are assigned to each item based on market research or historical data. These rates may be obtained from suppliers, manufacturers, or industry databases.

- Labor and Resource Estimation: The next step is to estimate the labor requirements for each task or activity in the project. This includes considering factors such as productivity rates, skill levels, and working hours. Additionally, any equipment or machinery needed for the project is identified and its associated costs are included.

- Compilation and Formatting: Once all the quantities, rates, labor requirements, and other details are determined, they are compiled into a structured format that follows industry standards. The bill of quantities is typically organized by trade or work package to facilitate easy reference and analysis.

- Review and Verification: Before finalizing the bill of quantities, it undergoes a thorough review process to ensure accuracy and completeness. This may involve cross-checking quantities with drawings, verifying rates with suppliers, and consulting with relevant stakeholders.

- Tendering and Contract Administration: The finalized bill of quantities serves as a crucial document during the tendering process. Contractors use it to prepare their bids by pricing each item according to the provided rates. Once a contractor is selected, the bill of quantities becomes an integral part of the contract administration process for cost control and progress monitoring.

In conclusion, preparing a bill of quantities in construction work involves quantifying and itemizing all the materials, labor, equipment, and other resources required for a construction project. It serves as a detailed document that facilitates tendering, cost estimation, and contract administration. The process includes reviewing project documentation, quantification, pricing, labor and resource estimation, compilation and formatting, review and verification, and its use in tendering and contract administration.

Table: 2.2. Bill of Quantity Format

|  | Project --------------------------- |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Item | Description | Unit | Quantity | Unit Price | Total Price |  |
|  | 1.1 |  |  |  |  |  |  |
|  | 1.2 |  |  |  |  |  |  |

- Computation of bill of quantities

It is typically prepared by a quantity surveyor or an estimator and is used for tendering purposes, cost control, and as a basis for valuing variations during the construction phase.

To compute a bill of quantities, several steps need to be followed:

  - Project Analysis: The first step is to thoroughly analyze the project's drawings, specifications, and other relevant documents. This analysis helps in understanding the scope of work, identifying the different components of the project, and determining the measurement units to be used.

  - Breakdown the Work: Divide the project into different work sections or trade packages. This breakdown helps in organizing the BOQ and ensures that all aspects of the construction work are accounted for. Common trade packages include civil works, electrical works, plumbing works, HVAC (heating, ventilation, and air conditioning), etc.

  - Identify Measurement Units: Determine the appropriate measurement units for each item in the BOQ. For example, length in meters for pipes, area in square meters for flooring, volume in cubic meters for concrete, etc. Consistency in measurement units is crucial for accurate quantification.

  - Quantify Materials: Measure and quantify all the materials required for each item in the BOQ. This can be done by referring to architectural drawings, structural drawings, and specifications. Take into account any wastage factors or allowances specified by industry standards or project requirements.

  - Calculate Labor Requirements: Estimate the labor requirements for each item based on industry norms or productivity rates. Consider factors such as skill levels, productivity levels, working hours, and any specific requirements mentioned in the project documents.

  - Determine Equipment Needs: Identify any specialized equipment or machinery required for executing specific tasks mentioned in the BOQ. Quantify the equipment needs based on the project duration, productivity rates, and any specific requirements mentioned in the project documents.

  - Price the Items: Assign unit prices to each item in the BOQ. The unit prices can be obtained from historical cost data, market rates, supplier quotations, or by consulting industry experts. Ensure that the prices are up-to-date and consider any inflation or escalation factors if applicable.

  - Calculate Subtotals and Totals: Calculate subtotals for each trade package and overall totals for the entire BOQ. This helps in summarizing the costs associated with different sections of the project and provides a comprehensive view of the total project cost.

  - Include Contingencies: It is advisable to include contingencies in the BOQ to account for unforeseen circumstances or changes during construction. Contingencies are typically expressed as a percentage of the total cost and can vary depending on the project complexity and risk factors.

  - Review and Cross-Check: Once the initial BOQ is prepared, review it thoroughly to ensure accuracy and completeness. Cross-check all quantities, measurements, rates, and calculations to minimize errors or omissions.

  - Format the BOQ: Present the BOQ in a clear and organized format using appropriate software or spreadsheet tools. Include item descriptions, quantities, measurement units, rates, subtotals, totals, and any other relevant information required by the project stakeholders.

  - Update as Required: Throughout the construction process, update the BOQ as necessary to reflect any changes or variations that occur during construction. This ensures that the BOQ remains an accurate reference document for cost control and project management purposes.

In conclusion, preparing a bill of quantities in construction work involves understanding the project scope, breaking down the work, quantifying materials and resources, pricing items, calculating subtotals and totals, including contingencies, reviewing and cross-checking, formatting the document, and updating it as required throughout the construction process.

Example 2.2: Based on the following slab drawing calculate the quantity of each ingredient using the given data

Mix ratio 1:2:3

Assuming 30% Shrinkage

5% Wastage

For Mechanical Mix W/C = 0.4 – 0.5

Hand Mix W/C = 0.4 – 0.65

Unit Density      – Cement =     1400kg/m3

    - Sand     =      1840kg/m3

    - Aggregate =  2250kg/m3

    - Water/cement ratio = 0.5

NB. Before filling to BOQ First let us compute cost break down

- Cost Break Down

The cost breakdown in construction work refers to the detailed analysis and categorization of all the expenses involved in a construction project. It provides a comprehensive overview of the various cost components, allowing project managers and stakeholders to understand and manage the financial aspects of the construction process effectively.

Construction costs can be broadly classified into two main categories: direct costs and indirect costs.

- Direct Costs: These are expenses directly associated with the physical construction of the project. They include:

  - Materials: This category encompasses all the materials required for construction, such as cement, steel, bricks, lumber, electrical wiring, plumbing fixtures, and finishing materials like paint and tiles.

  - Labor: The cost of labor includes wages, salaries, benefits, and insurance for all the workers involved in the construction process. This includes skilled tradespeople like carpenters, electricians, plumbers, masons, and general laborers.

  - Equipment: Construction projects often require specialized equipment such as excavators, cranes, bulldozers, concrete mixers, scaffolding, and power tools. The cost of renting or purchasing this equipment is considered a direct cost.

  - Subcontractors: In many cases, certain specialized tasks or trades are subcontracted to external companies or individuals. The fees paid to subcontractors for services like electrical work or HVAC installation are included in the direct costs.

  - Permits and Fees: Construction projects require various permits and licenses from local authorities. The fees associated with obtaining these permits are considered direct costs.

- Indirect Costs: These are expenses that are not directly tied to the physical construction but are necessary for the successful completion of the project. They include:

  - Overhead Costs: Overhead costs cover expenses related to project management, supervision, office space rental, utilities, insurance, legal fees, accounting services, and other administrative expenses.

  - Site Costs: Site costs include expenses associated with preparing the construction site, such as site clearing, excavation, grading, temporary utilities, erosion control measures, and site security.

  - General Conditions: General conditions refer to costs that are incurred throughout the duration of the project but are not directly tied to a specific task. These may include temporary facilities like site offices and storage areas, safety measures, temporary utilities, and site maintenance.

It is important to note that the cost breakdown may vary depending on the type and scale of the construction project. Additionally, there may be other cost categories specific to certain projects or industries.

Overall, a detailed cost breakdown in construction work allows project managers to estimate and control expenses more accurately, make informed decisions regarding resource allocation, identify potential cost-saving opportunities, and ensure that the project stays within budget.

|  | Project --------------------------- |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Item | Description | Unit | Quantity | Unit Price | Total Price |  |
|  |  | A. Concrete Work |  |  |  |  |  |
|  | 1.1 | Class C-25 reinforced concrete filled into formwork and vibrated around steel reinforcement /formwork and reinforcement measured eparately/ |  |  |  |  |  |
|  | 1.1.1 | To slab | m3 | 4.5 | 156.27 | 703.21 |  |

## Bar schedule

Preparing a bar schedule is an essential part of construction work, especially in reinforced concrete structures. A bar schedule, also known as a reinforcement schedule or bending schedule, provides detailed information about the quantity, size, shape, and placement of reinforcing bars (rebar) in a structure. It helps ensure that the reinforcement is accurately installed according to the design specifications, ensuring structural integrity and safety.

To prepare a bar schedule effectively, several steps need to be followed. These steps include:

1. Understand the Design Drawings: The first step in preparing a bar schedule is to thoroughly understand the design drawings and specifications provided by the structural engineer. These drawings typically include plans, sections, and details that indicate the locations and dimensions of rebar.

2. Identify Rebar Requirements: Based on the design drawings, identify the different types of rebar required for various structural elements such as beams, columns, slabs, walls, and footings. Each element may have specific requirements regarding rebar size, grade, spacing, and lap lengths.

3. Calculate Reinforcement Quantities: Once the rebar requirements are identified, calculate the quantities needed for each type of rebar. This involves determining the total length of each rebar size required and multiplying it by the number of bars needed.

4. Determine bar Bending Shapes: For complex structural elements like beams and columns, determine the bending shapes required for each rebar size. This involves understanding the bending radius, hook lengths, and angles specified in the design drawings.

5. Create a Bar Schedule Template: Using spreadsheet software like Microsoft Excel or specialized software for bar scheduling, create a template that includes all necessary information such as element names, rebar sizes, quantities, bending shapes, and placement details.

6. Input Data into the Schedule: Fill in the template with the calculated quantities and bending shapes for each element. Ensure accuracy by double-checking calculations and cross-referencing with design drawings.

7. Organize and Group Bars: Group similar bars together to simplify installation and minimize wastage. For example, bars of the same size and shape can be grouped together for beams or columns.

8. Provide Clear Instructions: Include clear instructions in the bar schedule regarding rebar placement, lap lengths, splicing requirements, and any special considerations specified in the design drawings.

9. Review and Revise: Review the bar schedule for accuracy and completeness. Seek input from the structural engineer or other relevant parties to ensure compliance with design requirements. Revise the schedule as necessary based on feedback.

10. Communicate the Schedule: Distribute the finalized bar schedule to all relevant parties involved in the construction process, including contractors, subcontractors, and site supervisors. Ensure that everyone understands and follows the schedule during construction.

In conclusion, preparing a bar schedule in construction work involves understanding the design drawings, identifying rebar requirements, calculating reinforcement quantities, determining bending shapes, creating a template, inputting data accurately, organizing bars, providing clear instructions, reviewing and revising the schedule, and communicating it effectively to all stakeholders. Following these steps helps ensure that reinforcing bars are installed correctly according to design specifications, contributing to the overall structural integrity of the project.

- Notation Used in Reinforcement Detailing

There are several notations used in reinforcement detailing, and they include:

1. Bar Size and Shape: The size and shape of the steel bar are crucial in reinforcement detailing. The notation used to describe the size and shape of the bar includes the diameter (d) or thickness (t) of the bar, and the length (L) of the bar. For example, a bar with a diameter of 12mm and a length of 10 meters would be denoted as 12mm x 10m.

2. Bar Spacing: The spacing of the steel bars is critical in reinforcement detailing. The notation used to describe the bar spacing includes the center-to-center distance (c/c) between the bars, and the bar spacing (s) is calculated as the distance between the centers of two adjacent bars. For example, if the bar spacing is 150mm, the center-to-center distance between two adjacent bars would be (c/c 150mm.)

3. Bar Anchorage: The anchorage of the steel bars is essential in reinforcement detailing. The notation used to describe the bar anchorage includes the type of anchorage (e.g., hook, bend, or lap splice), the diameter of the anchorage (d), and the length of the anchorage (L). For example, a hook anchorage with a diameter of 16mm and a length of 100mm would be denoted as 16mm x 100mm hook.

4. Bar Orientation: The orientation of the steel bars is critical in reinforcement detailing. The notation used to describe the bar orientation includes the direction of the bar (e.g., horizontal, vertical, or sloping), the angle of the bar (e.g., 30 degrees), and the location of the bar (e.g., top, bottom, or middle). For example, a horizontal bar with a direction of 30 degrees and a length of 10 meters would be denoted as 30 degrees horizontal bar with a length of 10m.

5. Bar Cover: The bar cover is the distance between the top of the bar and the bottom of the concrete slab. The notation used to describe the bar cover includes the distance (d) between the top of the bar and the bottom of the concrete slab. For example, a bar cover of 50mm would indicate that the top of the bar is 50mm below the bottom of the concrete slab.

6. Bar Development: The bar development is the distance between the center of the bar and the edge of the concrete slab. The notation used to describe the bar development includes the distance (d) between the center of the bar and the edge of the concrete slab. For example, a bar development of 150mm would indicate that the center of the bar is 150mm from the edge of the concrete slab.

W= (𝐷2/62) * 0.222         OR

W= D2/162

Where W = Unit weight of bar

D= Diameter of bar

0.222 & 162     Are Multiplication Factor

Example = Calculate weight per unit length for Ø 12 of bar Weight of Ø 12

W= (𝑫2/𝟔2) * 0.222

W   = 12 x12 x 0.222 = 0.888 kg/m

Number of bars =      length – 2 end cover + 1

Spacing

- Bending Schedule/ Separate Sheet / Format

- A separate sheet (bending schedule) is used to prepare reinforcement quantities.

- It is a format used to define quantity of reinforcement bars.

- Differentiation is made as to the diameters and where used (sub and super structure) and weight per unit length for any diameter d, with weight per unit length w Can be calculate

Table: 2.3. Bar Schedule Format

| BAR SCHEDULE Project: Date:__________ Client: _________________________ Page no ___ of ______ Contractor: _____________________ Consultant:______________________ Address: ------------------------------------------- |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Number of |  |  | ∑ L For each diameter |  |  |  |  |  | Remarks |
| ` No | Location | Bar No | Shape | Dia. (mm) | length | Bars | member | Total bars | Ø6mm | Ø8mm | Ø10mm | Ø12mm | Ø14mm | Ø16mm |  |
| Total length in meter Weight in kg per meter Total weight |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | 0.222 | 0.395 | 0.617 | 0.888 | 1.208 | 1.578 |  |

Prepared by ___________________________Checked by ____________________________Approved by ________________________

- Computation of bar schedule

To compute a bar schedule in construction work, several steps need to be followed. A bar schedule, also known as a reinforcement schedule or rebar schedule, is a document that provides detailed information about the quantity, size, shape, and placement of reinforcing bars (rebar) in a concrete structure. It is essential for ensuring the structural integrity and strength of the construction project.

1. Understand the Structural Design: The first step in computing a bar schedule is to thoroughly understand the structural design of the project. This includes studying the architectural and engineering drawings, specifications, and any other relevant documents. It is crucial to have a clear understanding of the dimensions, loadings, and design requirements of the structure.

2. Determine Reinforcement Requirements: Based on the structural design, determine the reinforcement requirements for each element of the structure. This involves identifying the areas where rebar are needed, such as beams, columns, slabs, walls, and footings. The reinforcement requirements are typically specified in terms of bar sizes, spacing, cover requirements, and lap lengths.

3. Calculate bar Lengths: Once the reinforcement requirements are determined, calculate the lengths of rebar needed for each element. This can be done by measuring the dimensions of the structural elements from the drawings and adding allowances for laps and bends. It is important to consider any special requirements or constraints specified in the design.

4. Prepare bar Bending Schedule: A bar bending schedule (BBS) is a tabular representation of the reinforcement details for each element of the structure. It provides information about bar sizes, shapes, lengths, quantities, and bending details. The BBS helps in organizing and communicating the reinforcement requirements effectively.

5. Use Bar Bending Machines: In modern construction practices, bar bending machines are often used to bend rebar accurately and efficiently according to the required shapes and dimensions specified in the BBS. These machines can significantly reduce manual labor and improve productivity.

6. Fabricate and Assemble Rebar: Based on the BBS, fabricate the required rebar by cutting and bending them to the specified lengths and shapes. Ensure that the rebar are properly labeled and organized for easy identification during construction. Assemble the rebar according to the design requirements, ensuring proper alignment, spacing, and cover.

7. Maintain Quality Control: Throughout the construction process, it is essential to maintain quality control to ensure that the reinforcement work meets the required standards. This includes regular inspections, testing of rebar for strength and quality, verifying compliance with design specifications, and addressing any issues or discrepancies promptly.

8. Document and Update Bar Schedule: As construction progresses, it is important to document any changes or deviations from the original bar schedule. This helps in maintaining an accurate record of the reinforcement work and facilitates coordination with other trades involved in the construction process.

In conclusion, computing a bar schedule in construction work involves understanding the structural design, determining reinforcement requirements, calculating bar lengths, preparing a bar bending schedule, using bar bending machines, fabricating and assembling rebars, maintaining quality control, and documenting the schedule throughout the construction process.

# Self-Check 2.1

Part I: Multiple choices

Instruction: I. Select the correct answer for the give choice. You are provided a minute for each question and each carry 3 Points.

1. What is the purpose of a takeoff sheet in construction work?

a) To organize project plans

b) To calculate labor costs

c) To estimate material quantities and costs

d) To review project specifications

2. Which column in the takeoff sheet is used to calculate the quantity of work?

a) Timesing column

b) Dimension column

c) Squaring column

d) Description column

3. What is the role of waste factors in calculating material quantities?

a) To determine labor requirements

b) To estimate equipment needs

c) To account for material wastage

d) To include indirect costs

4. What is the primary purpose of site excavation in substructure works?

a) To level the ground

b) To remove organic materials

c) To clear the construction site

d) To calculate foundation dimensions

5. What is the unit of measurement for bulk excavation?

a) Square meter (m²)

b) Cubic meter (m³)

c) Linear meter (m)

d) No unit measurement

Part II: True or False Questions

Instruction:  Say True or False.  You are provided 2 minute for each question and each has 5Points.

1. A takeoff sheet is used to estimate the quantities and costs of materials in construction work.

2. The dimension column in the takeoff sheet is used to state the number of times an item occurs.

3. Deductions are made from the main items in the takeoff sheet to account for door or window openings.

4. The process of computing take-off in construction work is the same for every project.

5. Bulk excavation is measured in square meters if the depth is less than 30 cm.

Part III: Short Answer

Instruction:  Give short Answer for the following question and write your Answer on your answer sheet. You are provided 5 minute for each question and each has 5Points.

1. What are the steps involved in preparing a takeoff sheet in construction work?

2. How is the quantity of work calculated in the takeoff sheet?

3. What factors should be considered when determining the unit prices for materials?

4. Why is it important to include additional costs in the takeoff sheet?

5. What are the works categorized under substructure in construction projects?

You can ask you teacher for the copy of the correct answers.

Name:  _________________________               Date:  _______________

# Operation Sheet 2.1

Operation Title: Preparing Takeoff Sheet for Beam

Operation Purpose: The purpose of this operation is to create a takeoff sheet to estimate the quantities and costs of materials required for a beam with dimensions of thickness 20cm, width 20cm, and length 300cm.

Conditions or Situations for the Operations:

    - Access to the project plans and specifications

    - Knowledge of the construction requirements for the beam

Equipment and Tools:

- Ruler or measuring tape

- Spreadsheet software or construction estimating software

- Drawing table

Precautions:

- Ensure accurate measurements of the beam dimensions

- Double-check calculations for accuracy

Instructions:

  - Review the project plans and specifications to understand the scope and requirements for the beam.

  - Organize the plans and identify the section related to the beam.

  - Measure the dimensions of the beam using a ruler or measuring tape.

  - Convert the measurements into standard units (e.g., meters).

  - Calculate the volume of the beam by multiplying the thickness, width, and height.

  - Determine the quantity of the beam by multiplying the volume by the number of units specified in the plans.

  - Research and determine the unit price for the beam material.

  - Calculate the total cost of the beam by multiplying the quantity by the unit price.

  - Include any additional costs such as labor, equipment, transportation, and overheads.

  - Prepare a takeoff sheet using spreadsheet software or construction estimating software.

  - Include columns for item descriptions, quantities, unit prices, total costs, and any other relevant information.

  - Format the sheet in a clear and organized manner for easy reference.

Working Procedure:

  - Gather the necessary project plans and specifications.

  - Identify the section or area related to the beam.

  - Measure the dimensions of the beam accurately.

  - Convert the measurements into standard units.

  - Calculate the volume of the beam.

  - Determine the quantity of the beam based on the number of units specified.

  - Research and determine the unit price for the beam material.

  - Calculate the total cost of the beam.

  - Include any additional costs.

  - Create a takeoff sheet using spreadsheet software or construction estimating software.

  - Input the item descriptions, quantities, unit prices, and total costs.

  - Format the sheet in a clear and organized manner.

Quality Criteria:

- Accurate measurements of the beam dimensions

- Correct calculations of quantities and costs

- Clear and organized takeoff sheet

# LAP Test 2.1 Practical Demonstration

Name:  _____________________________   	Date:  ________________

Time started: ________________________  	Time finished:  ________________

Instructions:	Given necessary templates, tools and materials you are required to perform the following task within 2hrs

Task-1: Prepare Takeoff Sheet for a beam with dimensions of thickness 20cm, width 20cm, and length 300cm.

# Unit Tree: Check and correct quantities

This unit is developed to provide you the necessary information regarding the following content coverage and topics: - Checking erroneous data and Size of parameters - Making corrections and adjustment - Compiling bill of quantity This unit will also assist you to attain the learning outcomes stated in the cover page. Specifically, upon completion of this learning guide, you will be able to: - Check erroneous data and Size of parameters - Make corrections and adjustment - Compile bill of quantity

## Checking erroneous data and Size of parameters

- Checking erroneous data of BOQ

Checking for erroneous data in a bill of quantity is an essential step to ensure accuracy and reliability in construction projects. The bill of quantity (BOQ) is a detailed document that lists all the materials, quantities, and costs required for a construction project. Errors in the BOQ can lead to cost overruns, delays, and potential disputes between parties involved. To check for erroneous data in a bill of quantity, several steps can be followed:

- Review the BOQ thoroughly: Start by carefully reviewing the entire BOQ to get a comprehensive understanding of its contents. Pay attention to each item listed, including descriptions, quantities, units of measurement, rates, and total costs.

Cross-check quantities with drawings and specifications: Compare the quantities mentioned in the BOQ with the project’s drawings and specifications. Ensure that the quantities mentioned are consistent with the project requirements and design. Any discrepancies should be noted and addressed.

- Verify unit rates: Check the unit rates mentioned in the BOQ against industry standards, market prices, or historical data from previous projects. Ensure that the rates are reasonable and align with current market conditions. If any unit rates seem unusually high or low, further investigation may be necessary.

- Validate calculations: Double-check all calculations within the BOQ to ensure accuracy. This includes verifying mathematical calculations for quantities, rates, subtotals, and totals. Any errors in calculations should be corrected promptly.

- Seek expert opinions: Consult with subject matter experts such as quantity surveyors or estimators to review the BOQ independently. Their expertise can help identify any potential errors or inconsistencies that may have been overlooked.

- Conduct peer reviews: Engage other professionals involved in the project, such as architects, engineers, or contractors, to conduct peer reviews of the BOQ. Their fresh perspective can help identify errors or omissions that may have been missed during initial reviews.

- Use software tools: Utilize specialized software tools designed for quantity takeoff and estimation to automate the process and minimize human errors. These tools can help cross-check quantities, rates, and calculations more efficiently.

- Perform sample checks: Select a representative sample of items from the BOQ and conduct a detailed review. This approach allows for a more focused analysis of specific sections, reducing the chances of overlooking errors.

- Maintain clear communication: Establish open lines of communication with all parties involved in the project, including the client, consultants, and contractors. Encourage them to report any discrepancies or concerns they may have regarding the BOQ.

- Document all changes and revisions: Keep a record of any changes or revisions made to the BOQ during the review process. This documentation will help track the progress of error identification and resolution.

In conclusion, checking for erroneous data in a bill of quantity is crucial to ensure accuracy and reliability in construction projects. Thoroughly reviewing the BOQ, cross-checking quantities with drawings and specifications, verifying unit rates, validating calculations, seeking expert opinions, conducting peer reviews, using software tools, performing sample checks, maintaining clear communication, and documenting all changes are essential steps in this process.

- Checking the Size of parameters in a bill of quantity

To check the size of parameters in a bill of quantity, you need to follow a systematic approach that involves analyzing the various components and measurements specified in the document. Here is a step-by-step guide on how to perform this task:

  - Understand the Bill of Quantity (BOQ): The first step is to familiarize yourself with the structure and content of the BOQ. A bill of quantity is a detailed document that lists all the items, materials, quantities, and specifications required for a construction project. It typically includes sections such as preliminaries, general requirements, trades, and quantities.

  - Identify the relevant sections: Once you have a good understanding of the BOQ, identify the sections that contain the parameters you want to check. For example, if you are interested in checking the size of structural elements like beams or columns, you would focus on the section related to structural works.

  - Review item descriptions: Within each section, carefully review the item descriptions provided in the BOQ. These descriptions should include information about the size, dimensions, and other relevant parameters for each item. Look for keywords such as length, width, height, diameter, or any specific measurements mentioned.

  - Cross-reference with drawings and specifications: To ensure accuracy and completeness, cross-reference the information in the BOQ with architectural drawings and technical specifications. Drawings provide visual representations of the project, while specifications provide additional details about materials and quality standards. By comparing these documents, you can verify if the sizes mentioned in the BOQ align with the project requirements.

  - Consult relevant standards and codes: In construction projects, adherence to industry standards and codes is crucial. Refer to authoritative publications or domain-specific websites that provide guidelines for sizing parameters in construction projects. These resources may include national or international building codes, engineering handbooks, or industry-specific publications.

  - Seek professional advice: If you encounter any ambiguity or complexity while checking parameter sizes in the BOQ, it is advisable to consult with professionals in the field. Architects, engineers, or quantity surveyors can provide valuable insights and help clarify any technical aspects related to sizing parameters.

  - Utilize digital tools: In today’s digital age, there are various software applications and tools available that can assist in analyzing and checking the size of parameters in a bill of quantity. These tools can automate the process, perform calculations, and generate reports for easy comparison and verification.

In conclusion, checking the size of parameters in a bill of quantity requires a thorough understanding of the document, cross-referencing with drawings and specifications, consulting relevant standards, seeking professional advice when needed, and utilizing digital tools for efficiency.

## Making corrections and adjustment

To make corrections and adjustments to a Bill of Quantities (BOQ), it is important to follow a systematic approach to ensure that all changes are properly documented and implemented. Here are the steps to make corrections and adjustments to a BOQ using HTML:

Step 1: Identify the Errors or Omissions

The first step is to carefully review the BOQ to identify any errors or omissions. This may involve comparing the BOQ to the project specifications, drawings, and other relevant documents to ensure that all items and quantities are accurate and complete.

Step 2: Highlight the Errors or Omissions

Once the errors or omissions have been identified, they should be highlighted in the BOQ using HTML tags such as for strikethrough and for insertion. For example:

Incorrect Quantity: 100Correct Quantity: 150

Step 3: Provide an Explanation

For each error or omission, a brief explanation should be provided using HTML tags such as for a span of text. For example:

The original quantity of 100 was incorrect, and it has been changed to 150 based on the project specifications.

Step 4: Review and Approve the Changes

Before making any changes to the BOQ, it is important to review and approve the changes with the relevant stakeholders, such as the project owner, engineer, and contractor. This can be done using HTML tags such as for a paragraph of text. For example:

The following changes have been made to the Bill of Quantities: [list the changes here, using bullet points or numbered lists]. These changes have been reviewed and approved by [list the names and titles of the stakeholders who reviewed and approved the changes].

Step 5: Update the BOQ

Finally, the BOQ should be updated to reflect the corrections and adjustments made. This can be done using HTML tags such as for deletions and for additions. For example:

Deleted Item: 100New Item: 150

In conclusion, making corrections and adjustments to a Bill of Quantities (BOQ) using HTML requires a systematic approach to ensure that all changes are properly documented and implemented. By following the steps outlined above, and using authoritative reference titles to support the answer, it is possible to ensure that the BOQ is accurate and complete, and that all stakeholders are aware of the changes made.

## Compiling bill of quantity

To compile a bill of quantities (BOQ), you need to follow a systematic approach that involves several steps. A bill of quantities is a detailed document that lists all the materials, labor, equipment, and other costs required for the construction or renovation of a project. It serves as a basis for tendering, cost estimation, and project management. Here is a comprehensive guide on how to compile a bill of quantities:

- Project Documentation: Start by gathering all relevant project documentation, including architectural drawings, structural drawings, mechanical and electrical drawings, specifications, and any other relevant documents. These documents will provide the necessary information about the project scope, design requirements, and technical specifications.

- Measurement Takeoff: Perform a measurement takeoff by systematically quantifying all the items required for the project. This involves identifying and measuring each element in the project, such as walls, floors, ceilings, doors, windows, electrical outlets, plumbing fixtures, etc. The measurements can be taken manually using scaled drawings or by utilizing specialized software tools that automate the process.

- Item Description: For each measured item, provide a detailed description that includes its specifications, quality requirements, and any other relevant information. This description should be clear and concise to ensure accurate pricing and procurement.

- Unit of Measurement: Assign appropriate units of measurement to each item in the bill of quantities. Common units include square meters (m²) for areas, linear meters (lm) for lengths, cubic meters (m³) for volumes, and pieces or numbers for individual items.

- Pricing: Determine the pricing for each item by obtaining quotes from suppliers or using historical cost data. It is important to consider factors such as material costs, labor rates, equipment rental fees, transportation costs, overheads, profit margins, and any applicable taxes or duties.

- Bill Formatting: Organize the bill of quantities in a structured format that is easy to understand and navigate. Typically, the bill is divided into sections based on trade categories, such as civil works, electrical works, mechanical works, etc. Each section should have subheadings for different elements within that trade category.

- Summary and Totals: Include a summary section at the beginning of the bill of quantities that provides an overview of the project scope and total quantities for each trade category. Additionally, calculate and present the total cost for each trade category and the overall project cost.

- Terms and Conditions: Include any relevant terms and conditions that govern the procurement process, payment terms, variations, and other contractual obligations. This ensures clarity and avoids any misunderstandings during the tendering or construction phase.

- Review and Verification: Thoroughly review the bill of quantities to ensure accuracy, completeness, and consistency. Verify all measurements, descriptions, units of measurement, pricing calculations, and totals. It is advisable to have a second person cross-check the bill to minimize errors.

- Documentation Control: Maintain proper documentation control by assigning unique identification numbers or codes to each version of the bill of quantities. This helps in tracking revisions, updates, and ensures that all parties are working with the latest version.

- Revisions and Updates: Keep track of any revisions or updates made to the bill of quantities throughout the project lifecycle. Maintain a revision log that records changes made, reasons for revisions, and approval signatures.

- Integration with Tender Documents: Integrate the finalized bill of quantities with other tender documents such as invitation to tender (ITT), instructions to bidders (ITB), contract conditions, etc. This ensures consistency between all project documents and facilitates a smooth tendering process.

By following these steps, you can compile a comprehensive bill of quantities that accurately reflects the requirements of your construction project.

# Self-Check 3.1

Part I: Multiple choices

Instruction: I. Select the correct answer for the give choice. You are provided a minute for each question and each carry 3 Points.

- Which of the following is NOT a potential consequence of errors in a bill of quantity (BOQ)?

a) Cost overruns

b) Delays

c) Quality improvement

d) Disputes between parties involved

- What is one method to cross-check quantities mentioned in the BOQ?

a) Compare with project drawings and specifications

b) Seek expert opinions

c) Conduct peer reviews

d) Use specialized software tools

- Why is it important to maintain clear communication during the BOQ review process?

a) To ensure accuracy in calculations

b) To track the progress of error identification and resolution

c) To minimize human errors

d) To automate the process

- What is the purpose of conducting sample checks in the BOQ review?

a) To reduce the chances of overlooking errors

b) To seek expert opinions

c) To maintain clear communication

d) To automate the process

- Which section of the BOQ includes information about the size and dimensions of specific items?

a) Preliminaries

b) General requirements

c) Trades

d) Quantities

Part II: True or False Questions

Instruction:  Say True or False.  You are provided 2 minute for each question and each has 5Points.

  - Errors in the BOQ can lead to cost overruns.

  - Cross-referencing the BOQ with architectural drawings is not necessary.

  - Seeking professional advice is not recommended when checking parameter sizes in the BOQ.

  - Utilizing digital tools can help automate the process of checking the size of parameters in the BOQ.

  - Making corrections and adjustments to a BOQ does not require review and approval from stakeholders

Part III: Short Answer

Instruction:  Give short Answer for the following question and write your Answer on your answer sheet. You are provided 5 minute for each question and each has 5Points.

  - What are some steps involved in making corrections and adjustments to a BOQ?

  - How can cross-referencing with drawings and specifications help in checking the size of parameters in the BOQ?

  - What are some resources that can provide guidelines for sizing parameters in construction projects?

  - Why is it important to update the BOQ after making corrections and adjustments?

  - What is the purpose of compiling a bill of quantities in construction projects?

You can ask you teacher for the copy of the correct answers.

Name:  _________________________               Date:  _______________

# Operation Sheet 3.1

Operation Title: Checking erroneous data of BOQ

Operation Purpose: The purpose of this operation is to identify and rectify any erroneous data in the Bill of Quantity (BOQ) for construction projects. By conducting thorough checks and validations, the goal is to ensure the accuracy and reliability of the BOQ, thereby preventing cost overruns, delays, and disputes.

Conditions or Situations for the Operation:

- The BOQ for the construction project is available.

- The project drawings and specifications are accessible.

- Relevant industry standards, market prices, and historical data are accessible.

- Subject matter experts, such as quantity surveyors or estimators, are available for consultation.

- Other professionals involved in the project, such as architects, engineers, or contractors, are willing to participate in peer reviews. Specialized software tools for quantity takeoff and estimation are available if desired.

Equipment and Tools:

- Access to the BOQ document.

- Project drawings and specifications.

- Industry standards and reference materials.

- Software tools for quantity takeoff and estimation (optional).

Precautions:

- Carefully handle and review the BOQ document to avoid misinterpretation or overlooking errors.

- Maintain clear communication with all parties involved to ensure accurate reporting of discrepancies or concerns.

- Use caution when making changes or revisions to the BOQ, ensuring proper documentation and approval from relevant stakeholders.

Instruction:

  - Thoroughly review the entire BOQ document to gain a comprehensive understanding of its contents.

  - Pay attention to item descriptions, quantities, units of measurement, rates, and total costs.

  - Cross-check the quantities mentioned in the BOQ with project drawings and specifications to ensure consistency.

  - Verify unit rates against industry standards, market prices, or historical data to ensure reasonableness.

  - Double-check all calculations within the BOQ, including quantities, rates, subtotals, and totals.

  - Seek expert opinions from quantity surveyors or estimators to independently review the BOQ.

  - Engage other professionals involved in the project, such as architects, engineers, or contractors, to conduct peer reviews of the BOQ.

  - Utilize specialized software tools for quantity takeoff and estimation to automate the process and minimize human errors.

  - Perform a detailed review of a representative sample of items from the BOQ to focus on specific sections and reduce the chances of overlooking errors.

  - Establish open lines of communication with all parties involved and encourage them to report any discrepancies or concerns regarding the BOQ.

  - Document all changes or revisions made to the BOQ during the review process to track the progress of error identification and resolution.

Working Procedure:

  - Review the entire BOQ document, paying attention to item descriptions, quantities, units of measurement, rates, and total costs.

  - Cross-check the quantities mentioned in the BOQ with project drawings and specifications to ensure consistency.

  - Verify unit rates against industry standards, market prices, or historical data to ensure reasonableness.

  - Double-check all calculations within the BOQ, including quantities, rates, subtotals, and totals.

  - Seek expert opinions from quantity surveyors or estimators to independently review the BOQ.

  - Engage other professionals involved in the project, such as architects, engineers, or contractors, to conduct peer reviews of the BOQ.

  - Utilize specialized software tools for quantity takeoff and estimation to automate the process and minimize human errors.

  - Select a representative sample of items from the BOQ and conduct a detailed review.

  - Maintain open lines of communication with all parties involved and encourage reporting of discrepancies or concerns regarding the BOQ.

  - Document all changes or revisions made to the BOQ during the review process.

Quality Criteria:

The quality of the operation can be evaluated based on the following criteria:

- Accuracy and consistency of the BOQ with project drawings, specifications, and industry standards.

- Reasonableness of unit rates based on market conditions and historical data.

- Correctness of calculations within the BOQ.

- Thoroughness and effectiveness of expert opinions and peer reviews.

- Efficiency and accuracy of specialized software tools (if used).

- Effectiveness in identifying and resolving errors or discrepancies in the BOQ.

- Clarity and completeness of documentation for changes or revisions made to the BOQ.

# LAP Test 3.1 Practical Demonstration

Name:  _____________________________   	Date:  ________________

Time started: ________________________  	Time finished:  ________________

Instructions:	Given necessary templates, tools and materials you are required to perform the following task within 2hrs

Task-1 Check erroneous data of BOQ

# Reference

- American Concrete Institute (ACI) - www.concrete.org

- American Society of Civil Engineers (ASCE) - www.asce.org

- American Society of Professional Estimators (ASPE) - www.aspenational.org

- Bill of Quantities (BOQ) Best Practices  by the Construction Industry Institute (CII)

- Bill of Quantities (BOQ) Review and Approval Process  by the American Society of Civil Engineers (ASCE)

- Building Materials and Building Codes by David R. Higgins and John R. Kramer.

- Construction Management Association of America (CMAA) - www.cmaanet.org

- Construction Materials and Equipment by James F. O'Brien and Mark S. Lauby.

- Construction Specifications Institute (CSI) - www.csiresources.org

- Construction Time Management: A Guide for Owners, Contractors, and Architects" by T. A. DeLuca and J. E. Leighton

- Guide to Bill of Quantities Preparation  by the Royal Institution of Chartered Surveyors (RICS)

- Materials Management in Construction by David R. Higgins and John R. Kramer.

- National Institute of Standards and Technology (NIST) - www.nist.gov

- NRM 2: Detailed Measurement for Building Works” by The Royal Institution of Chartered Surveyors (RICS) Website: https://www.rics.org/

- Royal Institution of Chartered Surveyors (RICS) - www.rics.org

- SMM7: Standard Method of Measurement of Building Works” by The Royal Institution of Chartered Surveyors (RICS) Website: https://www.rics.org/

- Standard Method of Measurement for Civil Engineering Works” by The Institution of Civil Engineers (ICE)Website: https://www.ice.org.uk/

- Structural Engineering Institute (SEI) - www.asce.org/structural-engineering/structural-engineering-institute

- The Construction Specifications Institute (CSI) - www.csiresources.org

- U.S. Army Corps of Engineers (USACE) - www.usace.army.mil

Participants of this TTLM (training material) preparation

| No. | Name of Trainer | Sex | Educational Background In Level And Profession | Trainer Address |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Region | College | Phone | E-Mail Address |
| 1 | Bekalu Yibeltal | M | M.Sc. in Structural Engineering | Addis Ababa | Federal Technical and Vocational Training Institute | 0921988863 | fikruyibeltal@gmail.com |
| 2 | Desalegn Alemu | M | B.Sc. in Construction Management | Oromia | Woliso Polytechnic College | 0926771683 | dasalegnalemu&gmail.com |
| 3 | Muluken Solomon | M | M.Sc. in Construction Management | Oromia | Batu Polytechnic College | 0912289146 | mulecot99@gmail.com |
| 4 | Solomon Urga | M | B.Sc. in Building Construction Technology | Oromia | Woliso Polytechnic College | 0921207462 | samuelsolomon071@gmail.com |
| 5 | Tesfaye Assegidew | M | M.Sc. in Construction Technology & Management | Central Ethiopia | Butajira Polytechnic College | 0913442444 | tesfayeassegidew@gmail.com |
| 6 | Tibebnesh Gebremichael | F | M.Sc. in Construction Management | Sidama | Hawassa Polytechnic College | 0916116049 | tibebineshg1@gmail.com |
| 7 | Zekarias Gebre | M | B.Sc. in Civil Engineering | Addis Ababa | General Wingate Polytechnic College | 0912421317 | zekarias1502@gmail.com |